## Slide 1: Basics of Monitoring, Evaluation & Control
MEC-1
Outline
Relationship between Monitoring, Evaluation & Control (MEC)
How MEC differs from Quality Management
Control interventions: Preventive Action, Correction, Defect Repair, Corrective Action & Rework.
Importance of MEC.
MEC processes in the PMI perspective.
Relationship between WPD, WPI and WPR.
General ITTO model of MEC processes in PMBoK.
Readings
PMBoK, pages 47-59, 81 & 466-467.
Rita, pages 35-36, 83-90 & 134-137.
Lecture Notes.

## Slide 2: What is Monitoring, Evaluation & Control (MEC) in PM?
Monitoring , Evaluating and Controlling a Project means:
Tracking the Project to see where it is (Monitoring)
Reviewing the Project to see where it ought to be and what, if any, is the Variance (Evaluating)
Regulate the Project to bring it back on track (Controlling)
Notes: Agile, Waterfall

## Slide 3: Linking Monitoring, Evaluation & Control
Where Project is (Monitoring)
Where the Project ought to be & How much Variance (Evaluation)
How to bring Project back On Track (Control)
Notes: Agile, Waterfall

## Slide 4: MEC and Quality Management … 1/2
Quality on a Project means meeting stakeholders’ requirements and expectations wrt functionalities. The degree to which a set of inherent characteristics fulfills requirement. As such, Quality has something to do with meeting the Product Scope
Example: Successful Q Management will ensure that a construction company delivers a house exactly as per BOQS and Construction Drawings
On the other hand, MEC goes beyond the boundaries of Scope and encompasses everything Schedule, Cost, Risks, HR etc.
Notes: Agile, Waterfall

## Slide 5: MEC and Quality Management … 2/2
Example: Successful MEC will ensure that a construction company delivers the house not only exactly as per BOQS and Construction Drawings, but also:
on or before time
within the budget
with the allocated resources
with a motivated team
without confronting unplanned risks or threats
with no major issues with the stakeholders
without a communication gap
with all sub-contracts closed to the satisfaction of all parties
Notes: Agile, Waterfall

## Slide 6: Monitoring
Monitoring is gathering, measuring and recording of sufficient information about the project to help make an intelligent comparison of planned and actual performance subsequently (which is evaluation)
Information can be obtained either from formal sources like direct observation, measurement, reports, briefings, participation in review meetings, letters; or from informal sources such as casual conversations, listening to rumors, gossip etc
Monitoring is a Passive Process
» Changes nothing: conveys where the project is in terms of Money, Time, Risk, Quality, and other areas
Notes: Agile, Waterfall

## Slide 7: Evaluation
Evaluation is the process of comparing monitored data/ performance with planned (baselined) data/ performance with a view to:
  Identifying Variances or Issues
  Assessing if these Variances or Issues impact the Baselines
  Discovering Trends & Patterns
  Suggesting Solutions to Issues & Variances
Evaluation is a Passive-Active Process
May require a more formal intervention (Tech advisers or external evaluators)
Notes: Agile, Waterfall

## Slide 8: Control
Control is the process of removing the Variances analysed during Evaluation, or Issues, to bring the Project Performance in conformity with the Baselines through:
  Corrections(aka Defect Repair)
  Corrective Actions
  Preventive Actions
  Rework
(Note: Rita considers ‘Defect Repair’ to be ‘Rework’)
Notes: Agile, Waterfall

## Slide 9: Control Interventions – Correction
Correction is an intentional activity to modify a non-conforming product or product component
Differs from Corrective Action in root cause analysis only
Example
  A component coming off a production line fails QC; the component is repaired or replaced; no root cause analysis is done to investigate into the reason(s) of its failure
Correction is a reactive process
Notes: Agile, Waterfall

## Slide 10: Control Interventions – Corrective Action … 1/2
Corrective action is an intentional activity that:
  Corrects the error/non-conformity and realigns the performance of the project work with the project management plan (baselines)
  Ensures that the error/con-conformity will not recur, through root cause analysis of the error/non-conformity
Example
  A component coming off a production line fails QC; another component does the same; root cause analysis suggests inadequate curing time; proper curing time is the corrective action
Notes: Agile, Waterfall

## Slide 11: Control Interventions – Corrective Action … 2/2
Corrective Action is a reactive process
Generally, Corrective Actions are undertaken to adjust performance within the existing project Baselines and do not change them.
All Corrective actions are reviewed and approved/ rejected by the Perform Integrated Change Control process, as Approved/Rejected Changes
Those Corrective actions which affect the PMP, project Baselines, policies, procedures, charter, contracts, SOW etc require approval of the CCB or the Sponsor
Notes: Agile, Waterfall

## Slide 12: Differentiating Correction & Corrective Action
Scenario: Car Production PDI
Problem: AC of one car not working (no gas)
Fill the gas (correction)
Why no gas (RCA)?
Leaky valve
Replace leaky valve (corrective action)
Result: Car ACs clearing PDIs
Notes: Agile, Waterfall

## Slide 13: Control Interventions – Preventive Action … 1/2
Preventive Action is an intentional activity that ensures the future performance of the project work is aligned with the project management plan
Examples
Stocking building material in anticipation of price hike after budget. This action will contribute to keeping the Project Cost within budget
Working overtime to prevent time loss to the impending monsoon rains. This action will contribute to prevent the Project from slipping in schedule
Preventive Action is a proactive process
Notes: Agile, Waterfall

## Slide 14: Control Interventions – Preventive Action … 2/2
Generally, Preventive Actions are undertaken to adjust performance within the existing project Baselines and do not change them
All Preventive actions are reviewed and approved/ rejected by the Perform Integrated Change Control process, as Approved/Rejected Changes
Those Preventive actions which affect the PMP, project Baselines, policies, procedures, Charter, contracts, SOW etc require approval of the CCB or the Sponsor
Notes: Agile, Waterfall

## Slide 15: Control Interventions – Rework (Defect Repair) … 1/2
Rework, is an intentional activity to bring a defective or nonconforming product, or product component into compliance with requirements or Specifications, by modifying, or redoing the entire non-conforming product or product component
Example
  A component coming off a production line is rejected by the QC; or is rejected by the Customer at Validate Scope for its failure to meet the scope
Rework is a reactive process
Notes: Agile, Waterfall

## Slide 16: Control Interventions – Rework (Defect Repair) … 2/2
Generally, Rework entails reviewing the entire process, starting with design, resulting in a modification(s) and creates new baseline
Therefore, all Reworks are reviewed and approved/ rejected by the Perform Integrated Change Control process, as Approved/Rejected Changes
Notes: Agile, Waterfall

## Slide 17: Why MEC? Importance of MEC … 1/3
Monitoring & Controlling ascertains if the project is performing or tracking to the Baselines in the Proj Mgt Plan or if there are any Variances from the Baselines
If there are Variances, the Monitoring & Control Process generates Changes in the form of Corrections, Corrective Actions, Preventive Actions or Defect Repairs, to remove the Variances

## Slide 18: Why MEC? Importance of MEC … 2/3
Monitoring and Controlling Process is a continuous process running in the “background” of the other four Process Groups
Ref: PMBOK Guide-5th Ed (page 50)

## Slide 19: Why MEC? Importance of MEC … 3/3
Time
Level of Process Interaction
MEC spans the entire Project Life Cycle
Forms part of All Knowledge Areas except HR where MEC manifested in the ‘Manage Project Team’ process
Leads to Job Opportunities
Worst Scoring Process Group on PMP Certification Exam
Ref: PMBOK Guide-5th Ed (page 50)

## Slide 20: MEC spanning Initiation & Planning? How?
Pre-Initiation:
- Business Case: Initial MEC & Prioritisation by PMO
- Feasibility Study: MEC of Business Case
Initiation:
- Charter & Stakeholder Register: Drafts MECed by Quality Dept for Format, Content, Accuracy etc
- Completion of Stakeholder Register in terms of Influence & Interest, and handling Strategies in itself a MEC process
Planning: All Project Plans MECed by Quality Dept for Format, Content, Accuracy etc & endorsed/checked/ assured/counter-signed by a relevant Functional Manager/ Chief Officer

## Slide 21: Ignoring MEC is like burying your Head in Sand
Project
Manager

## Slide 22: MEC in PMI Perspective
PG→ | Initiating | Planning | Executing | M&C | Closing
KA↓ |  |  |  |  | 
Integration | 1 | 1 | 1 | 2 | 1
Scope |  | 4 |  | 2 | 
Time |  | 6 |  | 1 | 
Cost |  | 3 |  | 1 | 
Quality |  | 1 | 1 | 1 | 
HR |  | 1 | 3 |  | 
Comm |  | 1 | 1 | 1 | 
Risk |  | 5 |  | 1 | 
Procurement |  | 1 | 1 | 1 | 1
Stakeholder | 1 | 1 | 1 | 1 | 
8
11
2
24
2
6
6
7
4
3
4
3
6
4
4

## Slide 23: MEC in PMI Perspective
Integration | 1. M&C Proj Work 2. Perform Integrated Change Control
Scope | Validate Scope Control Scope
Time | 5. Control Schedule
Cost | 6. Control Costs
Quality | 7. Control Quality
HR | 
Comm | 8. Control Communication
Risk | 9. Control Risks
Procurement | 10. Control Procurements
Stakeholder | 11. Control Stakeholder Engagements

## Slide 24: Monitoring, Evaluation & Control Data
Work Performance Data (WPD)
Work Performance Information (WPI)
Work Performance Report (WPR)
Notes: Agile, Waterfall

## Slide 25: WPD
Raw observations & measurements identified during activities being performed to carry out the project work
eg % work completed, Q & Tech Performance Measure, Actual Costs, Actual Durations etc
Manifestation of MONITORING
Produced by the Direct & Manage Project Work process
Goes to the Respective Monitoring & Control process
Notes: Agile, Waterfall

## Slide 26: WPI
Performance Data collected from the central Direct & Manage Project Work, analyzed in context and integrated based on relationships across areas, in the respect Monitoring & Control Process
eg Variances, Status of Deliverables, Implementation Status of Change Requests, Forecasts etc
Manifestation of EVALUATION
Produced by the respective Monitoring & Control Process
Goes to the overall Project Control (Monitor & Control Project Work)
Notes: Agile, Waterfall

## Slide 27: WPR
Physical or electronic representation of work performance information compiled in project documents, by the Overall Project Control (Monitor & Control Project Work), intended to generate decisions, actions, or awareness
eg Status Reports, Memos, Information Notes, Electronic Dashboards, Briefs, Recommendations etc
Produced by the Overall Project Control
Go to the Integrated Change Control, Project Management Plan & Project Communications
Notes: Agile, Waterfall

## Slide 28: WPD → WPI → WPR Examples
WPD
Actual Duration of an Activity, Work Package etc
Actual Cost of an Activity, Work Package etc
% work completed
Approved Change Request(s)
Status Reports Memos Information Notes Electronic Dashboards Briefs Recommendations Powerpoint presentation Excel Sheet Any Spreadsheet etc
WPI
Schedule Variance (SV) Schedule Performance Index (SPI) EACtime (Forecast)
Cost Variance (CV) Cost Performance Index (CPI) EACcost (Forecast)
TCPIs (based on Work & Funds Remaining) Status of Deliverable(s)
Implementation Status of Change Requests
WPR
Notes: Agile, Waterfall

## Slide 29: WPD → WPI → WPR Flow Path
D&M Proj Work
Respective M&C Process
Overall Proj Cont (M&C Proj Work)
Integrated Change Control
WPD
WPR
WPI
Project Manage-ment Plan
Project Comm-unication
Activity X/
Comp 6 Feb/
10 days)
Activity X took 3 days more than the planned 7 days and did not complete on due date of 3 Feb. Therefore, 3 days negative Variance
Proj Status Report on Activity X (& others)
Notes: Agile, Waterfall

## Slide 30: WPD → WPI → WPR Flow Path Complete Model
Direct & Manage Proj Work
Control Scope
Control Schedule
Control Costs
Control Quality
Control Comm
Control Risks
Control Procurements
Control S/Holder Engagement
Validate Scope
WPD
WPIs
Monitor & Control Proj Work
Perform Integrated Change Control
Develop PMP
Manage Proj Team
Manage Comm
WPRs
Approved Change Requests
Project Documents Updates
Project Plan Updates
Notes: Agile, Waterfall

## Slide 31: General Input-Output Model for any M&C Process in any KA
M&C Process in any KA
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output +
Change Request#
PMP: Project Management Plan
KA: Knowledge Area
w/a: where applicable
PD: Project Document
*: from the KA Executing Process or ‘Direct & Manage Project Work’ as applicable
**: to the ‘Monitor & Control Project Work’
# : to the ‘Perform Integrated Change Control’
KA Mgt Plan
KA Baseline (w/a)
Any other Mgt Plan (w/a)
Notes: Agile, Waterfall