## Slide 1: Forecasting
MEC-10
Outline
Basic Terms
Forecasting Variations
Forecasting Methods
Naïve Method
Single Moving Averages
Centred Moving Averages
Weighted Moving Averages
Exponential Moving Averages
Regression Analysis
Readings
PMBoK, pages 92 & 238.
Rita, page 190.
Stevenson, Ch 3.
Reid, Ch 8.
Krajewski, Ch 13.
Class Notes.

## Slide 2: What is Forecasting
Forecasting is predicting FUTURE DATA using EXISTING DATA
Data can be TIME-BASED/TIME SERIES, which is sequential, or CAUSAL which is both sequential and quantitative, and one set of data is dependent on another
Forecasting methods are named after these data types
Chart: Time Series
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Series 1 | 261 | 257 | 260 | 250 | 261 | 251 | 265 | 258 | 255 | 261
Chart: Causal
| 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Series 1 | 259 | 257 | 260 | 255 | 263 | 255 | 265 | 258 | 262 | 266
y=0.1439x2-0.9167x+259.5
y=0.6667x+256.33
Naïve Method
Averaging Methods
Regression Techniques
Notes: Agile, Waterfall

## Slide 3: Forecasting Methods
Forecasting
Qualitative
Quantitative
Expert Judgement
Surveys
Meetings
Time Series
Naïve Method
Causal/ Associative
Averaging Techniques
Delphi Method
Simple Moving Averages
Weighted Moving Averages
Centred Moving Average
Exponential Moving Average
Regression Techniques
Forecasting Methods already learnt
Estimating Methods in Cost & Schedule Planning
VACs, EACs, TCPIs parts of the EVM
Notes: Agile, Waterfall

## Slide 4: Basic Terms
Time Series: A time-ordered sequence of observations, taken at regular intervals (hourly, daily, weekly, monthly, quarterly, annually)
Examples: demand, supply, earnings, profits, shipments, accidents, outputs, precipitation, productivity, indices, etc
In project management, a series of events would also constitute time-series. For example, a series of a houses in a multiple housing project
Trend: A long-term upward or downward movement in data, over a long-term
Cycle: Wavelike Variations lasting more than a year
Seasonality: A short-term regular variations related to the calendar or time of day
Irregular Variation: Variation in data series caused by unusual circumstances
Notes: Agile, Waterfall

## Slide 5: Forecasting Variations
Trend
Irregular variation
Cycle
Seasonal Variations
Seasonal Variation of Human Resources on a Project
Wheat Harvesting
Eid ul Fitr
Time →
Time →
Time →
Time →
Notes: Agile, Waterfall

## Slide 6: Naïve Method – The Simplest Forecast
Example: On a multi-housing project, the time of completion of the first 10 houses (H1 to H10) is indicated in the table. What can be the forecasted duration of House # 11 (H11)?
House # | Duration to Complete
1 | 260
2 | 245
3 | 255
4 | 246
5 | 254
6 | 243
7 | 253
8 | 242
9 | 254
10 | 248
11 | ?
Simplest Method: Forecast duration is the previous house’s (H-10’s) actual duration, i.e. 248 days.
This is the Naïve Method of forecasting and is widely used for future estimating. Sometimes, the naïve forecast is indexed to inflation/escalation/increments. For example, in this case, duration of H-11 could be 248 days+10%
Naïve Forecast: A forecast for a future period/event equals the previous period/event’s actual value
Notes: Agile, Waterfall

## Slide 7: Averaging Methods – Simple Moving Averages
Chart: 
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11
Series 1 | 260 | 245 | 255 | 246 | 254 | 243 | 253 | 242 | 254 | 248
Series 2 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
House # | Duration to Complete
1 | 260
2 | 245
3 | 255
4 | 246
5 | 254
6 | 243
7 | 253
8 | 242
9 | 254
10 | 248
11 | ?
Forecasted Duration of H11
Mean | 250.0 | Fixed Average
Mean (minus 1st) | 248.9 | (the 1st House it took longer)
Mean (last 3) | 248.0 | Moving Average at k = 3
Mean (last 5) | 248.0 | Moving Average at k = 5
Mean (last 4) | 249.3 | Moving Average at k = 4
Notes: Agile, Waterfall

## Slide 8: Averaging Methods and Data with Trend
House # | Duration to Complete
1 | 261
2 | 257
3 | 260
4 | 253
5 | 256
6 | 245
7 | 247
8 | 240
9 | 242
10 | 239
11 | ?
Chart: 
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11
Series 1 | 261 | 257 | 260 | 253 | 256 | 245 | 247 | 240 | 242 | 239
Series 2 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
Forecasted Duration of H11 |  | 
Mean | 250.0 | Fixed Average
Mean (last 3) | 240.3 | Moving Average at k = 3
Mean (last 4) | 242.0 | Moving Average at k = 4
Mean (last 5) | 242.6 | Moving Average at k = 5
Mean is still 250 but there is a Trend
Forecast for H11 based on any Averaging Method will be erratic, as evident from the chart below
Using Trend Line | 235.6
Averaging Methods generally not used when there is a Trend
Consider the data set:
Notes: Agile, Waterfall

## Slide 9: Moving Average … 1/3
Moving Average is a technique to get an overall idea of the trends in a data set; it is an average of any subset of numbers. The moving average is extremely useful for forecasting long-term trends
Example: A construction company has data on construction cost per square foot which it can use to estimate cost for the next project
Variations include: Simple, Weighted, Centred, Exponential etc
Moving Average is used to overcome irregular, random, seasonal or cyclic variations
Overcoming variations is called "smoothing“
Moving Average is a smoothing process
Notes: Agile, Waterfall

## Slide 10: Moving Average … 2/3
Smoothing by Moving Average is done by taking average of three (or more) recent observations, then dropping the first observation and advancing to the next one, and continuing the process till getting to the period/unit for which forecast is required
Each new data point is included in the average as it becomes available, and the oldest data point is discarded
The number of observations averaged is referred to as the “k” number; the constant number k is specified at the outset
The smaller the number k, the more weight is given to recent periods; the greater the number k, the less weight is given to recent periods
Notes: Agile, Waterfall

## Slide 11: Moving Average … 3/3
A large k is desirable when there are wide, infrequent fluctuations in the series, i.e. the data fluctuates gracefully
A small k is most desirable when there are sudden shifts in the level of series
For quarterly data, a four-quarter moving average, MA(4), eliminates or averages out seasonal effects
For monthly data, a 12-month moving average, MA(12), eliminate or averages out seasonal effect
Equal weights are assigned to each observation used in the average
Notes: Agile, Waterfall

## Slide 12: SMA – The Concept
House # | Duration to Complete | 
 | (a) | 
1 |  | 
2 |  | 
3 |  | 
4 |  | 
5 |  | 
6 |  | 
7 |  | 
8 |  | 
9 |  | 
10 |  | 
11 |  | 
SMA (k=3)
(b)
260
245
255
250
262
250
253
253.3
242
246.0
254
249.7
248
248.0
248.7
251.7
247.7
250.0
246
254
243
House # | Duration to Complete | 
 | (a) | 
1 |  | 
2 |  | 
3 |  | 
4 |  | 
5 |  | 
6 |  | 
7 |  | 
8 |  | 
9 |  | 
10 |  | 
11 |  | 
SMA (k=3)
(b)
260
245
255
253
253.3
242
246.0
254
249.7
248
248.0
248.7
251.7
247.7
250.0
246
254
243
Notes: Agile, Waterfall

## Slide 13: SMA – How to work out
House # | Duration to Complete | 
 | (a) | 
1 | 260 | 
2 | 245 | 
3 | 255 | 
4 | 246 | 
5 | 254 | 
6 | 243 | 
7 | 253 | 
8 | 242 | 
9 | 254 | 
10 | 248 | 
11 |  | 
SMA (k=3)
(b)
253.3
248.7
251.7
247.7
250.0
246.0
249.7
248.0
SMA (k=4)
(c)
251.5
250.0
249.5
249.0
248.0
248.0
249.3
Sum of Errors
Error Squared (k=3)
(a-b)2
53.8
28.4
75.1
28.4
64.0
64.0
2.8
316.6
45.2
6.7
Error Squared (k=4)
(a-c)2
6.3
49.0
12.3
49.0
36.0
0.0
152.6
25.4
5.0
Error (k=3)
a-b
-7.3
5.3
-8.7
5.3
-8.0
8.0
-1.7
-7.0
-1.0
Error (k=4)
(a-c)
2.5
-7.0
3.5
-7.0
6.0
0.0
-2.0
-0.3
Mean Error
Root Mean Error
RMS Error
Notes: Agile, Waterfall

## Slide 14: SMA & Data Smoothing
Chart: 
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11
Actual Durations | 260 | 245 | 255 | 246 | 254 | 243 | 253 | 242 | 254 | 248
SMA (k=3) | 253.3333 | 248.6667 | 251.6667 | 247.6667 | 250 | 246 | 249.6667 | 248
SMA (k=4) | 251.5 | 250 | 249.5 | 249 | 248 | 248 | 249.25
Chart: 
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11
Series 1 | 260 | 245 | 255 | 246 | 254 | 243 | 253 | 242 | 254 | 248
Series 2 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
Notes: Agile, Waterfall

## Slide 15: Weighted Moving Average (WMA)
WMA is used when it is required to give different weightage to different data. For example it may be required to give more weightage to recent data
Example: In the original multi-housing project example, it is required to forecast the duration of the 11th house by giving 50% weightage to the most recent house duration, 30% to the middle duration and 20% to the earliest
8 | 242
9 | 254
10 | 248
11 | Forecast = 248x0.5 + 254x0.3 + 242x0.2 = 248.6
Sum of weights must be 1 (100%). In this case 50%+30%+20%= 100%
Notes: Agile, Waterfall

## Slide 16: Centred Moving Average (CMA)
CMA is used for a number of situations particularly when there is a seasonal variation and there is a requirement to:
  work out seasonal indices
  forecast sales/demand; or
  closely track the past data;
CMA can be computed, using data equally spaced on either side of the point in the series where the mean is calculated
When k is even, “smoothing of smoothing” is done
Notes: Agile, Waterfall

## Slide 17: CMA – Close Tracking of Data
House # | Duration to Complete | SMA (k=3) | CMA (k=3) | CMA Error | CMA Error Squared
 | (a) | (b) | (c) |  | (a-c)2
1 | 260 |  |  |  | 
2 | 245 |  | 253.3 | -8.3 | 69.4
3 | 255 |  | 248.7 | 6.3 | 40.1
4 | 246 | 253.3 | 251.7 | -5.7 | 32.1
5 | 254 | 248.7 | 247.7 | 6.3 | 40.1
6 | 243 | 251.7 | 250.0 | -7.0 | 49.0
7 | 253 | 247.7 | 246.0 | 7.0 | 49.0
8 | 242 | 250.0 | 249.7 | -7.7 | 58.8
9 | 254 | 246.0 | 248.0 | 6.0 | 36.0
10 | 248 | 249.7 |  |  | 
11 |  | 248.0 |  |  | 
 |  |  |  | Sum | 374.5
 |  |  |  | Mean | 46.8
 |  |  |  | RMS | 6.8
k odd (=3)
Notes: Agile, Waterfall

## Slide 18: CMA – Close Tracking of Data
Chart: 
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11
Actual Durations | 260 | 245 | 255 | 246 | 254 | 243 | 253 | 242 | 254 | 248
SMA (k=3) | 253.3333 | 248.6667 | 251.6667 | 247.6667 | 250 | 246 | 249.6667 | 248
CMA (k=3) | 253.3333 | 248.6667 | 251.6667 | 247.6667 | 250 | 246 | 249.6667 | 248
Notes: Agile, Waterfall

## Slide 19: CMA – Close Tracking of Data
House # | Duration to Complete | 
 | (a) | 
1 | 260 | 
2 | 245 | 
3 | 255 | 
4 | 246 | 
5 | 254 | 
6 | 243 | 
7 | 253 | 
8 | 242 | 
9 | 254 | 
10 | 248 | 
11 |  | 
k even (=4)
2.5 | 251.5
3.5 | 250.0
4.5 | 249.5
5.5 | 249.0
6.5 | 248.0
7.5 | 248.0
8.5 | 249.3
3.0 | 250.75
4.0 | 249.75
5.0 | 249.25
6.0 | 248.50
7.0 | 248.0
8.0 | 248.63
Notes: Agile, Waterfall

## Slide 20: CMA – Close Tracking of Data
House # | Dur to Complete | SMA (k=4) | CMA (k=4) | CMA (k=2) | CMA Error | CMA Error Square
 | (a) | (c) |  | (c) | (a-c) | (a-c)2
1 | 260 |  |  |  |  | 
2 | 245 |  |  |  |  | 
2.5 |  |  | 251.5 |  |  | 
3 | 255 |  |  | 250.75 | 4.25 | 18.06
3.5 |  |  | 250.0 |  |  | 
4 | 246 |  |  | 249.75 | -3.75 | 14.06
4.5 |  |  | 249.5 |  |  | 
5 | 254 | 251.5 |  | 249.25 | 4.75 | 22.56
5.5 |  |  | 249.0 |  |  | 
6 | 243 | 250.0 |  | 248.50 | -5.5 | 30.25
6.5 |  |  | 248.0 |  |  | 
7 | 253 | 249.5 |  | 248.00 | 5 | 25.00
7.5 |  |  | 248.0 |  |  | 
8 | 242 | 249.0 |  | 248.63 | -6.625 | 43.89
8.5 |  |  | 249.3 |  |  | 
9 | 254 | 248.0 |  |  |  | 
10 | 248 | 248.0 |  |  |  | 
11 |  | 249.3 |  |  |  | 
 |  |  |  |  | Sum | 153.83
 |  |  |  |  | Mean | 25.64
 |  |  |  |  | RMS | 5.06
k even (=4)
Notes: Agile, Waterfall

## Slide 21: CMA – Close Tracking of Data
Chart: 
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11
Actual Durations | 260 | 245 | 255 | 246 | 254 | 243 | 253 | 242 | 254 | 248
SMA (k=4) | 251.5 | 250 | 249.5 | 249 | 248 | 248 | 249.25
CMA (k=4) | 250.75 | 249.75 | 249.25 | 248.5 | 248 | 248.625
CMA (k=3) | 253.3 | 248.7 | 251.7 | 247.7 | 250 | 246 | 249.7 | 248
Notes: Agile, Waterfall

## Slide 22: CMA – Seasonal Indices
Example:
The manager of a call centre wants to know the “Seasonal Index” for calls received between 9 and 10 a.m.
Solution: Record the volume of calls for 21 days. Say, it comes to as follows:
Day Volume Day Volume Day Volume
Mon 55 Mon 52 Mon 50
Tues 67 Tues 60 Tue 64
Wed 75 Wed 73 Wed 76
Thu 82 Thu 85 Thu 87
Fri 98 Fri 99 Fri 96
Sat 90 Sat 86 Sat 88
Sun 36 Sun 40 Sun 44
Notes: Agile, Waterfall

## Slide 23: CMA – Seasonal Indices
Day | Calls Received | SMA (k=7) | CMA (k=7) | Daily Index
 | (a) | (b) | (c) | a÷c
Mon | 55 |  |  | 
Tue | 67 |  |  | 
Wed | 75 |  |  | 
Thu | 82 |  | 71.86 | 1.14
Fri | 98 |  | 71.43 | 1.37
Sat | 90 |  | 70.43 | 1.28
Sun | 36 | 71.86 | 70.14 | 0.51
Mon | 52 | 71.43 | 70.57 | 0.74
Tue | 60 | 70.43 | 70.71 | 0.85
Wed | 73 | 70.14 | 70.14 | 1.04
Thu | 85 | 70.57 | 70.71 | 1.20
Fri | 99 | 70.71 | 70.43 | 1.41
Sat | 86 | 70.14 | 71.00 | 1.21
Sun | 40 | 70.71 | 71.43 | 0.56
Mon | 50 | 70.43 | 71.71 | 0.70
Tue | 64 | 71.00 | 71.29 | 0.90
Wed | 76 | 71.43 | 71.57 | 1.06
Thu | 87 | 71.71 | 72.14 | 1.21
Fri | 96 | 71.29 |  | 
Sat | 88 | 71.57 |  | 
Sun | 44 | 72.14 |  | 
Day (Season) | Mean Index
Mon | 0.72
Tue | 0.87
Wed | 1.05
Thu | 1.18
Fri | 1.39
Sat | 1.24
Sun | 0.54
Notes: Agile, Waterfall

## Slide 24: Exponential Moving Average (EMA)
EMA forecasts the value of next event based on:
Actual Value of the previous item
Forecasted Value of the previous item
Weight assigned
EMA weigh past observations using exponentially decreasing weights as the observations get older; recent observations are given relatively more weight than the older observations
The amount of weight applied to the past observations, or the degree of smoothing required, is determined by the “smoothing constant”
EMA is in contrast to the SMA. In SMA, the same weights (=1/n) are assigned to the observations. In EMA, there are one or more smoothing parameters to be determined (or estimated) and these choices determine the weights assigned to the observations
Notes: Agile, Waterfall

## Slide 25: EMA Equation … 1/3
The exponential smoothing equation is:
Fn+1 =  yn + (1- )Fn
where Fn+1 = Forecast for the next unit (to be estimated)
= Smoothing constant, such 0 <  ≤ 1
yn = Actual value of the most recent unit
Fn = Forecasted value of the most recent unit
Large  (say 0.9, 0.8, 0.7, 0.6 etc) would mean:
MORE consideration to the previous ACTUAL DATA;
LESS consideration to previous FORECASTED DATA
Small  (say 0.1, 0.2, 0.3, 0.4 etc) would mean:
LESS consideration to the previous ACTUAL DATA;
MORE consideration to previous FORECASTED DATA
 = 0.5 would mean:
EQUAL consideration to the previous ACTUAL DATA and the previous FORECASTED DATA, because both  and (1- ) would be 0.5 in this case
Notes: Agile, Waterfall

## Slide 26: EMA Equation … 2/3
yn | Fn
y1 = | F1=
y2 = | F2 =
y3 = | F3 =
y4 = | F4 =
y5 = | F5 =
 | F6 =
yn = | Fn =
 | Fn+1 =
←
200
275
260
←
270
F2 = y1 + (1- )F1
268
←
248
F3 = y2 + (1- )F2
= (1- )0y1 + (1- )F1
252
262
←
F4 = y3 + (1- )F3
260
250
←
F5 = y4 + (1- )F4
252
←
F6 = y5 + (1- )F5
252
260
250
←
Fn+1 = yn + (1- )Fn
= (1- )0y2 + (1- )1y1 + (1- )2F1
= (1- )0y3 + (1- )1y2 + (1- )2y1 + (1- )3F1
= (1- )0y4 + (1- )1y3 + (1- )2y2 + (1- )3y1 + (1- )4F1
Substituting the value of the previous forecasted value & rearranging:
= (1- )0y5+ (1- )1y4 + (1- )2y3 + (1- )3y2 + (1- )4y1 + (1- )5F1
= (1- )0yn + (1- )1yn-1 + (1- )2yn-2 +…….+ (1- )n-1y1 + (1- )nF1
The working shows that weightage given to the Actual past observations decreases exponentially by a factor of (1-), i.e. weightage of (1-)0 to yn, (1-)1 to yn-1 , (1- )2 to yn-2 , (1- )3 to yn-3 … (1- )n-3 to y3 , (1- )n-2 to y2 and (1- )n-1 to y1
Notes: Agile, Waterfall

## Slide 27: EMA Equation … 3/3
Another Look:
The “Exponential” aspect becomes apparent when building the Equation from F1,y1:
F2 = y1 + (1- )F1 = y1 + (1- )F1
F3 =  y2 + (1- )F2 =  y2 + (1- )[ y1 + (1- )F1]
= y2 + (1- )y1 + (1- )2F1
F4 =  y3 + (1- )F3 = y3 + (1- )[y2 + (1- ) y1 + (1- )2F1 ]
= y3 + (1- )y2 + (1- )2y1 + (1- )3F1
F5 =  y4 + (1- )F4 = y4 + (1- )y3 + (1- )2y2 + (1- )3y1+(1- )4F1
Fn+1 =  yn + (1- )Fn = yn + (1- )yn-1 + (1- )2yn-2 +….+ (1- )3y2 + (1- )4F1
= (1- )0yn + (1- )yn-1 + (1- )2yn-2 +….+ (1- )n-1y1 + (1- )nF1
Example, if  = .7, and the next event is # 5, then in forecasting F5, weightage of Actual past observations will be considered reduced exponentially by a factor of 0.3, as tabulated:
Actual Past Value | Weightage = (1- )?
y4 | 0.7(0.3)0 = 0.7
y3 | 0.7(0.3)1 = 0.21
y2 | 0.7(0.3)2 = 0.063
y1 | 0.7(0.3)3 = 0.0189
Notes: Agile, Waterfall

## Slide 28: Applying EMA
In application, EMA is a simple affair. All what is required to be done is:
  Select a suitable smoothing constant ()
  Take the most recent observation (yn) and multiply it with the smoothing constant
  Take what was the forecasted (Fn) value of the most recent observation/ event and multiply it with the complementary of the smoothing constant i.e (1- )
  Add the two products; the sum is the forecasted value for the next unit
If the forecasted value (Fn) of the recent most event is not available, then:
  Start analysing the data from the start, or from where the last (Fn) is available, by calculating Fn using the EMA equation
  Continue calculating Fn by applying the EMA equation until the forecasted value of the target event is available
Notes: Agile, Waterfall

## Slide 29: EMA – Example 1
Consider the data for the original example
yn & Fn for various values of  are tabulated:
H # | Duration to Complete (yn)
1 | 260
2 | 245
3 | 255
4 | 246
5 | 254
6 | 243
7 | 253
8 | 242
9 | 254
10 | 248
11 | 
Forecasted Duration (Fn) |  |  |  |  |  |  | 
 = 1 |  = 0.8 |  = 0.6 |  = 0.5 |  = 0.4 |  = 0.2 |  = 0.1 |  = 0.0
260.0 | 260.0 | 260.0 | 260.0 | 260.0 | 260.0 | 260.0 | 260.0
260.0 | 260.0 | 260.0 | 260.0 | 260.0 | 260.0 | 260.0 | 260.0
245.0 | 248.0 | 251.0 | 252.5 | 254.0 | 257.0 | 258.5 | 260.0
255.0 | 253.6 | 253.4 | 253.8 | 254.4 | 256.6 | 258.2 | 260.0
246.0 | 247.5 | 249.0 | 249.9 | 251.0 | 254.5 | 256.9 | 260.0
254.0 | 252.7 | 252.0 | 251.9 | 252.2 | 254.4 | 256.6 | 260.0
243.0 | 244.9 | 246.6 | 247.5 | 248.5 | 252.1 | 255.3 | 260.0
253.0 | 251.4 | 250.4 | 250.2 | 250.3 | 252.3 | 255.0 | 260.0
242.0 | 243.9 | 245.4 | 246.1 | 247.0 | 250.2 | 253.7 | 260.0
254.0 | 252.0 | 250.5 | 250.1 | 249.8 | 251.0 | 253.8 | 260.0
248.0 | 248.8 | 249.0 | 249.0 | 249.1 | 250.4 | 253.2 | 260.0

Notes: Agile, Waterfall

## Slide 30: EMA – Example 1
Chart: 
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11
Yn | 260 | 245 | 255 | 246 | 254 | 243 | 253 | 242 | 254 | 248
Fn @ α=1.0 | 260 | 260 | 245 | 255 | 246 | 254 | 243 | 253 | 242 | 254 | 248
Fn @ α=0.8 | 260 | 260 | 248 | 253.6 | 247.52 | 252.704 | 244.9408 | 251.3882 | 243.8776 | 251.9755 | 248.7951
Fn @ α=0.6 | 260 | 260 | 251 | 253.4 | 248.96 | 251.984 | 246.5936 | 250.4374 | 245.375 | 250.55 | 249.02
Fn @ α=0.5 | 260 | 260 | 252.5 | 253.75 | 249.875 | 251.9375 | 247.4688 | 250.2344 | 246.1172 | 250.0586 | 249.0293
Fn @ α=0.4 | 260 | 260 | 254 | 254.4 | 251.04 | 252.224 | 248.5344 | 250.3206 | 246.9924 | 249.7954 | 249.0773
Fn @ α=0.2 | 260 | 260 | 257 | 256.6 | 254.48 | 254.384 | 252.1072 | 252.2858 | 250.2286 | 250.9829 | 250.3863
Fn @ α=0.1 | 260 | 260 | 258.5 | 258.15 | 256.935 | 256.6415 | 255.2774 | 255.0496 | 253.7447 | 253.7702 | 253.1932
Fn @ α=0.0 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260
Large  (say 0.9, 0.8, 0.7, 0.6 etc) would mean: LESS smoothing of the data
Small  (say 0.1, 0.2, 0.3, 0.4 etc) would mean: MORE smoothing of the data
Notes: Agile, Waterfall

## Slide 31: EMA – Example 2
Consider the data for the original example
yn & Fn for various values of  are tabulated:
Time Period | Actual Value (yn)
T1 | 71
T2 | 70
T3 | 69
T4 | 68
T5 | 64
T6 | 65
T7 | 72
T8 | 78
T9 | 75
T10 | 75
T11 | 75
T12 | 70
T13 | 
Forecasted Duration (Fn) |  |  |  |  |  |  | 
 = 1 |  = 0.8 |  = 0.6 |  = 0.5 |  = 0.4 |  = 0.2 |  = 0.1 |  = 0.0
71 | 71 | 71 | 71 | 71 | 71 | 71 | 71
71.0 | 71.0 | 71.0 | 71.0 | 71.0 | 71.0 | 71.0 | 71.0
70.0 | 70.2 | 70.4 | 70.5 | 70.6 | 70.8 | 70.9 | 71.0
69.0 | 69.2 | 69.6 | 69.8 | 70.0 | 70.4 | 70.7 | 71.0
68.0 | 68.2 | 68.6 | 68.9 | 69.2 | 70.0 | 70.4 | 71.0
64.0 | 64.8 | 65.8 | 66.4 | 67.1 | 68.8 | 69.8 | 71.0
65.0 | 65.0 | 65.3 | 65.7 | 66.3 | 68.0 | 69.3 | 71.0
72.0 | 70.6 | 69.3 | 68.9 | 68.6 | 68.8 | 69.6 | 71.0
78.0 | 76.5 | 74.5 | 73.4 | 72.3 | 70.6 | 70.4 | 71.0
75.0 | 75.3 | 74.8 | 74.2 | 73.4 | 71.5 | 70.9 | 71.0
75.0 | 75.1 | 74.9 | 74.6 | 74.0 | 72.2 | 71.3 | 71.0
75.0 | 75.0 | 75.0 | 74.8 | 74.4 | 72.8 | 71.7 | 71.0
70.0 | 71.0 | 72.0 | 72.4 | 72.7 | 72.2 | 71.5 | 71.0

Notes: Agile, Waterfall

## Slide 32: EMA – Example 2
Chart: 
| T1 | T2 | T3 | T4 | T5 | T6 | T7 | T8 | T9 | T10 | T11 | T12 | T13
Yn | 71 | 70 | 69 | 68 | 64 | 65 | 72 | 78 | 75 | 75 | 75 | 70
Fn @ α=1.0 | 71 | 71 | 70 | 69 | 68 | 64 | 65 | 72 | 78 | 75 | 75 | 75 | 70
Fn @ α=0.8 | 71 | 71 | 70.2 | 69.24 | 68.248 | 64.8496 | 64.9699 | 70.594 | 76.5188 | 75.3038 | 75.0608 | 75.0122 | 71.0024
Fn @ α=0.6 | 71 | 71 | 70.4 | 69.56 | 68.624 | 65.8496 | 65.3398 | 69.3359 | 74.5344 | 74.8137 | 74.9255 | 74.9702 | 71.9881
Fn @ α=0.5 | 71 | 71 | 70.5 | 69.75 | 68.875 | 66.4375 | 65.7188 | 68.8594 | 73.4297 | 74.2148 | 74.6074 | 74.8037 | 72.4019
Fn @ α=0.4 | 71 | 71 | 70.6 | 69.96 | 69.176 | 67.1056 | 66.2634 | 68.558 | 72.3348 | 73.4009 | 74.0405 | 74.4243 | 72.6546
Fn @ α=0.2 | 71 | 71 | 70.8 | 70.44 | 69.952 | 68.7616 | 68.0093 | 68.8074 | 70.6459 | 71.5168 | 72.2134 | 72.7707 | 72.2166
Fn @ α=0.1 | 71 | 71 | 70.9 | 70.71 | 70.439 | 69.7951 | 69.3156 | 69.584 | 70.4256 | 70.8831 | 71.2948 | 71.6653 | 71.4988
Fn @ α=0.0 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71
Notes: Agile, Waterfall

## Slide 33: Regression
Regression is a statistical method used to describe the nature of the relationship between variables, that is, positive or negative, linear or nonlinear
Regression addresses these questions statistically:
1. Are two or more variables linearly related?
2. If so, what is the strength of the relationship?
3. What type of relationship exists?
4. What kind of predictions can be made from the relationship?
Notes: Agile, Waterfall

## Slide 34: Equation of a Straight Line
y = a + bx
where
x = value of independent variable, on the x-axis
y = value of dependent variable, on the y-axis
a = intercept on the y-axis; fixed cost, quantity etc
b = slope of the line; ratio of differential in y-values to corresponding differential in x-values
Chart: 
| -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5
Series 1 | -1 | 1 | 3 | 5 | 7 | 9 | 11 | 13
Intercept on Y-axis (= 3 = a)
y-differential (=8)
x-differential (=4)
Slope =
= =
y-diff 8
x-diff 4
2 = b
When taking ratio (slope), sequencing of differential should be same i.e. y2-y1 & x2-x1, or y1-y2 & x1-x2. A negative relationship must yield negative b
Notes: Agile, Waterfall

## Slide 35: Regression - Example
The amount of cement consumed on a multi-housing project is a function of the covered area of the house
Independent Variable (x)  Covered Area (thousand square meters)
Dependent Variable (y)  Cement consumed (tonnes)
Data as follows:
Work out the Regression Line and the Correlation Coefficient (R)
x
10
12
6
15
8
5
y
30
32
25
46
29
19
Chart: Covered Area (sq meter x 1,000 )
| 10 | 12 | 6 | 15 | 8 | 5
Cement Bags (x10) | 30 | 32 | 25 | 46 | 29 | 19
Notes: Agile, Waterfall

## Slide 36: Finding the Regression Line Equation & the “R”
Tabulate the independent (x) and the dependent (y) variables, find their products and squares, and add them up:
Enter these sums into the following formulae to find the values of R, a and b:
x | y | xy | x2 | y2
. | . | . | . | .
. | . | . | . | .
. | . | . | . | .
x = | y = | xy = | x2 = | y2 =
x | y | xy | x2 | y2
. | . | . | . | .
. | . | . | . | .
. | . | . | . | .
Notes: Agile, Waterfall

## Slide 37: Regression – Example (Manual Calculations)
x
10
12
6
15
8
5
y
30
32
25
46
29
19
xy
300
384
150
690
232
95
x2
100
144
36
225
64
25
y2
900
1,024
625
2,116
841
361

56
181
1,851
594
5,867
y = 2.27x + 9.014
= 2.27 tonne per 1,000 sq meter
= 9.01 tonne
=0.95
Notes: Agile, Waterfall

## Slide 38: Regression Equation & ‘R’ using Trendline
Chart: Covered Area (sq meter x 10 )
| 10 | 12 | 6 | 15 | 8 | 5
Cement Bags (x10) | 30 | 32 | 25 | 46 | 29 | 19
R = 0.948999
Notes: Agile, Waterfall

## Slide 39: Regression – Getting the Units Right
In the early stages of design, it is believed that the cost of a Martian rover spacecraft is related to its weight. Cost and weight data for six spacecraft is as follows:
Linear Regression yields a strong relationship, as evident from the following:
y = 48.283 + 0.660, R = 0.985008
where: x = Rover weight in lbs
b = 0.660 million $ cost per lb weight of rover
a = 48.283 million $ fixed cost
y = rover cost in million $
Weight (lb) | Cost (million $)
400 | 278
530 | 414
750 | 557
900 | 689
1.130 | 740
1,200 | 851
Notes: Agile, Waterfall

## Slide 40: Regression
Notes: Agile, Waterfall

## Slide 41: How to Work out “R” & Regression Equation
Manually
Scientific Calculator
Trend line on Chart
Excel Sheet, manually with formula
Excel Sheet, using SLOPE and INTERCEPT commands
Excel Sheet, using Data Analysis Feature
Softwares, eg Minitab
Notes: Agile, Waterfall

## Slide 42
Notes: Agile, Waterfall