## Slide 1: Control Procurements
MEC-14
Outline
Domain of Controlling Procurements
Processes in the Procurements KA
Control Procurement Process and its ITTO
Readings
PMBoK, pages 379-386.
Rita, pages 89 & 500-507.
Lecture Notes.

## Slide 2: What is Controlling Procurements?
Control Procurements is the process of managing procurement relationships, monitoring contract performance, and making changes and corrections to contracts as appropriate.
It ensures that both the seller’s and buyer’s performance meets procurement requirements according to the terms of the legal agreement
Notes: Agile, Waterfall

## Slide 3: Procurement, Step-Wise: Planning & Executing
Planning
Make or Outsource analyses
If Outsource, Buy or Lease analysis
Creating a Procurement Mgt Plan
Creating Procurement SOW
Selecting a Contract Type
Creating the Procurement Documents
Determining the Source Selection Criteria
Executing
Find the Sellers through Advertising, Tendering, from the Pre-Qualified List
Getting the Procurement SOW and Procurement Docs to the Potential Sellers
Answering the Potential Sellers’ Queries
Holding Pre-Bid Conferences
Collecting Sellers’ Responses (Bids)
Scrutinising the Sellers’ Responses
Selecting the Seller
Negotiations with the Selected Seller(s)
Signing the Contract
Notes: Agile, Waterfall

## Slide 4: Procurement, Step-Wise: Controlling & Closing
Controlling
Managing Relationship between the Buyer and the Seller
Ensuring both Parties perform iaw the Contract
Managing Changes
Handling Claims, Disputes
Authorising/making Payments to the Seller
Holding Procurement Review Meetings
Reporting on Performance (Own and Seller’s)
Monitoring Cost, Schedule and Scope (Tech Performance) against the Contract
Controlling Quality
Controlling Communication with the Sellers
Understanding the Legal Implications of all actions
Managing Interfaces between all Sellers
Performing Audits and Inspections
Identifying, monitoring & controlling Risks
Accepting Validated Deliverables
Closing
Tying up all loose ends
Verifying that all the Validated Work and Deliverables accepted
Finalising Open Claims
Paying withheld Retainage
Issuing of Contract Closing notification
Notes: Agile, Waterfall

## Slide 5: Processes in the Procurement Knowledge Area
Plan Procurement Management
- Procurement Management Plan
- Procurement Statement of Work
- Procurement Documents
- Source Selection Criteria
- Make-or-buy decisions
- Change Requests
Conduct Procurement
- Selected Sellers
- Agreements
- Resource Calendars
- Change Requests
Process
Key Outputs
Control Procurement
- WPI
- Change Request
Close Procurement
- Closed Procurements
Notes: Agile, Waterfall

## Slide 6: Control Procurements Inputs & Outputs
Control Procure-ments
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output
+
Change Request
Procurement Mgt Plan
Procurement Documents (Plan Proc Mgt)
Agreements (Conduct Proc)
*: from the Direct & Manage Project Work process
**: to the Monitor & Control process
WPR (Mon & Cont Proj Work)
Approved Change Requests (ICC)
Notes: Agile, Waterfall

## Slide 7: WPD → WPI → WPR Flow Path Complete Model
Direct & Manage Proj Work
Control Scope
Control Schedule
Control Costs
Control Quality
Control Comm
Control Risks
Control Procurements
Control S/Holder Engagement
Validate Scope
WPD
WPIs
Monitor & Control Proj Work
Perform Integrated Change Control
Develop PMP
Manage Proj Team
Manage Comm
WPRs
Approved Change Requests
Project Documents Updates
Project Plan Updates
Notes: Agile, Waterfall

## Slide 8: Control Procurement Inputs … 1/2
Input | Details
Project Procurement Management Plan | How the procurement processes will be managed, monitored and controlled from developing procurement documentation through contract closure
Procurement Documents (from Plan Proc Mgt) | Procurement documents contain complete supporting records for administration of the procurement processes; this includes procurement contract awards, and the statement of work
Agreements (from Conduct Proc) | Agreements are understandings between parties, including understanding of the duties of each party. Includes contracts, subcontracts, or purchase orders
Approved Change Requests (from ICC) | Approved change requests can include modifications to the Terms and Conditions of the Contract, including the Procurement Statement of Work, Pricing, and Descriptions of the products, services, or results to be provided. All procurement-related changes are formally documented in writing and approved before being implemented through the Control Procurements process
Notes: Agile, Waterfall

## Slide 9: Control Procurement Inputs … 2/2
Input | Details
WPR | Seller performance-related documentation includes: Technical documentation. Seller-developed technical documentation and other deliverable information are provided in accordance with the terms of the contract. Work performance information. The seller’s performance reports indicate which deliverables have been completed and which have not.
WPD | Work performance data includes (1) the extent to which quality standards are being satisfied, (2) the costs that have been incurred or committed, and (3) identification of the seller invoices that have been paid. All data are collected as part of project execution
Notes: Agile, Waterfall

## Slide 10: Control Procurement Outputs … 1/3
Input | Details
WPI | WPI provides a basis for identification of current or potential problems to support later claims or new procurements. By reporting on the Performance of a vendor, the organization increases knowledge of the performance of the procurement, which supports improved forecasting, risk management, and decision making. Performance Reports also assist in the event there is a dispute with the vendor. WPI includes reporting Compliance of Contracts, which provides procuring organizations a mechanism to track specific deliverables expected and received from vendors. Contract Compliance Reports support improved communications with vendors so that potential issues are addressed promptly to the satisfaction of all parties
Change Requests | Control Proc process may result in Change Requests to the Project Management Plan, its subsidiary plans, and other components, such as the Cost Baseline, Schedule Baseline, and Procurement Management Plan
Notes: Agile, Waterfall

## Slide 11: Control Procurement Outputs … 2/3
Input | Details
Proj Mgt Plan Update | Includes updates to: Procurement Management Plan. This plan is updated to reflect any Approved Change Requests that affect procurement management, including impacts to costs or schedules. Schedule Baseline. If there are slippages that impact overall project performance, the Schedule Baseline may need to be updated to reflect the current expectations. Cost Baseline. If there are changes that impact overall project costs, the Cost Baseline may need to be updated to reflect the current expectations.
Project Documents Updates | Involves updation to Procurement documentation which may include: Procurement Contract with all supporting Schedules, Requested Unapproved Contract Changes, and Approved Change Requests. Seller-developed Technical Documentation and other WPI, such as Deliverables, Seller Performance Reports and Warranties, Financial Documents including Invoices and Payment Records, and the results of contract-related Inspections
Notes: Agile, Waterfall

## Slide 12: Control Procurement Outputs … 3/3
Input | Details
OPA Updates | OPA updated with : Correspondence including warnings of unsatisfactory performance, requests for contract changes or clarification, results of buyer audits/ inspections, seller’s weaknesses, a complete and accurate written record of all written and oral contract communications, as well as actions taken and decisions made. Payment Schedules and Requests. All payments made in accordance with the procurement contract terms and conditions. Seller Performance Evaluation Documentation. Prepared by the buyer, Performance Evaluations document the Seller’s ability to continue to perform work on the current contract, indicate if the seller can be allowed to perform work on future projects, or rate how well the Seller is performing the project work. These documents may form the basis for early termination of the seller’s contract or determine how contract penalties, fees, or incentives are administered. The results of these performance evaluations can also be included in the appropriate qualified seller lists.
Notes: Agile, Waterfall

## Slide 13: Control Procurement Tools & Techniques … 1/4
Input | Details
Contract Change Control System | A Contract Change Control system defines the process by which the procurement can be modified. It includes the paperwork, tracking systems, dispute resolution procedures, and approval levels necessary for authorising changes. The contract change control system is integrated with the integrated change control system.
Procurement Performance Reviews | A Procurement Performance Review is a structured review of the Seller’s progress to deliver project Scope and Quality, within Cost and on Schedule, as compared to the contract. It can include a review of seller-prepared documentation and buyer inspections, as well as quality audits conducted during seller’s execution of the work. The objective of a Performance Review is to identify performance successes or failures, progress with respect to the procurement statement of work, and contract noncompliance, which allow the buyer to quantify the seller’s demonstrated ability or inability to perform work. Such reviews may take place as a part of project status reviews, which would include key suppliers.
Notes: Agile, Waterfall

## Slide 14: Control Procurement Tools & Techniques … 2/4
Input | Details
Inspections & Audits | Inspections and Audits required by the buyer and supported by the seller, as specified in the procurement contract, can be conducted during execution of the project to verify compliance in the seller’s work processes or deliverables. If authorized by contract, some inspection and audit teams can include buyer procurement personnel.
Performance Reporting | WPD and WPRs supplied by sellers are evaluated against the agreement requirements. WPI from this evaluation is then reported as appropriate. Performance reporting provides management with information about how effectively the seller is achieving the contractual objectives.
Payment Systems | Payments to the seller are typically processed by the accounts payable system of the buyer after certification of satisfactory work by an authorized person on the project team. All payments should be made and documented in strict accordance with the terms of the contract.
Notes: Agile, Waterfall

## Slide 15: Control Procurement Tools & Techniques … 3/4
Input | Details
Claims Administration | Contested changes and potential constructive changes are those requested changes where the buyer and seller cannot reach an agreement on compensation for the change or cannot agree that a change has occurred. These contested changes are variously called claims, disputes, or appeals. Claims are documented, processed, monitored, and managed throughout the contract life cycle, usually in accordance with the terms of the contract. If the parties themselves do not resolve a claim, it may have to be handled in accordance with alternative dispute resolution (ADR) typically following procedures established in the contract. Settlement of all claims and disputes through negotiation is the preferred method.
Notes: Agile, Waterfall

## Slide 16: Control Procurement Tools & Techniques … 4/4
Input | Details
Records Management System | Used by the Project Manager to manage contract and procurement documentation and records. Consists of a specific set of processes, related control functions, and automation tools that are consolidated and combined as part of the Project Management Information System. Contains a retrievable archive of contract documents and correspondence.
Notes: Agile, Waterfall

## Slide 17: Some Control Procurement Activities … 1/3
Review Invoices (Were they submitted in the right form? Do they have all required supporting information? Are the charges allowable under the contract?)
Complete integrate change control
Document (Record everything – every phone call with the seller, every email, every requested change, every approved change etc)
Manage changes
Authorise payments to the Seller
Interpret that is and what is not in the contract
Interpret what the contract means
Resolve disputes
Make sure only authorised people are communicating with the Seller
Work out with the Procurement Manager regarding requested and approved changes and contract compliance
Notes: Agile, Waterfall

## Slide 18: Some Control Procurement Activities … 2/3
Hold Procurement Performance Review meetings with your team and the Seller
Report on Performance (Own as well as the Seller’s performance)
Monitor cost, schedule, and technical performance against the contract, including all of its components (terms and conditions, procurement SOW etc)
Understand the legal implications of action taken
Control Quality according to what is required in the contract
Issue Claims and review Claims filed by the Seller
Authorise the Seller’s work to start at the appropriate time, coordinating the Seller’s work with Project’s work as a whole
Correspond with the Seller and with others
Manage interfaces among all the Sellers on the Project
Send copes of Changes to the appropriate parties
Notes: Agile, Waterfall

## Slide 19: Some Control Procurement Activities … 3/3
Accept Verified Deliverables
Validate that the procurement is taking place according to the Scope
Validate that Changes are giving you the intended results
Perform Inspection and Audits
Identify risks for future work
Reestimate Risks, Costs and Schedule
Monitor and Control Risks
Be sensitive to the Constructive Changes
Notes: Agile, Waterfall

## Slide 20: Fixed Price (FP) Contract
Watch for the Seller cutting Scope
Watch for the Seller cutting Quality
When the Contract requires Seller’s costs to be transparent, make sure they are real costs that have been incurred, not just future costs (unless there is an agreement stating otherwise)
Watch for the over-priced Change Orders
Check for Scope Misunderstandings
Notes: Agile, Waterfall

## Slide 21: Time and Material (T&M) Contract
Provide day-to-day direction to the Seller
Attempt to get concrete Deliverables
Make sure the Project length is not extended
Make sure the number of hours spent on the work are reasonable
Watch for the situations when switching to a different form of contract makes sense (e.g. you determine a design SOW under a T&M contract and then switch to a FP contract for completion of the work)
Notes: Agile, Waterfall

## Slide 22: Cost Reimbursable (CR) Contract
Audit every invoice
Make sure all the costs are applicable and chargeable to your project
Make sure the Seller’s work is progressing efficiently
Watch for the Seller adding Resources to your Project that do not add value or perform real work
Watch for Resources being shifted from what was said in the Proposal (e.g. more experienced people are proposed and less experienced people are used, but you are charged at the higher rate)
Watch for the Seller charges that were nor part of the original plan
Reestimate the cost of the Project
Notes: Agile, Waterfall