## Slide 1: Monitoring & Control in Integration Management
MEC-16
Outline
Revisiting Data Flow on a Project in the context of Integration Management
Looking at the Integration Processes as a whole
What does the Monitor and Control Project Work process entail
How a Change is processed
What does the Perform Integrated Change Control Process entail
Readings
PMBoK-5, pages 86-100.
Rita-8, pages 132-141.
Lecture Notes.

## Slide 2: WPD → WPI → WPR Flow Path Complete Model
Direct & Manage Proj Work
Control Scope
Control Schedule
Control Costs
Control Quality
Control Comm
Control Risks
Control Procurements
Control S/Holder Engagement
Validate Scope
WPD
WPIs
Monitor & Control Proj Work
Perform Integrated Change Control
Develop PMP
Manage Proj Team
Manage Comm
WPRs
Approved Change Requests
Project Documents Updates
Project Plan Updates
PDs
Notes: Agile, Waterfall

## Slide 3: Processes in the Integration Knowledge Area
Develop Project Charter
- Project Charter
Develop Project Management Plan
- Project Management Plan
Process
Key Outputs
Direct & Manage Project Work
- Deliverables
- WPD
- Change Requests
Monitor & Control Project Work
- WPR
- Change Requests
Close Project or Phase
- Final Product, Service or Result Transition
Perform Integrated Change Control
- Approved Change Requests
- Change Log
Notes: Agile, Waterfall

## Slide 4: Monitor & Control Project Work Inputs & Outputs
Monitor & Control Project Work
PMP
PDs (w/a)
WPI*
OPA
Any Specific Input
PMP Updates
PD Updates
WPR**
OPA Updates
Any Specific Output
+
Change Request
All Management Plans
All Baselines
Schedule Forecast (Control Schedule)
Cost Forecast (Control Cost)
*: from the respective Control process
**: to the Perform Integrated Change Control and 5 other Processes
Validated Changes (Control Quality)
X
Notes: Agile, Waterfall

## Slide 5: Monitor & Control Project Work Inputs – 1/5
Input | Details
Project Management Plan | Communications management plan Cost baseline Cost management plan Human resource management plan Process improvement plan Procurement management plan Scope baseline Quality management plan Requirements management plan Change management plan Configuration management plan Risk management plan Schedule baseline Schedule management plan Scope management plan Stakeholder management plan
Notes: Agile, Waterfall

## Slide 6: Monitor & Control Project Work Inputs – 2/5
Input | Details
Schedule Forecast (from Control Schedule) | Derived from progress against the schedule baseline and expressed in terms of schedule variance (SV) and schedule performance index (SPI) Forecasted Project Completion Date derived from Planned Project Duration and SPI The forecast may be used to determine if the project is still within defined tolerance ranges and identify any necessary change requests.
Cost Forecast (from Control Cost) | Derived from progress against the cost baseline and computed estimates to complete (ETC), expressed in terms of cost variance (CV) and cost performance index (CPI) Estimate at completion (EAC) can be compared to the Budget at completion (BAC) to see if the project is still within tolerance ranges or if a change request is required Forecast also ascertained through ETC and TCPI
Notes: Agile, Waterfall

## Slide 7: Monitor & Control Project Work Inputs – 3/5
Input | Details
Validated Changes | Approved changes that result from the Perform Integrated Change Control process require Validation (through Quality Control) to ensure that the change was appropriately implemented A validated change provides the necessary data to confirm that the change was appropriately executed
WPI | WPI is the WPD collected from various controlling processes, analyzed in context, and integrated based on relationships across areas. Thus WPD data is transformed into WPI WPD in itself cannot be used in the decision-making process as it has only out-of-context meaning. Work performance information, however, is correlated and contextualized, and provides a sound foundation for project decisions WPI is circulated through communication processes Examples: Status of deliverables, implementation status for change requests, and forecasted estimates to complete
Notes: Agile, Waterfall

## Slide 8: Monitor & Control Project Work Inputs – 4/5
Input | Details
EEF | Governmental or industry standards (e.g., regulatory agency regulations, codes of conduct, product standards, quality standards, and workmanship standards) Organization work authorization systems Stakeholder risk tolerances Project Management Information System (e.g., an automated tool suite, such as a scheduling software tool, a configuration management system, an information collection and distribution system, or web interfaces to other online automated systems).
Notes: Agile, Waterfall

## Slide 9: Monitor & Control Project Work Inputs – 5/5
Input | Details
OPA | Organisational communication requirements Financial controls procedures (e.g., time reporting, required expenditure and disbursement reviews, accounting codes, and standard contract provisions) Issue and defect management procedures defining issue and defect controls, issue and defect identification, and resolution and action item tracking Change control procedures, including those for scope, schedule, cost, and quality variances Risk control procedures including risk categories, probability definition and impact, and probability and impact matrix Process measurement database used to make available measurement data on processes and products Lessons learned database
Notes: Agile, Waterfall

## Slide 10: Monitor & Control Project Work Outputs … 1/3
Output | Details
Change Requests | Variances from comparing planned results to actual results Change Requests expand, adjust, or reduce Project Scope, Product Scope, or Quality Requirements and Schedule or Cost Baselines Change Requests may necessitate the collection and documentation of new requirements Change Requests can impact the project management plan, project documents, or product deliverables Changes that meet the project’s change control criteria should go through the integrated change control process established for the project Changes may include: Corrective action—An intentional activity that realigns the performance of the project work with the Proj Management Plan Preventive action—An intentional activity that ensures the future performance of the project work is aligned with the Project Management Plan Defect Repair—an intentional activity to modify a nonconforming product or product component
Notes: Agile, Waterfall

## Slide 11: Monitor & Control Project Work Outputs … 2/3
WPR | WPR are the physical or electronic representation of WPI compiled in project documents, intended to generate decisions, actions, or awareness Project information may be communicated verbally from person to person. However, in order to record, store, and sometimes distribute WPI, a physical or electronic representation in the form of project documents is required WPR are a subset of project documents, which are intended to create awareness and generate decisions or actions Specific work performance metrics may be defined at the start of the project and included in the normal WPR provided to key stakeholders Examples: status reports, memos, justifications, information notes, recommendations, and updates
PMP/PD Updates | 
Notes: Agile, Waterfall

## Slide 12: Monitor & Control Proj Work – Tools & Techniques … 1/2
Tools & Techs | Details
Expert Judgement | To interpret the information provided by the monitor and control processes, or to resolve any situation emerging from the M&C process, expert judgement from professionals in the industry may be sought
Project Management Information System | Provides access to automated tools, such as scheduling, cost, and resourcing tools, performance indicators, databases, project records, and financials used during the Monitor and Control Project Work process.
Meetings | May include project team members, stakeholders, and others involved in or affected by the project Types: User groups, Review Meetings, Focal Groups etc
Notes: Agile, Waterfall

## Slide 13: Monitor & Control Proj Work – Tools & Techniques … 2/2
Tools & Techs | Details
Analytical Techniques | To forecast potential outcomes based on possible variations of project or environmental variables and their relationships with other variables: Regression analysis Grouping methods Causal analysis Root cause analysis Forecasting methods (e.g., time series, scenario building, simulation, etc.) Failure mode and effect analysis (FMEA) Fault tree analysis (FTA) Reserve analysis Trend analysis Earned value management (EVM) Variance analysis
Notes: Agile, Waterfall

## Slide 14: M&C PW – Tools & Techniques - Grouping
Grouping methods
Causal analysis
Root cause analysis
Failure Mode & Effect Analysis (FMEA)
Fault Tree Analysis (FTA)
Regression Analysis
Forecasting methods
Trend analysis
Earned Value Management
Variance Analysis
Reserve analysis
Root Cause Analysis
Trend Analysis, Smoothing, Forecasting
Risk Analysis
Notes: Agile, Waterfall

## Slide 15: Integrated Change Control

## Slide 16: Processing of a Change
Assess Impact within KA
Change Request
Implemented Change
Create a Change Request
Identify Source of Change
PM
Sponsor
Project Team
Stakeholder
Assess the Change 
Look for Options 
Change Approved or Rejected 
Update the Change Log 
Adjust the PMP, PDs, & Baselines 
Perform Integrated Change Control
Change Log
Approval/ Rejection Info
Direct & Manage Project Work
Approved Change
PMP
PDs
Baselines
Updation
Control Quality
Change Not Validated
Change Validated
Monitor & Control Project Work
Validation Info
Notes: Agile, Waterfall

## Slide 17: Perform Integrated Change Control Inputs & Outputs
Perform Integrated Change Control
PMP
PDs (w/a)
WPR*
OPA
Any Specific Input
PMP Updates
PD Updates
WPR
OPA Updates
Any Specific Output
+
Approved Change Requests
Scope Management Plan
Scope Baseline
Change Management Plan
*: from the Monitor & Control Project Work process
Change Requests
X
X
Notes: Agile, Waterfall

## Slide 18: Perform Integrated Change Control - Inputs – 1/2
Input | Details
Project Management Plan | Scope management plan, which contains the procedures for scope changes; Scope baseline, which provides product definition; and Change management plan, which provides the direction for managing the change control process and documents the formal change control board (CCB)
WPR | Work performance reports of particular interest to the Perform Integrated Change Control process include resource availability, schedule and cost data, and earned value management (EVM) reports, burnup or burndown charts
Change Requests | All of the Monitoring and Controlling processes , many of the Executing processes and one Planning process produce change requests as an output Change requests may include corrective action, preventive action, and defect repairs. However, corrective and preventive actions do not normally affect the project baselines—only the performance against the baselines
Notes: Agile, Waterfall

## Slide 19: Perform Integrated Change Control - Inputs – 2/2
Input | Details
EEF | Project management information system (PMIS) can influence the Perform Integrated Change Control process PMIS may include: scheduling software tool, a configuration management system, an information collection and distribution system, or web interfaces to other online automated systems
OPA | Following OPA can influence the Perform Integrated Change Control process: Change control procedures, including the steps by which official organization standards, policies, plans, and other project documents will be modified, and how any changes will be approved, validated, and implemented Procedures for approving and issuing change authorizations Process measurement database used to collect and make available measurement data on processes and products Project documents (e.g., scope, cost, and schedule baselines, project calendars, project schedule network diagrams, risk registers, planned response actions, and defined risk impact)
Notes: Agile, Waterfall

## Slide 20: Perform Integrated Change Control - Outputs – 1/2
Output | Details
Approved Change Requests | Change requests are processed according to the change control system by the project manager, CCB, or by an assigned team member Approved change requests are implemented through the Direct and Manage Project Work process The disposition of all change requests, approved or not, will be updated in the change log as part of updates to the project documents
Change Log | A change log is used to document changes that occur during a project These changes and their impact to the project in terms of time, cost, and risk, are communicated to the appropriate stakeholders Rejected change requests are also captured in the change log
Notes: Agile, Waterfall

## Slide 21: Perform Integrated Change Control - Outputs – 2/2
Output | Details
Project Management Plan Updates | Elements of the project management plan that may be updated include: Any subsidiary plans, and Baselines that are subject to the formal change control process Changes to baselines should only show the changes from the current time forward. Past performance may notbe changed. This protects the integrity of the baselines and the historical data of past performance.
Project Documents Update | Project documents that may be updated as a result of the Perform Integrated Change Control process include all documents specified as being subject to the project’s formal change control process.
Notes: Agile, Waterfall

## Slide 22: Perform Integrated Change Control – Tools & Techniques
Tools & Techs | Details
Expert Judgement | In addition to the project management team’s expert judgment, stakeholders may be asked to provide their expertise and may be asked to sit on the change control board (CCB). Such judgment and expertise are applied to any technical and management details during this process and may be provided by various sources, for example: Consultants Stakeholders, including customers or sponsors Professional and technical associations Industry groups Subject matter experts (SMEs) Project management office (PMO)
Meetings | 
Change Control Tools | Manual & Automated Tools
Notes: Agile, Waterfall