## Slide 1: Controlling Project Scope
MEC-2
Outline
Product Scope & Project Scope.
Documentation related to Product Scope & Project Scope.
Changes to Scope:
  - Good Changes
  Scope Creep
  Goldplating
- Controlling Project Scope.
Validating Product Scope.
Readings
PMBoK pages 118-119, 133-140 & 562.
Rita, pages 87, 170-171, 181-185 & 296.
Lecture Notes

## Slide 2: Scope Change – Nandipur Project
Petroleum Fuel → Natural Gas
Fuel Tanks
Notes: Agile, Waterfall

## Slide 3: Scope Change – Nandipur Project
Hotel deleted
Notes: Agile, Waterfall

## Slide 4: Basic Concepts
Project Scope
(Product Scope
+
How to achieve the Product: Planning, Execution, Management, Logistics etc)
Product Scope
(What & What Not of Product)
Project Scope Statement
Product Scope
Project Scope
Deliverables (for the Product & Project)
Acceptance Criteria
What is NOT part of the Project
Assumptions
Constraints
Product Requirements
Product Scope
Project Scope
Scope Baseline
Project Scope Statement
WBS
WBS Dictionary
Requirements Documentation
Notes: Agile, Waterfall

## Slide 5: Where to find Product & Project Scopes
Project Charter (High Level, as part of SOW)
Requirements Documentation
Requirements Traceability Matrix
Project Scope Statement
Scope Baseline
WBS Dictionary (most detailed)
Bill of Quantities & Specifications (BOQS)(Public Sector projects)
Notes: Agile, Waterfall

## Slide 6: Product & Project Scope in the Project Charter … 1/3
Project: Customer Satisfaction Fix-It Project (Improve the On-Line Ordering System Efficiency)
Stakeholder Requirements As Known (Requirements related to both Project and Product Scope)
Attached to this document are the detailed specifications for the existing system, the requirements that the existing system was designed to meet. It is expected that this project will not change how the system affects the existing requirements.
The project must include utilizing the data available from Quality Control
Notes: Agile, Waterfall

## Slide 7: Product & Project Scope in the Project Charter … 2/3
Project: The First Personal Assistant
Design a prototype and create the manufacturing plan for the first consumer product that can act as a personal assistant. This product would be worn on the ear, respond to voice commands, and do every thing that a human persona assistant can do.
Stakeholder Requirements As Known (Requirements related to both Project and Product Scope)
Attached to this document are the detailed specifications for the personal assistant as gathered by marketing research and as determined by potential customers of this product. The product should be able to perform Internet searches; make hotel, flight, and restaurant reservations; take dictation and fax or e-mail the results; and be able to make phone calls itself using its own voice. It must be small enough to be worn on the ear and respond to voice-only commands. The scope of this project does not call for typed entry into the system. It will be entirely voice activated and managed. The technical requirements consisting of acceptable weight ranges, acceptable materials, and other needs are attached. Creating marketing, advertising, and promotional plans are not part of this project; however, this work is authorized under a separate project, requiring the project team to provide the needed information. A list of that information and the schedule for its availability is also attached, but it is expected to change as the project progresses.
Notes: Agile, Waterfall

## Slide 8: Product & Project Scope in the Project Charter
Project: Consultancy Service to E2E Global Test Factory on adopting Lean Operating Principles
Notes: Agile, Waterfall

## Slide 9: Requirements Documentation
Full details of the Requirements (Requirements should be measureable, testable, traceable, complete, consistent and acceptable to key stakeholders)
Include:
Business Requirements (issues, opportunities, reasons)
Stakeholder Requirements
Solution Requirements (features, functions & characteristics of the product, service or result which will meet the Business and Stakeholder requirements)
Project Requirements (actions, processes, performance, safety or other conditions the Project needs to meet)
Quality Requirements (Validation/Acceptance criteria)
Transition Requirements (training etc to go from “as-is” to “to-be” status
Well-documented Requirements make it easier to detect any deviation in the Scope agreed for the Project or Product)
Notes: Agile, Waterfall

## Slide 10: Requirements Traceability Matrix (RTM) … 1/3
Links Product Requirements from their Origins to:
- the Deliverables that satisfy them
the Project Objectives
the Requirements Validation parameters (Test Cases)
Helps track requirements throughout the Project life cycle; helps ensure that the requirements as per Project Documentation are delivered at the end of the Project
Provides a structure for managing Changes to the Product Scope
Carry/provide the following information:
Requirement Identification No & Unique Identifier
Source of each Requirement
A textual description of the requirement
the Rationale for inclusion
Source, Priority, Version
Who is assigned to manage the Requirement
Current status (such as active, cancelled, deferred, added, approved, assigned, completed), and status date
Notes: Agile, Waterfall

## Slide 11: Requirements Traceability Matrix … 2/3
(Ref: Rita 8th Ed, page 171)
Requirements/ WBS/Deliverable→ Objectives ↓ | Reading Area |  |  |  | Book Storage |  |  | Public Meeting Space |  |  | Child-ren’s Area |  | Audio |  |  | Office Space |  | Computers |  |  |  | 
 | Magazines | Newspapers | Comfy Chairs -25 | Patron Desks-2 | Books - 150,000 | Books Categories - 15 | Signage for easy locating | Rooms | Separate Entrance | Drop-down Screens | Small Chairs – 80% | Story time Locale | Room for Books & Music | Shelves for Books - 15 | Racks for Music - 12 | Offices – 4 | Cubes - 15 | For Public Use - 48 | For Visitor Svc Desk - 12 | For Staff - 20 | With audio capability - 5 | Printers
Improve access to job resources by 20% |  | x |  | x |  |  |  | x |  | x |  |  |  |  |  |  |  | x | x |  |  | x
Improve local children’s reading levels by two grade levels in one year |  |  | x |  | x |  | x |  |  |  |  | x |  |  |  |  |  | x |  |  |  | 
Provide a pleasant space for the community members to meet | x | x | x |  |  |  |  | x | x |  | x |  | x | x | x |  |  |  |  |  |  | 
Replace the Existing Library by the end of next quarter | x | x | x |  | x | x | x |  |  |  |  | x |  | x |  | x | x | x |  | x | x | x
Notes: Agile, Waterfall

## Slide 12: Requirements Traceability Matrix … 3/3
If a requirement changes, RTM helps trace the affected test cases
If a test case fails, RTM helps determine the corresponding functionality
Helps ensure that all requirements are tested
(Ref: PMBOK 5th Ed, page 110)
Requirements Traceability Matrix |  |  |  |  |  |  |  | 
Project Name: |  |  |  |  |  |  |  | 
Cost Centre: |  |  |  |  |  |  |  | 
Proj Description: |  |  |  |  |  |  |  | 
ID | Assocate ID | Requirements Description | Business Needs, Goals, Opportunities, Objectives | Project Objectives | WBS Deliver-ables | Product Design | Product Devlop-ment | Test Cases
001 | 1.0 |  |  |  |  |  |  | 
 | 1.1 |  |  |  |  |  |  | 
 | 1.2 |  |  |  |  |  |  | 
 | 1.2.1 |  |  |  |  |  |  | 
002 | 2.0 |  |  |  |  |  |  | 
 | 2.1 |  |  |  |  |  |  | 
 | 2.1.1 |  |  |  |  |  |  | 
003 | 3.0 |  |  |  |  |  |  | 
 | 3.1 |  |  |  |  |  |  | 
 | 3.2 |  |  |  |  |  |  | 
004 | 4.0 |  |  |  |  |  |  | 
005 | 5.0 |  |  |  |  |  |  | 
Notes: Agile, Waterfall

## Slide 13: Project & Product Scope in the Scope Statement
3 Scope:
3.1 Building & Civil Works
In Scope Building, Driveways, Civil works, Services, Plants, Lifts, Machinery, Installations, Fittings, Implements, Provisions-for, Furnishings, Landscaping, and other items, as per architectural & structural drawings, BOQs and the contract. Ducting and conduiting for networking, as per networking drawings. Out of Scope Networking/IT systems or their installation. Laboratory equipment, tools and machines.
3.2 Laboratory Equipment and Machinery
In Scope All equipment as per Bidding Documents. POLs for rotables used in testing & commissioning of plants & machinery, before handover. Out of Scope Networking/IT systems or their installation. POLs for rotables after handover and during the warranty period.
3.3 Networking Cables and Devices
In Scope All equipment as per Bidding Documents. Shielding against rats. Out of Scope Ducting and conduiting for cables.
3.4 Library Books
In Scope 1. All Books as per Bidding Documents. Out of Scope 1. Magnetic tagging.
3.5 Furniture
In Scope All Office, Classroom, Lounge and Library furniture as per Bidding Documents. Transportation from works to site, and from site to the respective floors. Out of Scope 1. Termite proofing
Notes: Agile, Waterfall

## Slide 14: Project & Product Scope in the WBS Dictionary
The WBS dictionary is a document that provides detailed deliverable, activity, and scheduling information about each component in the WBS. Information in the WBS dictionary may include, but is not limited to:
Code of account identifier,
Description of work,
Assumptions and constraints,
Responsible organization,
Schedule milestones,
Associated schedule activities,
Resources required,
Cost estimates,
Quality requirements,
Acceptance criteria,
Technical references, and
Agreement information
Notes: Agile, Waterfall

## Slide 15: WBS Dictionary
WBS Dictionary |  |  | 
Cont Account ID # | Wk Pkg Name/No | Date of Update | Responsibility:
Work Package Deliverable Description |  |  | 
Work Involved to Produce Deliverable |  |  | 
Acceptance Criteria (how to know if the deliverable/work is acceptable) |  |  | 
Assumptions and Constraints |  |  | 
Quality Metrics |  |  | 
Technical Source Document |  |  | 
Scope |  |  | 
Resources Assigned |  |  | 
Duration |  |  | 
Schedule Milestones |  |  | 
Cost |  |  | 
Due Date |  |  | 
Interdependencies: Before this WP…………………….. After this WP…………………….. |  |  | 
Approved by: Project Manager …………………….. Date …………………….. |  |  | 
(Ref: Rita 8th Ed, page 181)
Notes: Agile, Waterfall

## Slide 16: Effect of Scope Change on other Project Constraints
 | Time | Cost | Quality | Risks
Scope  |  |  |  or ― |  or ―
Scope  |  |  |  or ― |  or ―
 : Increase,  : Decrease, ― : No Change
Scope change affects Time & Cost Constraints LIKEWISE
Scope change affects Quality & Risk Constraints LIKEWISE or may have NO EFFECT; all depends on the nature of the change
Notes: Agile, Waterfall

## Slide 17: Changes to Scope
Good Change to Scope
A good change makes the product better with very little downside. It doesn’t cost more time in the Schedule or more money from the Budget, and it doesn’t destabilize the Product or otherwise threaten its Quality
Good changes happen pretty rarely and nearly EVERY change has some impact that should be fully explored before going ahead with the change
Bad Change to Scope
A bad change is one that might seem from the outside like a good idea but ends up making an impact on the project constraints
Examples:
Scope Creep
Gold Plating
Notes: Agile, Waterfall

## Slide 18: Changes to Scope
Scope Creep – 1/2
The uncontrolled expansion to Product Scope or Project Scope without adjustments to Time, Cost and Resources
Caused by:
poor WBS Dictionary
poor Change Control
lack of proper Initial Identification of what is required to bring about the project objectives
weak Project Manager or Executive Sponsor
poor Communication between parties
lack of Initial Product Versatility
Notes: Agile, Waterfall

## Slide 19: Changes to Scope
Scope Creep - 2/2
Good WBS Dictionary prevents Scope Creep
(WBS Dictionary provides a description of the work to be done for each WBS work package and helps make sure the resulting work matches with what is needed. Therefore, a project manager can use the WBS Dictionary to prevent Scope Creep before work even start on the project rather than dealing with Scope Creep while the work is being done through the use of management skills and constant inspection)
Notes: Agile, Waterfall

## Slide 20: Changes to Scope
Gold Plating – 1/2
Giving the customer extras (e.g. extra functionality, higher Quality components, extra Scope, or better Performance)
Manifests in the “exceeding” part of a company’s policy of "meeting and exceeding the customers' expectations”
Gold plating often results from:
project team's impression, or fear, of customer’s expectations
previous projects which did not meet customer’s requirements
a team member's efforts to do the best, or to demonstrate how well he/she is doing (this is unplanned or inadvertent gold plating)
Ordered
Delivered in same price
Notes: Agile, Waterfall

## Slide 21: Changes to Scope
The project might not call for the best, just what was asked for. Therefore, the project manager must be on the lookout for team members providing extra Functionality, extra Work, or higher Quality than is required for the project
Since most projects have difficulty meeting the Project Objectives, all available effort should go into achieving those objectives, instead of gold plating
Gold Plating – 2/2
Notes: Agile, Waterfall

## Slide 22: Gold Plating or Scope Creep? … Example 1
Project: Develop a new computer game
Project Status: Nearing completion
Nature of Project: Internal, a Computer Game Company developing a new computer game which the Company will market under its own brand name
Situation 1: The head of the Company’s New Programmes Dept asks the Project team for the following changes to the Project Scope:
“We need to create a screensaver to market the game. Let’s kill two birds with one stone and test out a brand new graphics engine on it. Oh, and we’ll need a story for the screensaver, so we should write that too. Of course we have to recruit some killer voice talent for the screensaver. Memorable names sell more games”
Question: Is it a case of Gold Plating or Scope Creep? Does the change in Scope cause changes to the Schedule & Cost Baselines?
Notes: Agile, Waterfall

## Slide 23: Gold Plating or Scope Creep? … Example 1
Project: Develop a new computer game
Project Status: Nearing completion
Nature of Project: External, a Computer Game Company developing a new computer game for an external customer who will market the product under their (customer) brand name
Situation 2: The Project manager of the Computer Game Company makes the following changes to the Project Scope:
“Let us create a screensaver which will help the customer market the game. A brand new graphics engine will be the perfect add-on. The customer will feel really happy if we can write a story for the screensaver. And if we can recruit some killer voice talent for the screensaver, we are assured of the next project from the customer.”
Question: Is it a case of Gold Plating or Scope Creep? Does the change in Scope cause changes to the Schedule & Cost Baselines?
Notes: Agile, Waterfall

## Slide 24: Gold Plating or Scope Creep? … Example 2
Project: Develop a hotel’s Online Booking System
Situation 1: The web-developer hired for the project decides that it will be ‘cool’ to display all the luxuries of the hotel just before committing a room booking transaction by the guest.
The additional work takes him two more days of implementation effort. QA team does not have a requirement to really test this feature. The web-developer tests the new feature and feels exhilarated at the results. He lays out a demonstration for the Hotel’s GM
The GM is happy with the product and pleasantly surprised at the additional feature. But he observes that the new feature adds to the guests’ booking time; besides, majority of the hotel’s guests are the second or more timer business gets who want the booking just a click away. While appreciating the work done by the web-developer, the GM asks him to remove the additional feature.
Question: Is it a case of Gold Plating or Scope Creep? Does the change in Scope cause changes to the Schedule & Cost Baselines?
Notes: Agile, Waterfall

## Slide 25: Gold Plating or Scope Creep? … Example 2
Situation 2: The web-developer has delivered the web-portal. The GM appreciates the work and praises the developer to the hilt. He then asks the developer to display the photo of the room being booked to show all the luxuries of the hotel, just before the guest commits the room booking transaction by the guest.
Two days later, the developer demonstrates the new feature. The GM is overwhelmed. He declares the developer the best available in the town. He asks him to do it for all the rooms. Thrilled by the praise, the developer digs in the work, not bothering to ask the GM for a Scope Change.
Question: Is it a case of Gold Plating or Scope Creep? Does the change in Scope cause changes to the Schedule & Cost Baselines? Will the developer get the payment for extra work? If he gets it, will it be for the Change of Scope or due to goodwill of the GM? Which is the right approach?
Notes: Agile, Waterfall

## Slide 26: Control Scope
Process of monitoring the status of the Project Scope and the Product Scope, and managing changes to the Scope Baseline
Good Scope Control allows the Scope Baseline to be maintained throughout the Project
Scope Control ensures that requirements of all stakeholders are met
Good Scope Control prevents Scope Creep and Gold Plating
Notes: Agile, Waterfall

## Slide 27: Control Scope Inputs & Outputs
Control Scope
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output
+
Change Request
Scope Mgt Plan
Scope Baseline
Change Mgt Plan
Configuration Mgt Plan
Requirements Mgt Plan
Requirements Documentation
Requirements Traceability Matrix
(from the Collect Requirements process)
*: from the Direct & Manage Project Work process
**: to the Monitor & Control process
Notes: Agile, Waterfall

## Slide 28: “Control Scope” Flow Process
D&M Proj Work
Integrated Change Control
Variance Analysis (WPI) FAVOURABLE 
Initiate Change Request
Control Scope
v
Quality Control
Approved Scope Change Request (Rework if Request Rejected)
Variance Analysis (WPI) UNFAVOURABLE 
Causes (for rejections, rework, corrections, corrective actions etc)
WPD (Measurements of Requirements, etc)
Change Request
1.All 10 hydrants of Brand X installed
2.Variance: Hydrants of Brand Z were the requirement
4.No Variance: All Hydrants of correct Brand installed
3.Hydrants of Brand X Approved or Hydrants of Brand X Not Approved; Replace them
Notes: Agile, Waterfall

## Slide 29: Control Scope Inputs – 1/2
Input | Details
Project Management Plan | Scope Management Plan How the Project Scope will be Monitored & Controlled Shows the previously agreed upon Deliverables and the Plans for gaining their formal Acceptance Scope Baseline Provides the approved Scope Requirements Management Plan How the Project Requirements will be analysed, documented and managed Change Management Plan How the Changes will be processed and managed on the Project Configuration Management Plan a plan for making sure everyone knows what version of the Scope, Schedule, and other components of the Project Management Plan are the latest version Defines how you the changes to the deliverables and the resulting documentation will be managed, including which organizational tools to use
Notes: Agile, Waterfall

## Slide 30: Control Scope Inputs – 2/2
Input | Details
Requirements Documentation | See slide # 10
Requirements Traceability Matrix | See Slide # 11
WPD (from D&M PW) | Measured specifications of the Deliverables Number of Change Requests initiated Number of Change Request accepted Number of Deliverables completed
Notes: Agile, Waterfall

## Slide 31: Control Scope Outputs … 1/2
Output | Details
WPI | How well Product Deliverables are meeting the Requirements Include Scope Variances; their causes and impact on Schedule or Cost; Forecast for future scope performance etc
Change Request | Change to Scope Baseline or other components of the Project Management Plan Include Preventive or Corrective Actions, Defect Repairs or Enhancement Requests
Project Plan Updates | Scope Baseline Update Possible changes to the Scope Statement, WBS & WBS Dictionary Other Baseline Updates Cost and Schedule Baselines if affected by the Scope Change
Notes: Agile, Waterfall

## Slide 32: Control Scope Outputs … 2/2
Project Documents Updates | Requirements Documentation Requirements Traceability Matrix
OPA Updates | Causes of Variances Corrective Action chosen and the Reasons Other types of Lessons learnt
Notes: Agile, Waterfall

## Slide 33: Control Scope – Tools & Techniques
Tools & Techs | Details
Variance Analysis | Determines the Cause & Degree of difference between the Baseline and Actual Performance Performance Measurements used to assess the magnitude of Variation form the original Scope Baseline Important aspects of Project Scope Control include determining the Cause & Degree of the Variance relative to the Scope Baseline and deciding whether Corrective or Preventive Action is required
Gradient
Requirement : 5o max with a tolerance of 0.20%
Actual : 5.08o
Variance : ?
Notes: Agile, Waterfall

## Slide 34: Validate Scope Inputs & Outputs
Validate Scope
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output +
Change Request
Scope Mgt Plan
Scope Baseline
Requirements Documentation
Requirements Traceability Matrix
(from the Collect Requirements process)
*: from the Direct & Manage Project Work process
**: to the Monitor & Control Project Work process
***: from the Control Quality process
Verified Deliverables***
Accepted Deliverables
Notes: Agile, Waterfall

## Slide 35: “Validate Scope” Flow Process
D&M Proj Work
Integrated Change Control
QC Passed/ Deliverable VERIFIED 
Close Project/ Phase
Initiate Change Request
Quality Control
v
Validate Scope (Meeting with Customer)
Approved Scope Change Request
QC Failed/ Deliverable NOT VERIFIED 
Completed Deliverable
Deliverable NOT VALIDATED/ NOT ACCEPTED by Customer
Deliverable VALIDATED/ ACCEPTED by Customer
Change Request
Notes: Agile, Waterfall

## Slide 36: Validate Scope Inputs
Input | Details
Project Management Plan | Scope Management Plan How the Project Scope will be Monitored & Controlled Shows the previously agreed upon Deliverables and the Plans for gaining their formal Acceptance Scope Baseline Provides the approved Scope
WPD (from D&M PW) | Degree of Compliance with Requirements Number of Nonconformities, Severity of the Nonconformities Number of Validation Cycles performed in a period of time
Requirements Documentation | (As for Control Scope)
Requirements Traceability Matrix | (As for Control Scope)
Verified Deliverables | Deliverables that are completed and checked for correctness through the Control Quality process
Notes: Agile, Waterfall

## Slide 37: Validate Scope Outputs … 1/2
Output | Details
WPI | Accepted Deliverables Unaccepted Deliverables: reasons, causes Progress of Project
Accepted Deliverables | Deliverables that meet the Acceptance Criteria are formally signed off and approved by the Customer (external Project) or Sponsor (internal Project) Formal documentation received from the Customer or Sponsor acknowledging formal Stakeholder Acceptance of the Project’s Deliverables is forwarded to the Close Project or Phase process
Change Requests | The completed Deliverables that have not been formally Accepted are documented, along with the Reasons for Non-acceptance of those deliverables Unaccepted Deliverables may require a Change Request for Defect Repair, Corrective Action etc Change Requests processed for review and disposition through the Perform Integrated Change Control process
Notes: Agile, Waterfall

## Slide 38: Validate Scope Outputs … 2/2
Project Documents Updates | Project documents that may be updated as a result of the Validate Scope process include any documents that define the product or report status on product completion Verified project documents may require approvals from the Customer or Sponsor in the form of signatures or signoffs
OPA Updates | Own Performance Customer’s attitude Lessons learnt
Notes: Agile, Waterfall

## Slide 39: Validate Scope – Tools & Techniques
Tools & Techs | Details
Inspections | Inspection includes activities such as Measuring, Examining, and Validating to determine whether Work and Deliverables meet Requirements and Product Acceptance Criteria Inspections are sometimes called Reviews, Product Reviews, Audits, and Walkthroughs In some application areas, these different terms have unique and specific meanings
Group Decision-Making Techniques | Delphi, Consensus, Majority, Plurality, Veto etc For internal Projects
Notes: Agile, Waterfall