## Slide 1: Variance Analysis
MEC-3
Outline
Materiality and Trends
Types of Variance in Project Management
Material Variances in Projects
Labour Variances in Projects
Readings
Drury, Chapter 17
Lecture Notes

## Slide 2: What is Variance?
It is the difference between what is estimated or planned and how it turns out to be in actual effect
There is a plot of land on which a house is to be built. Based on the expert opinion, it is estimated to cost Rs 10 million. Once complete, the house has actually cost Rs 12 million. The house has yielded an UNFAVOURABLE or NEGATIVE Variance of Rs 2 million
Notes: Agile, Waterfall

## Slide 3: What is Variance Analysis?
Variance Analysis is finding out the Variance as well as its root causes
In the previous example, the UNFAVOURABLE or NEGATIVE Variance of Rs 2 million may have been due to escalating prices of building material, particularly bricks, cement and steel, between the time of estimation and the period of execution
Notes: Agile, Waterfall

## Slide 4: ‘Materiality’ in Variance Analysis
‘Materiality’ refers to the impact of Variance. When calculating Variances, materiality needs consideration
An Unfavourable Variance of Rs 1.00 on a brick planned at Rs 9.00 isn't a big deal if the quantity required is small but would add significantly to the material cost if the quantity required is for the entire house
A Favourable Variance of Rs 2,000 on a geyser is not significant but a Rs 10 Favourable Variance on a bag of cement is
Time spent on Variance Analysis should be proportional to the effect of the Variance on the Project Baselines; no need being penny wise
Notes: Agile, Waterfall

## Slide 5: Importance of Trends in Variance Analysis
Control actions based on Point-in-time (Singular) Variances need caution; Variance Trends over time yield enable better Control actions
A negative variance over time of say Rs 9, 10, 11, 8 and 11 is indicative of a steady trend of increasing costs and, if large enough to be material, merits investigation followed by a suitable Control action
Notes: Agile, Waterfall

## Slide 6: Types of Variance (High Level)
Estimated to Planned
Planned to Actual
Estimated to Actual
Estimates
Plan
Actuals
Notes: Agile, Waterfall

## Slide 7: A. Estimated to Planned Variance
Variance between what was Estimated for the Project, based on the estimation techniques or expert opinion, and what emerged upon Planning
Occurs in situations where projects are quoted based on best guesses and ball park figures, by a group who will not actually execute the work. Detailed planning, however, results in different figures
Reasons for such a Variance: new processes, technology, laws, taxes etc introduced since the initial estimates, or a flawed estimate, or excessive delay between initiation & planning
If the variance is significantly Unfavourable, the whole Business Case or the Feasibility Study for the Project would need review, or the Project might be shelved
Notes: Agile, Waterfall

## Slide 8: B. Planned to Actual Variance
Variance between what was Planned for the Project and how it is actually working out
Yields Progress of the Project
Most widely used in Project Management as EVM and various types of Variance Analyses like Material Rate & Usage Variance, Labour Rate & Efficiency Variance etc
Reasons for such a Variance: change in material and labour costs, taxes, force majeure, scope creep, progressive elaboration etc
If the variance is significantly Unfavourable, the situation is controlled through Preventive or Corrective Actions, or Defect Repair
Notes: Agile, Waterfall

## Slide 9: C. Estimated to Actual Variance
Variance between what was Estimated for the Project and how it is actually working out
Applies to Projects which are started intuitively, without a plan or relying mostly on the Business Case or Feasibility Study
Also applies to Procurement Contracts where Bids differ significantly from the Quotations; if so, the corrective action may warrant change of vendors, processes, materials, contractual stipulations, etc.
Notes: Agile, Waterfall

## Slide 10: Types of Variance (High Level)
Estimated to Planned
Planned to Actual
Estimated to Actual
Chart: 
| Category 1 | Category 2
Series 1 | 4 | 4
Series 2 | 5 | 5
Series 3 | 3 | 3
Estimated
Planned
Actual
C
A
B
Chart: 
| Category 1 | Category 2
Series 1 | 4 | 4
Series 2 | 5 | 5
Series 3 | 3 | 3
Planned
Actual
Estimated
A
B
C
Chart: Ideally: A, B, C ≈ 0
| Category 1 | Category 2
Series 1 | 4 | 4
Series 2 | 4.15 | 4.15
Series 3 | 4.075 | 4.075
Notes: Agile, Waterfall

## Slide 11: Variance Analysis of Changes in Direct Material & Labour Costs on Project

## Slide 12: Direct Costs
Direct Costs as understood in Accounting
Direct costs refer to cost incurred on materials, labor and overhead expenses related to the production of a product. Other costs, such as depreciation or administrative expenses, are more difficult to assign to a specific product, and therefore are considered indirect costs
Direct Costs as applicable to Project Management
Direct costs refer to costs incurred on the materials used and the HR employed on the project
Notes: Agile, Waterfall

## Slide 13: Variance Analysis of Changes in Rates and Quantities … 1/3
While Budgeting, Materials & Human Resources are Costed using Standard Rates & Quantities
Should these Rates or Quantities change during the Project Life Cycle, Cost Performance would be affected Favourably or Unfavourably
Variance Analysis quantifies the effect of Variance between the Standard & Actual Rates & Quantities for Materials used and Labour employed on a Project
Three possible variance cases:
Variance involving Material Purchased and Material Used
Variance involving the Material Purchased, Material Used & Material Unused
Variance involving the Material Held in Stock, Material Purchased, Material Used & Material Unused
Notes: Agile, Waterfall

## Slide 14: Variance Analysis of Changes in Rates and Quantities … 2/3
Variance is expressed as a Monetary Quantity and suffixed FAVOURABLE or UNFAVOURABLE depending on its effect on the Project Cost Performance
Variance Analysis is an interplay of 4 Attributes:
  Standard Rate: The rate or cost at which any material for a project is planned; eg Rs 350 per cement bag
  Standard Quantity: Quantity of material required for a certain activity based on Quantity Standard; eg 1,000 bags of cement required to pour 2,000 sq ft of 5” slab based on a Quantity Standard of 0.5 bag/sq ft of 5” slab
  Actual Rate: Actual Rate at which the consumed material is purchased; eg Rs 380 per cement bag
  Actual Quantity: Actual Quantity of material used in the activity; eg 1,200 bags of cement consumed to pour 2,000 sq ft of 5” slab
Notes: Agile, Waterfall

## Slide 15: Variance Analysis of Changes in Rates and Quantities … 3/3
This course will introduce the subject through only the following four types of Variances in Direct costs:
  Material Cost Variance (MCV)
  Material Usage Variance (MUV)
  Labour Wage Rate Variance (LRV)
  Labour Efficiency Variance (LEV)
Notes: Agile, Waterfall

## Slide 16: Basic Definitions … 1/2
Material Rate Variance (MRV)
Variance due to difference in Actual & Standard Rates Actual Quantity.
Material Usage Variance (MUV)
Variance due to difference in Actual & Standard Quantities at Standard Rate
Labour Wage Rate Variance (LRV)
Variance due to difference in Actual & Standard Labour Rates on Actual Worktime or Effort
Labour Efficiency Variance (LEV)
Variance due to difference in Actual & Standard Worktimes or Efforts at Standard Labour Rate
Variance FAVOURABLE if respective
ACTUAL RATE or QTY < STD RATE or QTY, & vice versa
Notes: Agile, Waterfall

## Slide 17: Basic Definitions … 2/2
Variance | Fixed Attribute | Differing Attributes
MRV | Actual Quantity of Material | Actual & Standard Purchase Costs
MUV | Standard Cost of Material | Actual & Standard Quantities of Material
LRV | Actual Worktime | Actual & Standard Labour Rates
LEV | Standard Labour Rate | Actual & Standard Worktime
Worktime or Effort measured in Man-Hours, Man-Days, Man-Weeks, Man-Months & so on, where:
One Man-Hour = One Man working for One Hour
One May-Day = One Man working for One Day (8 Hours)
One Man-Week= One Man working for One Week (40 Hours or 5 days, @ 8 Hours per day, or as planned in the Project Calendar)
Notes: Agile, Waterfall

## Slide 18: Working out Standard Quantity (SQ) … 1/2
Due care needs to be exercised when working out SQ from the Quantity Standards as given in the Company’s OPAs, manufacturing standards or such other documents. The underlying principle is to apply the Quantity Standard to the scope of the activity/deliverable (Quantity produced, Area covered etc) to get the SQ. Following table illustrates:
SQ has nothing to do with the quantity purchased, consumed or available ex-stock
Material | Activity Deliverable | Quantity Standard (qs) | Deliverable Scope (s) | SQ = qs x s
Cement | 5” thick slab | 0.5 bag/sq ft of slab | 2,000 sq ft slab | 0.5x2,000 = 1,000 bags
Limestone | Cement | 1.5:1 (1.5 ton limestone → 1.0 ton cement) | 1,000 ton cement | (1.5:1)x1,000 = 1,500 ton limestone
Rubber | Trampoline sheets | 5 kg/sheet | 10,000 sheets | 5x10,000 = 50,000 kg rubber
Bricks | 9” thick wall | 1,000 bricks/ 100 sq ft of wall | 8,000 sq ft wall | 1,000 x8,000 = 80,000 100 bricks
Notes: Agile, Waterfall

## Slide 19: Working out Standard Quantity (SQ) … 2/2
If the given Scope is per unit, then take the number of units into consideration to get the overall Scope. For example:
Material | Activity Deliverable | Quantity Standard (qs) | Deliverable Scope (s = units x scope per unit) | SQ = qs x s
Rubber | Trampoline sheets | 5 kg per 100 sq ft | 10,000 sheets, each with an area of 200 sq ft = 2,000,000 sq ft | (5/100)x2,000,000 =100,000 kg
Notes: Agile, Waterfall

## Slide 20: Variance Analysis – Material Rate Variance (MRV)
Work Package (WP) Scope: Aluminum Windows with Single Pane Glass
20 houses, 10 windows/house, 48 sq ft/window
Standard Rate for WP Costing: Rs 500 per sq ft
MRV = Qty (Std Rate-Act Rate) = 20x10x48x(500-800) = Rs 2,880,000 (U)
20x10x48 sq ft
x
Rs 800 per sq ft
= Rs 7,680,000
20x10x48 sq ft
x
Rs 500 per sq ft
=Rs 4,800,000
Rs 2,880,000 (U)
MRV
Material Purchased
Actual Qty
x
Actual Rate
Actual Qty
x
Std Rate
After the project started, the scope was changed to have double glazed (double paned) windows for better habitability. Resultantly, the rate escalated to Rs 800/sq ft. This scope change would lead to what is known as the MRV
MRV = AQ x (SR-AR)
or
where:
AQ = Actual Quantity
SR = Standard Rate
AR = Actual Rate
Notes: Agile, Waterfall

## Slide 21: Variance Analysis – Material Usage Variance (MUV)
Work Package (WP) Scope: Aluminum Windows with Single Pane Glass
20 houses, 10 windows/house, 48 sq ft/window
Standard Rate for WP Costing: Rs 500 per sq ft
MUV = Std Rate(Std Qty-Act Qty) = 500x(20x10x48-20x9x48) = Rs 480,000 (F)
20x9x48 sq ft
x
Rs 500 per sq ft
= Rs 4,320,000
20x10x48 sq ft
x
Rs 500 per sq ft
=Rs 4,800,000
Rs 480,000 (F)
MUV
Material Used
Actual Qty
x
Std Rate
Std Qty
x
Std Rate
After the project started, the scope was changed to delete one window from each house as one room was to be converted into a store. This scope change would lead to what is known as the MUV
MUV = SR x (SQ-AQ)
or
where:
SR = Standard Rate
SQ = Standard Quantity
AQ = Actual Quantity
Notes: Agile, Waterfall

## Slide 22: Variance Analysis – Combining MRV & MUV - General Template
MRV
or
LRV
MUV
or
LEV
Net Effect
MRV/LRV FAVOURABLE (+) if: Actual Rate < Std Rate, otherwise UNFAVOURABLE (-)
MUV/LEV FAVOURABLE (+) if: Actual Qty < Std Qty, otherwise UNFAVOURABLE (-)
AQ x (SR-AR) =
= SR x (SQ-AQ)
Actual Qty
x
Actual Rate
Actual Qty
x
Std Rate
Actual Qty
x
Std Rate
Std Qty
x
Std Rate
Material Purchased
Material Used
Net Effect FAVOURABLE (+) if: between MRV(or LRV) & MUV(or LEV), both are Favourable, or the Favourable Variance is greater
Net Effect UNFAVOURABLE (-) if: between MRV(or LRV) & MUV(or LEV), both are Unfavourable, or the Unfavourable Variance is greater
The UPRIGHT rule is for MRV(or LRV) & MUV(or LEV), and not for the Net Effect
Notes: Agile, Waterfall

## Slide 23: Variance Analysis (Material) – Simplest Case – considering the Material Used and Material Purchased
Material: Cement On a certain construction project, first slab with an area of 2,000 sq ft has been poured. For this activity, the standard quantities and rates for cement were: 0.5 bag per sq ft; Rs 400 per bag. The cement was actually purchased @ Rs 500 per bag and 900 bags were consumed in the pouring. Carry out Variance Analysis (find MRV, MUV and Overall Effect on Project Cost Performance).
900 bags
x
Rs 500 per bag
= Rs 450,000
900 bags
x
Rs 400 per bag
=Rs 360,000
0.5 bag/sq ft x 2,000 sq ft
x
Rs 400 per bag
=Rs 400,000
Rs 90,000 (U)
MRV
Rs 40,000 (F)
MUV
Rs 50,000 (U)
Net Effect
Material Purchased
Actual Qty
x
Actual Rate
Actual Qty
x
Std Rate
Material Used
Actual Qty
x
Std Rate
Std Qty
x
Std Rate
900 bags
x
Rs 400 per bag
=Rs 360,000
Notes: Agile, Waterfall

## Slide 24: Variance Analysis (Material) – considering the Material Purchased, Material Used & Material Unused
Material: Cement On a certain construction project, first slab with an area of 2,000 sq ft has been poured. For this activity, the standard quantities and rates for cement were: 0.5 bag per sq ft; Rs 400 per bag. 1,200 bags were actually purchased @ Rs 500 per bag and, on completion of pouring, 250 bags remained in the store. Carry out Variance Analysis (find MRV, MUV and Overall Effect on Project Cost Performance).
1,200 bags
x
Rs 500 per bag
= Rs 600,000
1,200 bags
x
Rs 400 per bag
=Rs 480,000
0.5 bag/sq ft x 2,000 sq ft
x
Rs 400 per bag
=Rs 400,000
Rs 120,000 (U)
MRV
Rs 20,000 (F)
MUV
Rs 100,000 (U)
Net Effect
Material Purchased
Actual Qty
x
Actual Rate
Actual Qty
x
Std Rate
Material Used
Actual Qty
x
Std Rate
Std Qty
x
Std Rate
1,200-250 bags
x
Rs 400 per bag
=Rs 380,000
Notes: Agile, Waterfall

## Slide 25: Variance Analysis (Material) – considering the Material Held in Stock, Material Purchased, Material Used & Material Unused … 1/2
Material: Cement On a certain construction project, first slab with an area of 2,000 sq ft has been poured. For this activity, the standard quantities and rates for cement were: 0.5 bag per sq ft; Rs 400 per bag. 1,200 bags were actually purchased @ Rs 500 per bag, while 100 bags (purchased previously @ Rs 450) were already in stock. On completion of pouring, 250 bags remained in the store. Carry out Variance Analysis (find MRV, MUV and Overall Effect on Project Cost Performance).
100 1,200 bags
x + x
Rs 450 500 per bag
= Rs 45,000+600,000
100+1,200 bags
x
Rs 400 per bag
=Rs 520,000
0.5 bag/sq ft x 2,000 sq ft
x
Rs 400 per bag
=Rs 400,000
Rs 125,000 (U)
MRV*
Rs 20,000 (U)
MUV
Rs 145,000 (U)
Net Effect
Material Purchased
Actual Qty
x
Actual Rate
Actual Qty
x
Std Rate
Material Used
Actual Qty
x
Std Rate
Std Qty
x
Std Rate
100+1,200-250 bags
x
Rs 400 per bag
=Rs 420,000
*In this case, the formula
MRV = AQ x (SR-AR) will be difficult to
apply; template recommended; see next slide
Notes: Agile, Waterfall

## Slide 26: Variance Analysis (Material) – considering the Material Held in Stock, Material Purchased, Material Used & Material Unused … 1/2
Material: Cement On a certain construction project, first slab with an area of 2,000 sq ft has been poured. For this activity, the standard quantities and rates for cement were: 0.5 bag per sq ft; Rs 400 per bag. 1,200 bags were actually purchased @ Rs 500 per bag, while 100 bags (purchased previously @ Rs 450) were already in stock. On completion of pouring, 250 bags remained in the store. Carry out Variance Analysis (find MRV, MUV and Overall Effect on Project Cost Performance).
100 1,200 bags
x + x
Rs 450 500 per bag
= Rs 45,000+600,000
100+1,200 bags
x
Rs 400 per bag
=Rs 520,000
Rs 125,000 (U)
MRV*
Material Purchased
Actual Qty
x
Actual Rate
Actual Qty
x
Std Rate
*If required to use the formula MRV = AQ x (SR-AR), it must be done separately for the opening inventory (MRV1 in this case) and the purchase done (MRV2):
MRV1 = 100 x (400-450) = 5,000 (U)
MRV2 = 1,200 x (400-500) = 120,000 (U)
MRV = 5,000 (U) + 120,000 (U) = 125,000 (U)
Notes: Agile, Waterfall

## Slide 27: Variance Analysis (Labour)
On a certain construction project, HR Assignment Plan assigned 200 unskilled workers, on a particular activity, for 100 days, on a daily wage of Rs 500. Due to countrywide shortage and escalating inflation no worker was available for less than Rs 600 per day, and only 190 workers could be made available. The activity actually took 80 days to complete. Carry out Variance Analysis (find LRV, LEV and Overall Effect on Project Cost Performance).
Actual Qty
x
Actual Rate
Actual Qty
x
Std Rate
Actual Qty
x
Std Rate
Std Qty
x
Std Rate
Actual Effort
x
Actual Lab Rate
Actual Effort
x
Std Lab Rate
Actual Effort
x
Std Lab Rate
Std Effort
x
Std Lab Rate
190x80 man-days
x
Rs 600 per man-day
= Rs 9,120,000
190x80 man-days
x
Rs 500 per man-day
= Rs 7,600,000
200x100 man-days
x
Rs 500 per man-day
= Rs 10,000,000
Rs 1,520,000 (U)
LRV
Rs 880,000 (F)
Net Effect
LEV
Rs 2,400,000 (F)
190x80 man-days
x
Rs 500 per man-day
= Rs 7,600,000
Notes: Agile, Waterfall