## Slide 1: Schedule Control
MEC-4
Outline
Schedule Baseline and Project Schedule.
Control Schedule process.
Schedule Controlling Tools & Techniques:
- MC aspects of CPM.
- MC aspects of CCM.
- MC through Leads & Lags.
- MC through Crashing & Fast Tracking.
- MC through Resource Levelling & Resource Smoothing.
- Relationship between various Schedule MC tools.
- MC aspects of What If scenarios.
- MC aspects of Simulation
Simple Exercise in Schedule MC on MS Proj 2010.
Readings
PMBoK, pages 158-159, 176-192.
Rita, pages 87, 219 & 228-239.
Step by Step, Ch 6, 12 & 14.
Lecture Notes.

## Slide 2: Schedule Baseline
Approved Version of the Schedule Model, comprising:
  Start & Finish Dates
  Sequencing & Logical Relationship (Dependencies)
  Milestones
Presented in the form of:
  Milestone Chart
  Gantt or Bar Chart
  Network Diagram
Notes: Agile, Waterfall

## Slide 3: Project Schedule
Project Schedule is the document a Project Manager uses to track the schedule progress such as activities completed, activities in progress, actual start and finish dates, percentage complete, hours spent, resource allocations etc.
Presented in the form of:
  Milestone Chart
  Gantt or Bar Chart
Notes: Agile, Waterfall

## Slide 4: Schedule Baseline vs Project Schedule … 1/5
Develop Schedule
Approve (Baseline) the Schedule
Schedule
Add actual Schedule Performance Data (WPD)
Schedule Baseline
Project Schedule
Planning
Execution
Notes: Agile, Waterfall

## Slide 5: Schedule Baseline vs Project Schedule … 2/5
A/3
C/5
D/4
E/6
B/2
ST
END
Schedule (Pre-Baseline)
Project Schedule
Schedule Baseline (Gray bars)
Running Schedule (Red or Blue Bars)
Notes: Agile, Waterfall

## Slide 6: Schedule Baseline vs Project Schedule … 3/5
Schedule Baseline is an “approved” version, or a snapshot of the Project Schedule
Project Schedule is the “actual”, whereas Schedule Baseline is the “plan”
Schedule Baseline is a “Frozen” document while Project Schedule is a “Living” document
Project Schedule is a Project Document, whereas Schedule Baseline is a part of the Project Management Plan
Project Schedule is updated as the project is being executed, whereas Schedule Baseline is revised only as a result of an approved change
Notes: Agile, Waterfall

## Slide 7: Schedule Baseline vs Project Schedule … 4/5
Schedule performance is measured by comparing the actual (Project Schedule) vs the baseline (Schedule Baseline)
At the beginning of project execution, the Project Schedule is the same as the Schedule Baseline. As work is done on the project, the actual progress is updated on the project schedule
At any given date, the latest version of the actual (project) schedule is referred to as the “Project Schedule”
Notes: Agile, Waterfall

## Slide 8: Schedule Baseline vs Project Schedule … 5/5
Differences summed up:
Schedule Baseline | Project Schedule
Planned Schedule | Actual/Running Schedule
“Frozen” document | “Living” document
Part of the Proj Mgt Plan | A Project Document
Revised only as a result of an Approved Change | Updated as the project is being executed
Notes: Agile, Waterfall

## Slide 9: Processes in the Schedule Knowledge Area
Plan Schedule Management
- Schedule Management Plan
Define Activities
- Activities List
- Activities Attributes
- Milestones List
Process
Key Outputs
Sequence Activities
- Network Diagrams
Estimate Activities Resources
- Activities Resource Requirements
- Resource Breakdown Structure
Estimate Activities Durations
- Activities Durations Estimates
Develop Schedule
- Schedule Baseline - Schedule Data
- Project Schedule - Proj Calendars
Control Schedule
- WPI - Schedule Forecasts
- Change Request
Notes: Agile, Waterfall

## Slide 10: Control Schedule Inputs & Outputs
Control Schedule
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output
+
Change Request
Schedule Mgt Plan
Schedule Baseline (from the Develop Schedule process)
Project Schedule
Project Calendars
Schedule Data
(from the Develop Schedule process)
*: from the Direct & Manage Project Work process
**: to the Monitor & Control process
Schedule Forecast**
Notes: Agile, Waterfall

## Slide 11: What Control Schedule Entails?
(Ref: PMBOK 5th Ed, page 186)
Notes: Agile, Waterfall

## Slide 12: Control Schedule Inputs
Input | Details | 
PSMP | How to Monitor & Control Schedule | 
Schedule Baseline | Start & Finish Dates Sequencing & Logical Relationship (Dependencies) Milestones | 
WPD | Activities Completed with Start & Finish Dates Activities in Progress with Start Date & % Complete | 
OPA | Schedule control policies, procedures, guidelines Control Tools Monitoring & Reporting Methods | 
Proj Schedule | An output of a Schedule Model that presents linked activities with planned start/finish dates, durations, milestones, and resources | 
Proj Calendars | One or more Calendars | 
Schedule Data | Milestones Activities | Activities Attributes Assumptions & Constraints
Notes: Agile, Waterfall

## Slide 13: Control Schedule Outputs
Output | Details
WPI | SV & SPI for WBS components (WPs & Control Accounts)
Change Request | Based on Schedule Variance Analysis, Recommendations for: Changes to Schedule Baseline Corrective, Preventive Actions & Defect Repairs
PMP Updates | Schedule Baseline PSMP for any changes in Proj Schedule Management Cost Baseline
PD Updates | Schedule Data Project Schedule updated with actual situation Risk Register updated the schedule delay risks
OPA Updates | Causes of Variances Corrective Action chosen and the reasons Other types of Lessons learned
Schedule Forecast | Indirectly from Estimate At Completion (EAC) in EVM
Notes: Agile, Waterfall

## Slide 14: Control Schedule Tools & Techniques
Tool Category | Tools | 
Performance Reviews | Trend Analysis CPM CCM EVM | 
Project Management Software | e.g. MS Project, @ Risk | 
Resource Optimization Techniques | Resource Levelling Resource Smoothing | 
Modelling Techniques | What-If Scenario Simulation (Monte Carlo) | 
Leads & Lags |  | 
Schedule Compression | Crashing Fast Tracking | Reduce Scope Lower Quality
Scheduling Tool | Gantt Chart (Manual or Software) | 
Notes: Agile, Waterfall

## Slide 15: Trend Analysis
Variance Trend
Performance Index Trend
Regression Analysis
Performance improving or deteriorating?
Forecast
Notes: Agile, Waterfall

## Slide 16: Critical Path Method – MC Challenges when Multiple Paths Near Critical
Paths | Duration
Start-D-E-G-H-C-End | 32
Start-D-F-G-H-C-End | 31
Start-D-F-B-End | 16
Start-A-F-G-H-C-End | 33
Start-A-F-B-End | 18
Variance on Critical Path have a direct impact on the Project
Variance on Near Critical Paths can identify Schedule Risk; more the Near Critical Paths, more the Risks of Delays
Status of Floats; more the remaining float more the flexibility, security. In a way this is RESERVE ANALYSIS
Avoid such a situation by exploring the possibility of fast tracking on any near critical path, or even introducing a dummy activity on the critical path as a reserve margin; a dummy activity, of say 8, would help eliminate the other two near critical paths
3 Near Critical Paths
Start
D
A
E
G
H
C
F
B
End
4
8
5
7
8
6
7
5
Notes: Agile, Waterfall

## Slide 17: Critical Chain Method – MC Challenges when little Buffer on Feeder Path
Difference between Buffer remaining and Buffer needed to protect the delivery/completion date of a Deliverable can help determine CORRECTIVE ACTION. In a way this is RESERVE ANALYSIS
Start
End
A
2
B
6
C
5
D
7
E
5
G
5
H
6
F
6
Without Buffers, CDEF = 23
GHEF = 24
Start
End
A
2
B
6
Feeding Buffer
9+5
C
5
D
7
E
5
G
5
H
6
F
6
Resource Buffer
5
Feeding Buffer
1+5
Project Buffer
8
Max Feeding Buffer available on GHEF is 23-22=1. Should G or H be delayed by 1 or more, it will make this path the Critical Chain
Feeding Buffer
Feeding Buffer
9
1
Notes: Agile, Waterfall

## Slide 18: Resource Levelling … 1/3
Start
R1: 8 hrs
R2: 8 hrs
A
R1: 8 hrs
B
R2: 8 hrs
C
Day 1
Day 2
Day 3
Activity C dependent on Activities A & B
Duration 2 Days, but
R1 over-allocated
Over-allocation of R1 resolved by delaying Activities B & C by one day each
New Duration 3 Days
This is Resource Levelling
R1: 8 hrs
R2: 8 hrs
A
R1: 8 hrs
B
R2: 8 hrs
C
Start
Here Resource Levelling has been achieved by applying Lag on Activity B
The same result would be achieved if Activity B is put in FS dependency to Activity A, as indicated by the dotted line
Notes: Agile, Waterfall

## Slide 19: Resource Levelling … 2/3
Adjustment of Start & Finish Dates to produce a Resource Limited Schedule
Lengthens the Schedule & increases Cost to deal with a limited amount of Resources, Resource Availability and other Resource Constraints
Also caters to situation where lengthening of Schedule is preferred to hiring Resources
Downside:
  Can cause change in the Critical Path or generate Near Critical Paths
  Lengthens the Schedule & increases Cost
Notes: Agile, Waterfall

## Slide 20: Resource Levelling … 3/3
“Lag” applied to a dependent activity in an SS or FF dependency is akin to Resource Levelling
to
A
B
An SS Dependency
to
A
B
An FF Dependency
A
B
The same FF Dependency with Lag applied to B
Lag
A
B
The same SS Dependency with Lag applied to B
Lag
Notes: Agile, Waterfall

## Slide 21: Resource Smoothing … 1/2
A technique that adjusts the activities of a Schedule Model such that the requirements for Resources on the Project do not exceed certain Predefined Source Limits; consider the following the Resources Requirement for a project:
The Resources have been capped at 5, considering the Float of the Activities, and ensuring that the completion dates are not changed, thereby maintaining the integrity of the Critical Path
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Series 1 | 2 | 3 | 5 | 7 | 8 | 6 | 4 | 2
Column1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Series 1 | 2 | 3 | 5 | 7 | 8 | 6 | 4 | 2
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Series 1 | 2 | 3 | 5 | 5 | 5 | 5 | 4 | 2
Column1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Notes: Agile, Waterfall

## Slide 22: Resource Smoothing … 2/2
For periods requiring more than 5 resources, shortfall would be hired. For periods requiring less than 5 resources, the extra resources would be employed on other activities
Critical Path is not changed
Notes: Agile, Waterfall

## Slide 23: Crashing
Adding or adjusting resources in activities on the Critical Path in order to compress the schedule while maintaining the original Project Scope
Trades Time for Money
Downside: Increased Costs, and possibly Risk
R1, R2
R1, R2,
R3, R4
Notes: Agile, Waterfall

## Slide 24: Fast Tracking
A schedule compression technique in which activities or phases normally done in series, or planned in series, are performed in parallel for at least a portion of their duration
Downside: Often results in Rework (Cost), usually increases Risk and requires more attention to Communication
“Lead” applied to a dependent activity in an FS dependency is akin to Fast Tracking
A
B
C
A
B
C
to
to
D
E
An FS Dependency
D
E
Lead
The same FS Dependency with Lead applied to E
Notes: Agile, Waterfall

## Slide 25: Leads & Lags … 1/6
Applied during Network Analysis to find ways to:
  bring Project Activities that are behind into alignment with the Plan, (Leads) or
  make adjustments to the Start or Finish Dates of Activities to meet certain technical or other requirements (Lags)
Lead Amount of time a Successor (Dependent) activity can be advanced with respect to a Predecessor activity. Akin to Fast Tracking
Lag Amount of time a Successor (Dependent) activity can be delayed with respect to a Predecessor Activity. Akin to Resource Levelling
In the Examples following:
Total Duration is of Predecessor & Dependent Activities put together, minus the overlap or plus the gap
Start & Finish Dates are of the Dependent Activity wrt the Successor Activity
Notes: Agile, Waterfall

## Slide 26: Leads & Lags … 2/6
-12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
0
10
7
10
7
FS
FS-2
Total Dur = 15 wks
Start = Wk 9
Finish = Wk 15
Complete Punch List: 10 wks
Landscape Building Lot: 7 wks
FS-2 wks
(Lead)
This also means Fast Tracking the activities by 2 weeks
Notes: Agile, Waterfall

## Slide 27: Leads & Lags … 3/6
-12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
0
10
7
10
7
FF
FF-2
Total Dur = 10 wks
Start = Wk 2
Finish = Wk 8
Complete Punch List: 10 wks
Landscape Building Lot: 7 wks
FF-2 wks
(Lead)
Notes: Agile, Waterfall

## Slide 28: Leads & Lags … 4/6
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
0
1
15
FS
FS+12
Start = Day 2
Finish = Day 28
Total Dur = 28 days
1
15
Ground Floor Slab: 1 d
Brickwork for 1st Floor: 15 d
FS+12 d (Lag – for curing time)
Notes: Agile, Waterfall

## Slide 29: Leads & Lags … 5/6
-12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
0
60
50
SS
SS+15
Start = Day 16
Finish = Day 65
Total Dur = 65 days
60
50
Write Draft: 60 d
Edit Draft: 50 d
SS+15 d (Lag)
This cannot be a case of Resource Levelling since the Lag is due to Technical Reasons and not due to Resource Constraints
Notes: Agile, Waterfall

## Slide 30: Leads & Lags … 6/6
-12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
0
10
8
FF
FF+5
Total Dur = 15 wks
Start = Wk 4
Finish = Wk 15
10
8
Complete Interiors: 10 wks
Landscape Building Lot: 8 wks
FF + 5 wks
(Lag)
If the Lag is due to Resource Constraints, it is a case of Resource Levelling too
Notes: Agile, Waterfall

## Slide 31: What-If Scenario … 1/2
Process of evaluating scenarios in order to predict their Effect (+ve or –ve) on Project Objectives
An analysis of the question: “What if the situation represented by scenario ‘X’ happens?” eg in a Wedding Project, an Event Manger may think of following situations for an inter-city barat:
What if a dulha’s dress does not fit?
What if the buses do not arrive?
What if a barat vehicle drops out or goes amiss?
What if dacoits greet the wedding party enroute?
What if buggy breaks down or does not turn up?
What if the band does not turn up?
What if barat reaches late?
What if bride walas delay the food?
What if the guests get food poisoning?
Notes: Agile, Waterfall

## Slide 32: What-If Scenario … 2/2
The event manager will prepare contingency plans for each of these scenarios
In General,
Schedule Network Analysis is performed using Schedule to compute difference scenarios such as delays in major component delivery, extension of specific engineering durations, force majeure etc
Outcome of analysis used to assess the Feasibility of the Project Schedule under adverse conditions, preparing Contingency & Response Plans to overcome or mitigate he impact of the unexpected situations
Often, there is no way to meet the Schedule if these scenarios occur. But it always makes sense to try to understand the impact they will have on the Schedule
A tool more for Risk Management than Time Management
Notes: Agile, Waterfall

## Slide 33: Simulation
Project Duration
Calculating Multiple Project Durations with different sets of activity Assumptions, usually using Probability Distributions constructed from the 3-Point Estimates to account for uncertainty
Example: Monte Carlo simulation in which a distribution of possible activity durations is defined for each activity and used to calculate a distribution of possible outcomes for the total project
Notes: Agile, Waterfall