## Slide 1: Control Costs
MEC-5
Outline
Cost Baseline, Project Funding Requirements & Project Budget
Contingency Reserves and Management Reserves
Control Costs process
Cost Controlling Tools & Techniques
Simple Exercise in Cost MC on MS Proj 2010
Readings
PMBoK, pages 212-226.
Rita, pages 88 & 262-266.
Step by Step, Ch 13 & 14
Lecture Notes

## Slide 2: Cost Baseline
Approved Version of the Time Phased Cost Budget for the Project (Spending Plan indicating how much money is approved for the Project and when the Funds are required – the Cash Flow Plan)
Excludes Management Reserves
Developed as a summation of the approved budgets for the different Schedule Activities, Work Packages etc
The Cost Baseline is, therefore, Accumulative and Activity/ Work Package based
Notes: Agile, Waterfall

## Slide 3: Project Funding Requirements
Forecasted Proj Costs (Projected Expenditures + Liabilities)
Project Funding Requirements
Total and Periodic Funding Requirements (eg monthly, quarterly, annually), derived from the Cost Baseline
Funding Requirements is, therefore, Periodic Time-based
Includes Projected Expenditures plus Anticipated Liabilities
Management Reserves are not part of the Cost Baselines but they are part of the Project Funding requirements. Therefore, the difference between the Cost Baseline and Funding requirement at Project completion is Management Reserves, as depicted:
Cost Baseline
Management Reserves
Notes: Agile, Waterfall

## Slide 4: Relationship between Cost Baseline, Project Funding Requirements & Project Budget
Forecasted Proj Costs (Projected Expenditures + Liabilities)
Project Funding Requirements
Cost Baseline
Management Reserves
Management Reserves
Project Budget
Notes: Agile, Waterfall

## Slide 5: Cost Baseline & Management Reserve
PV
AC
Notes: Agile, Waterfall

## Slide 6: Project Budget & Cost Baseline
Total Amount −−→ | Project Budget | Management Reserves |  |  | 
 |  | Cost Baseline | Control Accounts | Contingency Reserve1 | 
 |  |  |  | Work Package Cost Estimates | Activities Contingency Reserves
 |  |  |  |  | Activities Cost Estimates
 | Project Budget Component |  |  |  | 
1For those Work Packages which do not break down into activities
Costs estimated for all resources:
Direct Labour
Materials
Equipment
Services
Facilities
IT
Financing (incl Int)
Inflation allowance
Exchange Rates
Indirect Costs (can be included at the activity level or at higher levels)
Ref: PMBOK 5th Ed, page 213
Notes: Agile, Waterfall

## Slide 7: Funding Requirements, Project Budget & Cost Baseline
Chart: Activities
| 0 | 1 | 3 | 5 | 8 | 8 | 10 | 13 | 13 | 15 | 18 | MR
Funding Requirement | 0 | 100 | 200 | 200 | 300 | 500 | 600 | 400 | 250 | 150 | 100 | 500
Baseline | 0 | 100 | 300 | 500 | 800 | 1300 | 1900 | 2300 | 2550 | 2700 | 2800
Proj Budget | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300
Activity | Due (Wk) | Activity Cost | Accumulative (Baseline) | Project Budget
1 | 1 | 100 | 100 | 
2 | 3 | 200 | 300 | 
3 | 5 | 200 | 500 | 
4 | 8 | 300 | 800 | 
5 | 8 | 500 | 1,300 | 
6 | 10 | 600 | 1,900 | 
7 | 13 | 400 | 2,300 | 
8 | 13 | 250 | 2,550 | 
9 | 15 | 150 | 2,700 | 
10 | 18 | 100 | 2,800 | 
MR |  | 500 |  | 3,300
Baseline
Funding Requirements
Notes: Agile, Waterfall

## Slide 8: Simple CBS & Project Budgeting
Activities
Work Packages
Control Accounts
Cost Baseline
Management Reserves
Project Budget
725
750
350
75
550
100
1,900
650
2,550
500
3,050
160
15
220
30
260
40
250
50
360
90
Notes: Agile, Waterfall

## Slide 9: Processes in the Cost Knowledge Area
Plan Cost Management
- Cost Management Plan
Process
Key Outputs
Estimate Costs
- Activities Cost Estimates
- Basis of Estimates
Determine Budget
- Cost Baseline
- Project Funding Requirements
Control Costs
- WPI - Cost Forecasts
- Change Request
Notes: Agile, Waterfall

## Slide 10: Control Costs Inputs & Outputs
Control Costs
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output
+
Change Request
Cost Mgt Plan
Cost Baseline (from the Determine Budget process)
Project Funding Requirements (from the Determine Budget process)
Activity Cost Estimates
Basis of Estimates
*: from the Direct & Manage Project Work process
**: to the Monitor & Control process
Cost Forecasts**
(from the Estimate Costs process)
Notes: Agile, Waterfall

## Slide 11: Control Costs Inputs & Outputs
Ref: PMBOK 5th Ed, page 215
Notes: Agile, Waterfall

## Slide 12: Control Costs Inputs
Input | Details
Project Cost Management Plan | How the Project Costs will be Controlled
Project Management Plan | Cost Management Plan Cost Baseline
WPD | Activities that have Started Activities’ Progress Finished Deliverables Costs Incurred
OPA | Cost Control-related Policies, Procedures & Guidelines Control Cost Tools Monitoring & Reporting Methods
Project Funding Requirements | Projected Expenditures Anticipated Liabilities
Notes: Agile, Waterfall

## Slide 13: Control Cost Outputs 1/2
Output | Details
WPI | CV & CPI values for WBS components, in particular the Work Packages and Control Accounts
Change Request | Based on Cost Variance Analysis, Recommendations for: Changes to Baselines (Cost, Scope etc) Corrective, Preventive Actions & Defect Repairs
PMP Updates | Based on Change Requests, projected Changes to: Cost Baseline viz Activity Cost Estimates etc PCMP, such as changes to Control Thresholds, or specified Levels of Accuracy reqd in managing the Project’s Cost, or Changes based on Stakeholders’ feedback
PD Updates | Cost estimates Basis of estimates
Notes: Agile, Waterfall

## Slide 14: Control Cost Outputs 1/2
Output | Details
OPA Updates | Causes of Variances Corrective Action chosen and the Reasons Financial Databases Other types of lessons learned from Project Cost Control
Cost Forecast | EAC, ETC, VAC, TCPI for the Remaining Project
Notes: Agile, Waterfall

## Slide 15: Control Costs Tools & Techniques
Tool Category | Tools
Performance Reviews | EVM TCPI Forecasting Variance Analysis Trend Analysis Reserve Analysis
Project Management Software | e.g. MS Project
Notes: Agile, Waterfall