## Slide 1: Earned Value Management
MEC-6
Outline
Key Terms, and Status and Forecasting aspects of EVM
Explanation of concepts through EVM tracking on a Simple Project
EVM Graphics
In-depth look at EV, PV and EAC(Cost)
Readings
PMBoK, pages 217-224.
Rita, pages 266-279.
Lecture Notes.

## Slide 2: Earned Value Management (EVM)
Tool to determine both Cost & Schedule Variances
Key Terms (Some common with Schedule Variance, others specific to Schedule Variance:
Budget At Completion (BAC)
Planned Value (PV)
Earned Value (EV)
Actual Cost (AC)
Cost & Schedule Variances (CV & SV)
Cost & Schedule Performance Indices (CPI & SPI)
Current Schedule & Cost Performance
Forecast Schedule & Cost Performance
Estimate At Completion (EAC)
Estimate To Complete (ETC)
Variance At Completion (VAC)
To Complete Performance Index (TCPI)
Notes: Agile, Waterfall

## Slide 3: When to EVA?
Any time
At Planned completion of Activities, Work Pages or Milestones
At Actual completion of Activities, Work Packages or at Actual Milestones (best)
Notes: Agile, Waterfall

## Slide 4: Simple Project
Activity | Duration | Estimated Cost + Cont Res | Predecessor Activity | Successor Activity
A | 4 | 200 | ST | B
B | 6 | 540 | A | C,G
G | 3 | 270 | B | D
C | 5 | 550 | B | D
D | 4 | 600 | C,G | E
E | 6 | 540 | D | F
F | 5 | 300 | E | END
Baseline Cost |  | 3,000 |  | 
End of Time Period | PV/Cost Baseline
4 | 200
10 | 740
13 | 1,010
15 | 1,560
19 | 2,160
25 | 2,700
30 | 3,000
Data from the network diagram tabulated along with costing of each activity. Scheduling & Costing information converted into the Cost Baseline/PV
A 4 (200)
B 6 (540)
C 5 (550)
D 4 (600)
END
E 6 (540)
F 5 (300)
ST
G 3 (270)
Let us take a simple project and do its EV analysis (EVA) at different points of its execution
(Figure in the parenthesis is the cost of the Activity inclusive of its Contingency Reserve)
Notes: Agile, Waterfall

## Slide 5: Simple Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
50 | 100 | 150 | 200 | 290 | 380 | 470 | 560 | 650 | 740 | 940 | 1,140 | 1,340 | 1,450 | 1,560 | 1,710 | 1,860 | 2,010 | 2,160 | 2,250 | 2,340 | 2,430 | 2,520 | 2,610 | 2,700 | 2,760 | 2,820 | 2,880 | 2,940 | 3,000 |  | 
A 4 (200)
B 6 (540)
C 5 (550)
D 4 (600)
END
E 6 (540)
F 5 (300)
ST
G 3 (270)
Figure in the parenthesis is the cost of the Activity inclusive of its Contingency Reserve
A 4/200
B 6/540
D 4/600
C 5/550
E 6/540
F 5/300
G 3/270
← Cost Baseline
Notes: Agile, Waterfall

## Slide 6: EVA of the Project on completion of Activity A
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
50 | 100 | 150 | 200 | 290 | 380 | 470 | 560 | 650 | 740 | 940 | 1,140 | 1,340 | 1,450 | 1,560 | 1,710 | 1,860 | 2,010 | 2,160 | 2,250 | 2,340 | 2,430 | 2,520 | 2,610 | 2,700 | 2,760 | 2,820 | 2,880 | 2,940 | 3,000 | PV | 
A 4/200
B 6/540
D 4/600
C 5/550
E 6/540
F 5/300
G 3/270
A 5/300
D 4/600
E 6/540
F 5/300
B 6/540
C 5/550
G 3/270
Today
How much we had planned to achieve so far? This is PV
PV = A+Bx2/6 = 200+540x2/6 = 380
What have we earned so far? This is EV
EV = A = 200
How much the project has cost us so far? This is AC
AC = 300
CV = EV-AC = 200-300 = -100
CPI = EV/AC = 200/300 = 0.67
CV% = CV/EV = -100/200 = - 50%
SV = EV-PV = 200-380 = -180
SPI = EV/PV = 200/380 = 0.53
SV% = SV/PV = -180/380 = - 60%
Notes: Agile, Waterfall

## Slide 7: EVA of the Project on completion of Activity B
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
50 | 100 | 150 | 200 | 290 | 380 | 470 | 560 | 650 | 740 | 940 | 1,140 | 1,340 | 1,450 | 1,560 | 1,710 | 1,860 | 2,010 | 2,160 | 2,250 | 2,340 | 2,430 | 2,520 | 2,610 | 2,700 | 2,760 | 2,820 | 2,880 | 2,940 | 3,000 | PV | 
A 4/200
B 6/540
D 4/600
C 5/550
E 6/540
F 5/300
G 3/270
A 5/300
B 6/600
D 4/600
E 6/540
F 5/300
C 4/550
G 3/270
Today
PV = A+B+Cx2/5+Gx2/3
= 200+540+550x2/5+270x2/3 = 1,140
EV = A+B = 200+540 = 740
AC = A+B = 300+600 = 900
CV = EV-AC = 740-900 = -160
CPI = EV/AC = 740/900 = 0.82
CV% = CV/EV = -160/740 = - 22%
SV = EV-PV = 740-1,140 = -400
SPI = EV/PV = 740/1,140 = 0.65
SV% = SV/PV = -400/1,140 = - 35%
Notes: Agile, Waterfall

## Slide 8: EVA of the Project on completion of Activities C&G
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
50 | 100 | 150 | 200 | 290 | 380 | 470 | 560 | 650 | 740 | 940 | 1,140 | 1,340 | 1,450 | 1,560 | 1,710 | 1,860 | 2,010 | 2,160 | 2,250 | 2,340 | 2,430 | 2,520 | 2,610 | 2,700 | 2,760 | 2,820 | 2,880 | 2,940 | 3,000 | PV | 
A 4/200
B 6/540
D 4/600
C 5/550
E 6/540
F 5/300
G 3/270
A 5/300
B 6/600
C 5/600
G 4/300
D 4/600
E 6/540
F 5/300
Today
PV = A+B+C+G+D/2
= 200+540+550+270+600/2 = 1,860
EV = A+B+C+G = 200+540+550+270 = 1,560
AC = A+B+C+G = 300+600+600+300 = 1,800
CV = EV-AC = 1,560-1,800 = -240
CPI = EV/AC = 1,560/1,800 = 0.87
CV% = CV/EV = - 240/1,560 = - 15%
SV = EV-PV = 1,560-1,860 = -300
SPI = EV/PV = 1,560/1,860 = 0.84
SV% = SV/PV = -300/1,860 = - 16%
Notes: Agile, Waterfall

## Slide 9: EVM Graphics
Chart: Time
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
PV | 0 | 50 | 100 | 150 | 200 | 290 | 380 | 470 | 560 | 650 | 740 | 940 | 1140 | 1340 | 1450 | 1560 | 1710 | 1860 | 2010 | 2160 | 2250 | 2340 | 2430 | 2520 | 2610 | 2700 | 2760 | 2820 | 2880 | 2940 | 3000
Baseline | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
Proj Budget | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150 | 3150
EV | 0 | 200 | 740 | 1560
AC | 0 | 300 | 900 | 1800
Proj Budget = 3,000+150 = 3,150
Baseline Budget/BAC = 3,000
EV
AC
PV
EAC(Time)
EAC(Cost)
Work Remaining
Funds Remaining
VAC
CV
SV
ETC/Funds Reqd to complete the Proj
Management Reserves @ 5% = 150
380
VAC = BAC-EAC = 3,000-3,500 = -500
Work Rem = BAC-EV = 3,000-1,560 = 1,440
Funds Rem = BAC-AC = 3,000-1,800 = 1,200
ETC = EAC-AC = 3,500-1,800 = 1,700
TCPIBAC = work rem/funds rem = (3,000-1,560)/(3,000-1,800) = 1.2
TCPIEAC = work rem/funds req = (3,000-1,560/(3,500-1,800) = 0.85
CV = EV-AC = 1,560-1,800 = -240
CPI = EV/AC = 1,560/1,800 = 0.87
CV% = CV/EV = - 240/1,560 = - 15%
SV = EV-PV = 1,560-1,860 = -300
SPI = EV/PV = 1,560/1,860 = 0.84
SV% = SV/PV = -300/1,860 = - 16%
EACtime = Baseline Time/SPI = 30/0.84 = 38
EACcost = Baseline Cost/CPI = 3,000/0.87 = 3,448
Notes: Agile, Waterfall

## Slide 10: Finding Variances & Indices – Basic leading Questions
Schedule Variance & Performance Index:
What we have EARNED (EV) and what we had PLANNED TO EARN (PV)?
Cost Variance & Performance Index:
What we have EARNED (EV) and at WHAT COST (AC)?
Notes: Agile, Waterfall

## Slide 11: EVM Graphics - Tracking Variances & Indices
Chart: Timeline
| 0 | 3 | 6 | 9 | 12 | 15 | 20 | 25 | 30
Ideal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SV | -50 | -40 | -50 | -30 | -20
CV | -40 | -50 | -30 | -40 | -30
SPI | 0.75 | 0.9 | 0.91667 | 0.9625 | 0.98
CPI | 0.78947 | 0.87805 | 0.94828 | 0.95062 | 0.9703
Notes: Agile, Waterfall

## Slide 12: Further Look at the EAC(Cost)
3. What has been Spent + Budget for Remaining Work modified by Cost & Schedule Performance
= 1,800 + 1,440/(0.87 x 0.84) = 3,770
If the CPI is expected to be the same for the remainder of the project
= 3,000/0.87 = 3,448
BAC
CPI
EAC =
4. What has been Spent + What more to be Spent on Remaining Work; initial plan needs review (re-estimate remaining activities bottom up)
EAC = AC + new bottom up ETC = 1,800 + 1,750 (say) = 3,550
2. What has been Spent + Budget for Remaining Work; if future work will be accomplished at the planned rate:
EAC = AC + (BAC – EV ) = 1,800 + (3,000 – 1,560) = 3,240
EAC = AC +
(BAC – EV)
CPI x SPI
Notes: Agile, Waterfall

## Slide 13: EVM – Another Simplified Example
Analysis (WPI)
80 blocks should have cost: 80 x Rs 10K = Rs 800K. This is EV
At the end of Day 10, 100 blocks should have been delivered, which would have cost: 100 x Rs 10K = Rs 1,000K. This is PV
These 80 blocks actually invoiced/cost Rs 900K. This is AC
Procurement Project
200 heavy duty concrete security blocks. This is Project Scope
Total Cost: Rs 2,000K. This is BAC
Rs 10K per block; 200 blocks deliverable in 20 days @ 10 blocks per day. This is Cost Baseline
Contract Type: Cost Reimbursable
Situation at the end of Day 10
80 blocks delivered; Contractor invoiced Rs 900K for these 80 blocks. This is WPD
Notes: Agile, Waterfall

## Slide 14: EVM Cost Performance - Simplified Example
Chart: Time in Days
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Series 1 | 0 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000
Series 2 | 0 | 80 | 160 | 240 | 320 | 400 | 480 | 560 | 640 | 720 | 800
Series 3 | 0 | 90 | 180 | 270 | 360 | 450 | 540 | 630 | 720 | 810 | 900
PROJ BUDGET = 2,000+150 = 2,150
MGT RES @ 7.5% = 150
SV= 800-1,000 = -200
SPI= 800/1,000 = 0.80
CV = 800-900 = -100
CPI = 800/900 = 0.89
AC
EV
PV
Cost Baseline
BAC = 2,000
CV

## Slide 15: EVM Cost Performance - Simplified Example
Chart: Time in Days
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Series 1 | 0 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000
Series 2 | 0 | 80 | 160 | 240 | 320 | 400 | 480 | 560 | 640 | 720 | 800
Series 3 | 0 | 90 | 180 | 270 | 360 | 450 | 540 | 630 | 720 | 810 | 900
Series 4 | 800 | 880 | 960 | 1040 | 1120 | 1200 | 1280 | 1360 | 1440 | 1520 | 1600 | 1680 | 1760 | 1840 | 1920 | 2000
PROJ BUDGET = 2,000+150 = 2,150
MGT RES @ 7.5% = 150
SV= 800-1,000 = -200
SPI= 800/1,000 = 0.80
CV = 800K-900 = -100
CPI = 800/900 = 0.89
AC
EV
PV
Cost Baseline
BAC = 2,000
CV

## Slide 16: EVM Cost Performance - Simplified Example
Chart: Time in Days
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Series 1 | 0 | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000
Series 2 | 0 | 80 | 160 | 240 | 320 | 400 | 480 | 560 | 640 | 720 | 800
Series 3 | 0 | 90 | 180 | 270 | 360 | 450 | 540 | 630 | 720 | 810 | 900
Series 4 | 800 | 880 | 960 | 1040 | 1120 | 1200 | 1280 | 1360 | 1440 | 1520 | 1600 | 1680 | 1760 | 1840 | 1920 | 2000
Series 5 | 900 | 990 | 1080 | 1170 | 1260 | 1350 | 1440 | 1530 | 1620 | 1710 | 1800 | 1890 | 1980 | 2070 | 2160 | 2250
EAC
PROJ BUDGET = 2,000+150 = 2,150
VAC
ETC
MGT RES @ 7.5% = 150
VAC = 2,000-2,250 = -250
SV= 800-1,000 = -200
SPI= 800/1,000 = 0.80
CV = 800K-900 = -100
CPI = 800/900 = 0.89
EAC = 2,000/.89 = 2,250
ETC = 2,250-900 = 1,350
Work Remaining
AC
EV
PV
Cost Baseline
Funds Remaining
TCPIBAC = (2,000-800)/(2,000-900) = 1.09
TCPIEAC = (2,000-800)/(2,250-900) = 0.89
BAC = 2,000
CV

## Slide 17: EAC(Cost) in the Last Example
3. = 900 + 1,200/(0.89 x 0.80) = 2,588
= 2,000/0.89 = 2,250
BAC
CPI
EAC =
4. EAC = AC + new bottom up ETC = 900 + 1,400 (say) = 2,300
2. EAC = AC + (BAC – EV ) = 900 + (2,000 – 800) = 2,100
EAC = AC +
(BAC – EV)
CPI x SPI
Notes: Agile, Waterfall

## Slide 18: Finding EV & PV from Narrative when taking Uniform Rates
PV | EV
Portioning BAC on the basis of Fraction of Time Completed | Portioning BAC on the basis of Fraction of Work Completed
Evaluating Work Planned on the basis of Baselined Cost per Unit | Evaluating Work Completed on the basis of Baselined Cost per Unit
Pitching Time Completed against PV per Unit Time | 
Portioning BAC using Fraction of Time/Work Completed
Evaluating Work Planned/Completed using Rate (Cost per Unit)
Notes: Agile, Waterfall

## Slide 19: Finding EV & PV when taking Uniform Rates
Example:
On a certain project, 200 km of oil pipeline is to be laid, in 50 weeks, at a Cost of 2,200 monetary units (mu). Assume the rate of laying the pipeline to be uniform. Today, at the end of Week-20, 90 km has been laid. What is the PV and EV?
Baselined Cost per unit work = 2,200 mu/200 km = 11 mu/km
Work Planned per unit time = 200 km/50 wks = 4 km/wk
Work Planned = time elapsed x work per unit time = 20 wk x 4km/wk = 80 km
PV per unit time = 2,200 mu/50 wks = 44 mu/wk
PV = Fraction of Time Completed x BAC = 20 wk/50wk x 2,200 mu = 880 mu
PV = Work Planned x Cost per km = 80 km x 11 mu/km = 880 mu
PV = Time Completed x PV per Unit Time = 20 wk x 44 mu/wk = 880 mu
EV = Fraction of Work Completed x BAC = 90 km/200km x 2,200 mu = 990 mu
EV = Work Completed x Cost per km = 90 km x 11 mu/km = 990 mu
Notes: Agile, Waterfall

## Slide 20: EVM - General Template for Schedule & Cost Monitoring, Evaluation & Forecast
PV
AC
SV
SV
EV
CV
At Completion Schedule Variance
ETC
Work Remaining
Funds Remaining
VAC
BAC
EAC
Baseline Proj Duration
Estimated Proj Duration
Notes: Agile, Waterfall

## Slide 21: EVM for Cost Performance – Present Status
Term | Formula | What it means
Planned Value (PV) |  | As of today, the estimated value of the WORK PLANNED to be done
Earned Value (EV) |  | As of today, the estimated value of the WORK ACTUALLY ACCOMPLISHED?
Budget at Completion (BAC) |  | BUDGET for the TOTAL PROJECT
Cost Variance (CV) | = EV-AC | Difference between ACCOMPLISHED WORK & PLANNED WORK (+ under, - over budget)
Cost Performance Index (CPI) | = EV/AC | Comparison of ACCOMPLISHED WORK with PLANNED WORK (ACCOMPLISHED WORK as fraction or % of PLANNED WORK) (>1 under, <1 over budget)
Notes: Agile, Waterfall

## Slide 22: EVM for Cost Performance – Forecast
Term | Formula | What it means
Estimate At Completion (EAC) | BAC/CPI AC + ETC AC + (BAC-EV) AC + (BAC-EV) CPI x SPI | As of today, how much is the TOTAL PROJECT COST Expected to be?
Estimate To Complete (ETC) | EAC-AC | As of today, how much MORE the Project will Cost?
Variation At Completion (VAC) | BAC-EAC | How much OVER or UNDER BUDGET the Project will be at Completion
To-Complete Performance Index (TCPI) | (BAC-EV) (BAC-AC)* | CPI of the Remaining Work Ratio of WORK REMAING to MONEY REMAINING * Denominator based on BAC or EAC
Notes: Agile, Waterfall