## Slide 1: Controlling Human Resources on Projects
MEC-7
Outline
Relationship between HR Management and HR Control
Controlling HR through Manage Project Team process
Getting Cooperation from Project Team & Stakeholders
HR Conflicts on Projects - their inevitability, prevention and resolution
HR Conflicts in terms of Assertiveness and Empathy
Leadership and Leadership Styles
Leadership Styles in terms of Relationships and Task Behaviour
Readings
PMBoK, pages 279-285.
Rita, pages 357-365.
Lecture Notes

## Slide 2: What is Controlling HR?
Controlling Human Resources in Project Management is an in-built activity into the “Manage Project Team” process, which is the:
“The process of tracking team member performance, providing feedback, resolving issues, and managing changes to optimise project performance”
Though an Executing Process, a number of activities in the “Manage Project Team” pertain to MEC as well, as indicated in blue:
Encouraging good communication Working with other organisations Using negotiation skills Using leadership skills Observing what is happening Using an issue log Keeping in touch | Completing project performance appraisals Making good decisions Influencing the stakeholders Being a leader Actively looking for and helping to resolve conflicts that the team members cannot resolve on their own
Notes: Agile, Waterfall

## Slide 3: Processes in the HR Knowledge Area
Plan HR Management
- HR Management Plan
Process
Key Outputs
Acquire Project Team
- Project Staff Assignments
- Resource Calendars
Develop Project Team
- Team Performance Assessments
Manage Project Team
- Change Requests
Notes: Agile, Waterfall

## Slide 4: Manage Project Team Inputs & Outputs
Manage Project Team
PMP
PDs (w/a)
WPD
OPA
Any Specific Input
PMP Updates
PD Updates
OPA Updates
EEF Updates
Any Specific Output
+
Change Request
HR Mgt Plan
Project Staff Assignments (from the Acquire Proj Team process)
Team Performance Assessments (from the Develop Proj Team process)
Issue Log (from the Manage Stakeholder Engagement)
*: from the Monitor & Control Project Work process
WPR*
X
X
X
Notes: Agile, Waterfall

## Slide 5: Manage Project Team Inputs … 1/2
Input | Details
HR Management Plan | How the Project HR should be defined, staffed, managed, controlled, and eventually released
Proj Staff Assignments | Documentation which lists project team members and their assignments
Team Performance Assessments | The project management team makes ongoing formal or informal assessments of the project team’s performance By continually assessing the project team’s performance, actions can be taken to resolve issues, modify communication, address conflict, and improve team interaction
Issue Log (specimen on next slide) | A project document used to document and monitor elements under discussion or in dispute between project Stakeholders
Notes: Agile, Waterfall

## Slide 6: Manage Project Team Inputs … 2/2
Issue # | Issue | Date | Raised by | Person Assigned | Resolution Due Date | Status | Date Resolved | Resolution
Input | Details
WPR | WPRs help determine future HR requirements, recognition and rewards from such performance areas as Performance areas as schedule control, cost control, quality control, and scope validation
OPA | OPA that can influence MEC aspects of project HR: • Certificates of appreciation, • Newsletters, • Websites, • Bonus structures, • Corporate apparel, and • Other organizational perquisites.
Notes: Agile, Waterfall

## Slide 7: Manage Project Team Outputs
Input | Details
Change Request | Staffing changes: - moving people to different assignments, outsourcing some of the work, and replacing team members who leave. Preventive actions like cross training to reduce problems during project team member absences and additional role clarification to ensure all responsibilities are fulfilled
Proj Mgt Plan Update | 
Project Documents Updates | Issue log, Project Staff Assignments
EEF & OPA Updates | Input to organisational performance appraisals Personnel skill updates Historical information and lessons learned documentation, Templates Organisational standard processes
Notes: Agile, Waterfall

## Slide 8: Manage Project Team Tools & Techniques
Input | Details
Observation and Conversation | Used to stay in touch with the work and attitudes of project team members The project management team monitors progress toward project deliverables, accomplishments that are a source of pride for team members, and interpersonal issues
Project Performance Appraisals | Done to clarify roles and responsibilities, provided constructive feedback to team members, discover unknown or unresolved issues, develop individual training plans, and establish of specific goals for future time periods
Conflict Management | Conflict resolution techniques
Interpersonal Skills | A combination of technical, personal, and conceptual skills to analyze situations and interact appropriately with team members, to capitalise on their strengths
Notes: Agile, Waterfall

## Slide 9: Getting Cooperation from Project Team & Stakeholders…1/2
Cooperation & Performance from Project Team & Stakeholders received by the Project Manager through exercise of Powers:
Positional Powers
Formal (Legitimate): Power based on Proj Manager’s authority
Example: “You need to listen to me when I tell you to do this work, because I have been put in charge!”
Reward: Power stemming from the Proj Manager rewarding the team members for good work
Example: “In view of your completing the last activity well on time and within budget, I am assigning you as part of the team going to China for the factory acceptance trials”
Penalty (Coercive): Power coming from the ability of the Proj Manager to penalise defaulting team members
Example: “If this does not get done on time, I will remove you from the group going to China for the factory acceptance trials”
Notes: Agile, Waterfall

## Slide 10: Getting Cooperation from Project Team & Stakeholders…2/2
Personal Powers
Expert: Power coming from the Project Manager being a technical or project management expert
Example: “This project manager has been very successful on other projects. Let’s give him a chance!”
“If the project manager wants to crash this activity through overtime, it’s got be crashed. Period”
Referent: Power coming from a Proj team member liking, respecting or wanting to be like the Proj Manager. It is the power of charisma and fame
Example: The most liked and respected project manager in the organization says, “I think we should change the content of our standard project charter”
Reward & Expert best powers
Notes: Agile, Waterfall

## Slide 11: Recognition & Reward System on the Project
Say such complimentary words as “Shabash”, “Well Done”, “Shukriya” etc more often; avoid counter-complimentary words, like “damn”, “bera gharak karr dia” etc
Award prizes, even simple goodies, on good performance
Recommend team members for raises, bonuses, promotions etc even if such actions do not form part of the performance reviews
Send notes to the Functional Mangers of the project team managers about their good performance
Hold milestone parties or other celebrations
Notes: Agile, Waterfall

## Slide 12: HR Conflicts – Old vs New Thinking
Old Thinking | New Thinking
Conflict is dysfunctional and caused by personality differences or a failure of leadership | Conflict is an inevitable result of organisation interactions
Conflict is to be avoided | Conflict can be beneficial
Conflict is resolved by physical separation or the intervention of the upper management | Conflict is resolved through openness, identifying the causes, and problems solving by the people involved and their immediate managers
Notes: Agile, Waterfall

## Slide 13: HR Conflicts – Inevitability on Projects
Reasons:
Nature of projects such that it tries to address the needs and requirements of many stakeholders
Limited power of the project manager (Functional/Weak Matrix Org)
Scarce resources
Necessity of obtaining resources from functional managers (Functional/Weak Matrix Org)
Scheduling priorities
Personal work styles
Notes: Agile, Waterfall

## Slide 14: HR Conflicts – Putting them in Order
Schedules
Project Priorities
Resources
Technical opinions
Administrative procedures
Cost
Personality
Notes: Agile, Waterfall

## Slide 15: HR Conflicts – Preventing them
Informing the team of:
Clearly assigning work without ambiguity or overlapping responsibilities
Making work assignment interesting and challenging
Following good project management and project planning practices
Exactly where the project is headed - Project constraints and objectives - The contents of the project charter - All key decisions - Changes |  | Good Communication
Notes: Agile, Waterfall

## Slide 16: HR Conflicts – Resolving them
Withdraw/Avoid. Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others (bury head in sand/closing eyes/lose-lose)
Smooth/Accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships (appeasing/lose-win or staying engaged → win-win)
Compromise/Reconcile. Searching for solutions that bring some degree of satisfaction to all parties in order to temporarily or partially resolve the conflict (give and take/trade off/win-win lose-lose)
Force/Direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency (might is right/win-lose)
Collaborate/Problem Solve/Confront. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment (win-win)
Notes: Agile, Waterfall

## Slide 17: HR Conflicts – Possible Approaches
Both of you want this Lab to come up. I am sure we can come to agreement on the purchase of computers and what is best for the project
Smoothing
We have talked enough about new computers. We’ll not have them (or we’ll have them)
Forcing
I suggest we run the CSE softwares on the existing computers and then see if they need to be replaced
Collaborating
Why was this lab not included in the development plans for the CFY? Let us wait for the NFY now
Withdrawing
Let us use the existing computers for CBT for admissions tests and buy new computers for the new Lab
Collaborating
Conflict Situation: A new Lab for CSE Dept is to be established. HOD wants new Computers for the Lab; Director Planning thinks the existing ones ex-stock will serve the purpose equally well
Let us equip the lab with 50% new computers and 50% existing computers
Compromising
Notes: Agile, Waterfall

## Slide 18: HR Conflicts – in terms of Empathy & Assertiveness
Concern for Others/Empathy
Concern for Self/Assertiveness
Force
Direct
Collaborate
Problem Solve
Confront
Withdraw
Avoid
Smooth
Accommodate
Compromise
Reconcile
Lose-Win
Win-Win
Win-Lose
Lose-Lose
Lose-Lose/Win-Win
Notes: Agile, Waterfall

## Slide 19: HR MEC – Leadership Styles … 1/3
Directing This style involves telling others what to do
Facilitating When facilitating, the project manager coordinates the inputs of others
Coaching In coaching, the manager helps others achieve their goals
Supporting A supporting leadership style means the project manager provides assistance along the way
Autocratic This is a top-down approach where the manager has power to do whatever he or she wants. The manager may coach or delegate, but everyone does what the manager wants them to do
Consultative This bottom-up approach uses influence to achieve results. The manager obtains others’ opinions and acts as the servant-leader for the team
Consultative-Autocratic In this style, the manager solicits input from team members, but retains decision-making authority for him - or herself
Notes: Agile, Waterfall

## Slide 20: HR MEC – Leadership Styles … 2/3
Consensus This style involves problem solving in a group, and making decisions based on group agreement.
Delegating With a delegating style, the manager establishes goals and then gives the project team sufficient authority to complete the work. For basic project management, the manager involves the team in the planning process and assigns or delegates planning and executing work to team members. Delegating can be hard for some people, because they feel they can do the work better themselves. Using proper project management practices should help a project manager feel comfortable that others know what needs to be done and that the project can be successful
Bureaucratic This style focuses on following procedure exactly. The bureaucratic style may be appropriate for work in which details are critical or in which specific safety or other regulations must be strictly adhered to
Notes: Agile, Waterfall

## Slide 21: HR MEC – Leadership Styles … 3/3
Charismatic Charismatic managers energize and encourage their team in performing project work. With this style, project success may become dependent on the presence of the charismatic leader, and the team relies on the leader for motivation.
Democratic or Participative This style involves encouraging team participation in the decision-making process. Team members “own” the decisions made by the group, which results in improved teamwork and cooperation.
Laissez-faire The French term “laissez-faire” has been translated as meaning “allow to act,” “allow to do,” or “leave alone.” A laissez-faire manager is not directly involved in the work of the team, but manages and consults as necessary, This style can be appropriate with a high skilled team.
Notes: Agile, Waterfall

## Slide 22: Leadership – in terms of Relationship & Task Behaviours
Participative
Consultative
Democratic
Charismatic
Supportive
Consensus
Guiding
Persuading
Selling
Coaching
Observing
Delegating
Laissez-faire
Directing
Autocratic
Telling
Bureaucratic
Task Behavior The extent to which the Project Manager engages in the Project, i.e., defining roles (telling what, how, when, where, and if more than one person, who is to do what), Goal Setting, Organising, Establishing Time Lines,
Relationship Behavior The extent to which the Project Manager engages with the Project Team in two-way (multi-way) communication, listening, facilitating behaviors, socio-emotional support
Task Behaviour
Relationship Behaviour
Notes: Agile, Waterfall