## Slide 1: Control Risks
MEC-9
Outline
The domain of Monitoring & Controlling Risks
Processes of the Risk KA and the Control Risk Process
Role of Contingency and Management Reserves in the MEC of Risks
Some typical Risk MEC Situations
Readings
PMBoK, pages 349-354.
Rita, pages 88 & 431-443.
Lecture Notes

## Slide 2: What is Monitoring & Controlling Risks?
» Monitoring & Controlling Risks is the process of:
implementing Risk Response Plans
tracking Identified Risks and their Trigger conditions, for their validity and changes
monitoring Residual and Secondary Risks
identifying and analysing New Risks (Known Unknowns)
controlling New Risks (Unknown Unknowns) as they occur
evaluating risk process effectiveness throughout the project
» Monitoring & Controlling responsibilities entrusted to the Risk Owners (Risk Owners also propose/develop and implement risk response plans)
Notes: Agile, Waterfall

## Slide 3: Actions involved in MEC of Risks -1/4
Look for the occurrence of Risk Triggers
Monitor Residual Risks
Identify New Risks and then analyse and plan for them (Risks can be identified anytime during the project, along with plans for how to handle the newly identified risks)
Evaluate the effectiveness of the risk management plan:
"Are the risk management processes working?"
Develop new Risk Responses:
"That plan no longer seems like it will work based on new information. Let's plan a different response."
Collect and communicate Risk Status to the stakeholders:
"Four identified risks occurred last month, and all risk response plans were implemented successfully. Next month we expect eight other risks to potentially occur. Risk reserves are still considered adequate for covering the identified risks on this project.” or
Notes: Agile, Waterfall

## Slide 4: Actions involved in MEC of Risks – 2/4
"Remember that one of the major risks on the project could occur next week"
Determine if Assumptions are still valid
Ensure proper risk management procedures are being followed
Revisit the Watch List to see if additional risk responses need to be determined:
"This change to the product scope might increase the impact of risk X, currently on our watch list. Let's analyse it"
Revisit the High and Medium Risks and see if they can be de-escalated to the Watch List; see if Medium Risks need escalation to High:
“Though we had risk Y rated High, do we need to de-escalate it in view of the improved law and order situation in the country?”
Notes: Agile, Waterfall

## Slide 5: Actions involved in MEC of Risks – 3/4
Recommend corrective actions to adjust to the severity of actual risk events:
"This risk did not have the impact we expected, so let's adjust the contingency plan we are in the middle of implementing and change what we will do if the risk reoccurs”
Look for any unexpected effects or consequences of risk events: "We did not expect this risk to damage the construction site if the risk occurred. We need to decide how to fix the damage after we finish implementing the already agreed-upon contingency plan."
Reevaluate risk identification and qualitative and quantitative risk analysis when the project deviates from the baseline:
"The project cost is over the cost baseline (or over the schedule baseline). This implies we missed some major risks. Let's hold a risk identification session."
Notes: Agile, Waterfall

## Slide 6: Actions involved in MEC of Risks - 4/4
Update risk management, response plans and project documents with approved changes and any relevant information from the work performance data
Look at the changes, including recommended corrective actions, to see if they lead to identifying more risks:
"We keep having to take corrective action related to this problem. Let's look at the root cause and identify any risks for the remaining part of the project that relate to the problem."
Submit change requests to integrated change control
Closing of Risks that are no longer applicable (to enable the team to concentrate on the risks that are still open)
Create a database of risk data that may be used throughout the organisation on other projects.
Perform variance and trend analysis on project performance data
Use contingency reserves and adjust for approved changes
Notes: Agile, Waterfall

## Slide 7: Processes in the Risk Knowledge Area
Plan Risk Management
- Risk Management Plan
Identify Risks
- Risk Register
Process
Key Outputs
Perform Qualitative Analysis
-
Perform Quantitative Analysis
-
Plan Risk Responses
-
Control Risks
- WPI
- Change Request
Notes: Agile, Waterfall

## Slide 8: Control Risks Inputs & Outputs
Control Risks
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output
+
Change Request
Risk Mgt Plan
Risk Register (from Identify Risks)
*: from the Direct & Manage Project Work process
**: to the Monitor & Control process
Risk Register updated:
New Risks
Residual Risks
Secondary Risks
Other Changes ***
WPR (from Mon & Cont Proj Work)
X
***: changes to Risk Register contents resulting from implementation of Response Plans, Risk Reassessment, Risk Audits, Risk Reviews, etc
Notes: Agile, Waterfall

## Slide 9: WPD → WPI → WPR Flow Path Complete Model
Direct & Manage Proj Work
Control Scope
Control Schedule
Control Costs
Control Quality
Control Comm
Control Risks
Control Procurements
Control S/Holder Engagement
Validate Scope
WPD
WPIs
Monitor & Control Proj Work
Perform Integrated Change Control
Develop PMP
Manage Proj Team
Manage Comm
WPRs
Approved Change Requests
Project Documents Updates
Project Plan Updates
Notes: Agile, Waterfall

## Slide 10: Monitor & Control Risks Inputs
Input | Details
Project Risk Management Plan | How the Project Risks will be Monitored & Controlled
WPD | Status of Deliverables Schedule Progress Costs incurred
WPR | EV Data (including Forecasting Data) Variance Analysis
Risk Register | Key inputs for Risks monitoring & control: |  | 
 | Identified Risks Watch List Risk Responses | Residual Risks Risk Owners Risk Trigger | Contingency Reserves (Time & Cost)
Notes: Agile, Waterfall

## Slide 11: Monitor & Control Risks Outputs … 1/2
Output | Details
WPI | Results of Risk Audits Status of risks (possibility of their closure now or in near future) Assessment of Risks
Change Request | Corrective Actions Workarounds
Residual Risks | Risk remaining after the application of the Risk Response
New Risks | Risks not previously identified and hence not in the Risk Register
Risk Register Updates | Contents of the WPIs Results of implemented risk responses Residual Risk New Risks Closing of risks no longer applicable Details of what happened when risks occurred
Notes: Agile, Waterfall

## Slide 12: Monitor & Control Risks Outputs … 2/2
Output | Details
Project Management Plan Updates | Updates resulting from approved Change Requests
OPA Updates | Updated with: Risks & Risk Responses (appropriate contents of Risk Register) Checklists
Notes: Agile, Waterfall

## Slide 13: Monitor & Control Risks – Tools & Techniques … 1/2
Tools & Techs | Details
Risk Reassessments | Regular reassessment of risks involving, or resulting in: Identification of new risks Additional/iterative qualitative & quantitative analysis of previously identified risks, and/or of new risks Further risk response planning of previously identified risks, and/or of new risks
Risk Audits | Performed at a frequency and in a format spelt out in the Risk Management Plan, with the purpose of: Assessing the overall effectiveness of risk management processes on the project Examining the effectiveness of risk responses in dealing with the identified risks and their root causes
Workarounds | Unplanned responses developed to deal with: the occurrence of unanticipated events or problems (unknown unknowns) on a project the risks that had been accepted because of unlikelihood of occurrence and/or minimal impact, but have occurred
Notes: Agile, Waterfall

## Slide 14: Monitor & Control Risks – Tools & Techniques … 2/2
Tools & Techs | Details
Reserve Analysis | Throughout execution of the project, some risks may occur with positive or negative impacts on budget or schedule contingency reserves Reserve analysis checks how much reserve remains and how much might be needed for the amount of risk remaining at any time in the project
Variance and Trend Analysis | Trends in the project’s execution reviewed using Earned Value Analysis, other methods of project variance and Trend Analysis
Meetings | Project risk management is be an agenda item at periodic status meetings Amount of time required for that item will vary, depending upon the risks that have been identified, their priority, and difficulty of response The more often risk management is practiced, the easier it becomes Frequent discussions about risk make it more likely that people will identify risks and opportunities
Notes: Agile, Waterfall

## Slide 15: Using Reserves and other Actions
Nature of the Risk Occurring
Risk is a part of the Risk Response Plan and budgeted with Contingency Reserve
Use of Reserves & other Actions
Use the Contingency Reserve set aside for the risk
Risk is a part of the Risk Response Plan but not budgeted with Contingency Reserve (i.e. the Risk was Accepted) or Risk is not part of the Risk Response Plan and, therefore, not budgeted with Contingency Reserve
Create a workaround (take corrective or preventive action, like Fast Tracking or Crashing if it is a problem with schedule), or Adjust the project to accommodate or make up for the impact of the risk including resulting changes, or Use Management Reserves if approved and released by the management of the performing organisation
Risk which was a part of the Risk Response Plan and was budgeted with Contingency Reserve, does not occur
Return the associated Contingency Reserve to the company Do not use the reserves to address other risks/issues on the project
Notes: Agile, Waterfall

## Slide 16: Using Reserves - Summary
Contingency Reserve used only to handle the impact of the specific risk it was set aside for
Reserves are not a free amount of time or cost that can be used at will by the Project Manager for any needs
Notes: Agile, Waterfall

## Slide 17: Monitor & Control New Risks (Unknown Unknowns)
Analyse and qualify the risk, going through the process of:
Qualitative risk analysis, followed by Quantitative risk analysis if required, depending on the EMV
Planning a Risk Response if EMV Med or High
Updating Risk Register
Situation 1: A new risk, i.e. a risk not listed in the Risk Register, is identified or discovered
Notes: Agile, Waterfall

## Slide 18: Monitor & Control New Risks (Unknown Unknowns)
Create a workaround
Look for any unexpected effects of the risk
Reevaluate the Identify Risk process
Update the Risk Register
Use Management Reserves if approved and released by the management of the performing organisation
Situation 2 : A new risk, i.e. a risk not listed in the Risk Register, has occurred
Notes: Agile, Waterfall

## Slide 19: Summary of Actions
Project Stage | Risk Identified or New | Has the Risk Occurred? | KU or UU | Major Actions
Planning/ Execution | Identified | No | KU | Monitor
Execution | Identified | Yes | KU | Respond as per plan Expend Contingency Res Update Risk Register
Execution | New | No | KU | Analyse the Risk Devise Response Allocate Contingency Res Update Risk Register
Execution | New | Yes | UU | Create a workaround Look for any unexpected effects Reevaluate the Identify Risk process Update Risk Register Use Management Reserves if approved and released by the management
Notes: Agile, Waterfall