<Project Name>

Cost Management Plan

<Insert Project Logo here>

<Month, Year>

Health and Human Services Agency, Office of Systems Integration

Revision History

| Revision History |  |  |  |
| --- | --- | --- | --- |
| Revision/WorkSite # | Date of Release | Owner | Summary of Changes |
| Initial Draft - | 06/30/2014 | A- PMO | Initial Release |
| Admin #4306 | 04/09/2015 | A - PMO | Incorporated Cost Management Plan tailoring guide information into this template. Assigned new WorkSite document number. |
| Admin #4306v2 | 01/29/2016 | A - PMO | Moved instructions to the top of each section; clarified information about references to the WBS; changed Procurement Center to Acquisition Center. |

Remove template revision history and insert Project Cost Management Plan revision history.

Approvals

| Name | Role | Date |
| --- | --- | --- |

Insert Project Approvals here.

Table of Contents

1.	Introduction	1

1.1	Purpose	1

1.2	Scope	1

1.3	References	2

1.3.1	Best Practices Website	2

1.3.2	Project Document Repository	2

1.3.3	Project Cost Database and Tool	3

1.4	Acronyms	3

1.5	Document Maintenance	3

2.	Participant Roles and Responsibilities	4

2.1	Office of Systems Integration (OSI)	4

2.1.1	OSI Director	4

2.1.2	OSI Chief Deputy Director	4

2.1.3	OSI Budget Office	4

2.1.4	OSI Accounting Office	4

2.1.5	OSI Acquisition Center	4

2.1.6	<Project Name> Project Director	4

2.1.7	<Project Name> Project Manager	5

2.1.8	<Project Name> Project Financial Manager	5

2.1.9	<Project Name> Project Financial Analyst(s)	5

2.1.10	<Project Name> Project Functional Manager(s)	5

2.2	Project Sponsor: < Organization Name >	5

2.2.1	Sponsor Financial Staff	5

2.2.2	Independent Verification and Validation (IV&V)	5

2.2.3	Independent Project Oversight Consultant (IPOC)	6

2.3	Federal Partner: < Name >	6

2.4	Contractors	6

2.5	Counties/Local Offices	6

3.	State Budget and Accounting Approach	6

3.1	Budget Planning	7

3.1.1	Project Concept Approval	7

3.1.2	Project Document (< FSR/SPR or APD>) Development	7

3.1.3	Project Estimation Techniques	8

3.1.4	Budget Change Proposal (BCP) / Supplementary Premise Information (SPI) Development	8

3.1.5	Budget Hearings and Questions	8

3.1.6	Responding to Budget Drills and Analyses	8

3.2	Acquisitions Tracking	9

3.2.1	Acquisitions for IT and Non-IT Goods	9

3.2.2	Acquisitions for Services	9

3.2.3	Personnel and Operations Expenditures	10

3.3	Expenditure Reports and Metrics	11

3.4	Changes to the Budget	11

3.5	Budget Reconciliation	12

3.5.1	Yearly Reconciliation of the Project’s Financial Books	12

3.5.2	Final Reconciliation the Project’s Financial Books	12

4.	Cost Management Approach	12

4.1	Cost Planning	13

4.1.1	Resource Planning	13

4.1.2	Cost Estimating	13

4.1.3	Establishing the Cost Baseline	14

4.2	Cost Tracking	14

4.2.1	Project Labor Hour Tracking	14

4.2.2	Consultant Costs and Labor Hours Tracking	14

4.2.3	Overall Cost Tracking	15

4.3	Cost Reporting and Metrics	15

4.4	Cost Control and Changes	15

4.4.1	Cost Variances	15

4.4.2	<Project Name> Executive Steering Committee	16

4.4.3	Cost Re-Planning	16

4.4.4	Cost Re-Baselining	16

4.5	Cost Closeout	16

4.5.1	Annual Cost Summary	16

4.5.2	Lessons Learned on Cost Management	16

5.	Reconciling the State Process to the Project Process	16

5.1	Budgeting and the Cost Baseline	17

5.2	Attendance Tracking and Time Reporting	17

5.3	Invoice Processing	17

5.4	Budget Changes and Cost Control	18

5.5	Reconciliation	18

6.	County Budget Management	18

7.	Project Cost Tool	19

7.1	Cost Tool Description	19

7.2	Using the Cost Tool	19

List of Tables

Table 1. Levels of Cost Management	1

List of Figures

Figure 1. Relationship of Budget/Accounting Processes to Cost Management Processes	2

# Introduction

## Purpose

The purpose of cost management is to ensure the project and its contractors will complete the project within budget. This Cost Management Plan identifies the processes and procedures used to manage costs throughout the project’s life cycle. The plan covers the cost management approach, expenditure tracking, variance analysis, oversight of contractor costs, and reconciliation between the State budget, accounting, and project management cost processes.

Additionally, the plan covers who is responsible for tracking expenditures, how variances will be addressed, and the cost tracking and reconciliation between the State and project management cost processes. This plan also describes the cost management tool that will be used.

## Scope

The scope encompasses the two levels of cost management for OSI projects. One level is the detailed accounting level of tracking budget, expenditures, salary and benefits, and overhead costs in accordance with the normal State of California budget process. The second level is the project management level of tracking costs against work performed in accordance with the OSI Best Practices standards derived from the Project Management Institute’s Project Management Body of Knowledge (PMBOK). Table 1 shows the differences in terminology that will be used in this plan when discussing the two different levels.

Table 1. Levels of Cost Management

| State Budgeting/Accounting | Project Cost Management |
| --- | --- |
| Budget Planning | Cost Planning |
| Accounting/Expenditure Tracking | Cost Tracking, Reporting and Metrics |
| Changes to the Budget | Cost Control and Changes |
| Reconciliation | Cost Closeout |

Adding to the complexity is the interaction of the budget and cost management processes with the contract management (acquisitions and invoicing) and time reporting (attendance and timesheet tracking) processes. All of these processes must interact and reconcile with each other.

In the figure below, the items toward the left hand side of the chart represent the state budget, accounting and contract management processes (lightly shaded bubbles). The items towards the right hand side of the chart represent the project cost management processes (white bubbles). The two processes must reconcile at the Initial Baseline, (after the Budget Act is signed) in the monthly attendance and time reporting processes, in the monthly expenditure and cost update processes, and whenever there is a re-plan and a new baseline established.

Tracking &

Change Control

Planning

Readiness

Hearings

Budget

Act

Amendments

Invoices

Initial Baseline

Change Control

Board

Re

-

Planning

Resource

Planning

Cost Tracking

Incorporate

Lessons

Learned

APD

FSR

BCC

Variance Analysis

(monthly)

Re

-

Baseline

Re

-

Baseline

Re

-

Baseline

Rev 1

Lessons

Learned &

Closeout

Analyze

Lessons

Learned

Archive

Cost Data

Unacceptable

Variance

Acceptable

Variance

Work

Authorizations

Encumbrances

Cost

Estimating

Cost

Budgeting

Time Reporting

(against WBS)

Reconciliation

And/Or

TAP

State/Fed

Approvals

BCP

POs/

Contracts

Master Project

Cost

(to the WBS Level)

Expenditures

Attendance

Tracking

Reconciliation

Figure 1. Relationship of Budget/Accounting Processes to Cost Management Processes

| Chart Color | Description |
| --- | --- |
| White | Project Cost Management |
| Yellow | Budget Baseline w/possible revisions |
| Pink | Funding and Expenditure Documentation |
| Gray | Contracts and Invoices |

## References

### Best Practices Website

For guidance on the Office of Systems Integration (OSI) budget/cost management methodology refer to the OSI Best Practices Website (BPWeb) (http://www.bestpractices.osi.ca.gov).

### Project Document Repository

Refer to the WorkSite repository located at < path and/or server > for all project-specific documentation. Indicate the location of the project’s hardcopy library.

### Project Cost Database and Tool

The current budget and expenditures are kept in a database/tool/spreadsheet located at < path and/or server>.  The Project uses the <tool name> for managing costs.

## Acronyms

List only acronyms applicable to this document.  If the list becomes longer than one page, move the acronym list to the Appendix.

| APD |  |  | Advance Planning Document (Federal funding document) |
| --- | --- | --- | --- |
| APDU |  |  | Advance Planning Document Update (Federal funding document) |
| BCC |  |  | Budget Change Concept |
| BCP |  |  | Budget Change Proposal (State funding document) |
| BPWeb |  |  | Best Practices Website (http://www.bestpractices.osi.ca.gov) |
| CALSTARS |  |  | California State Accounting and Reporting System |
| CM |  |  | Contract Manager |
| DGS |  |  | Department of General Services |
| DOF |  | Department of Finance |  |
| FSR |  | Feasibility Study Report (State funding document) |  |
| IPOC |  |  | Independent Project Oversight Consultant |
| IPOR |  |  | Independent Project Oversight Report |
| IV&V |  |  | Independent Verification and Validation |
| M&O |  |  | Maintenance and Operations |
| OSI |  |  | Office of Systems Integration |
| PCA |  |  | Program Cost Account |
| PIER | Post Implementation Evaluation Review |  |  |
| PMBOK |  | Project Management Body of Knowledge |  |
| SCO |  | State Controller’s Office |  |
| SOW | Statement of Work |  |  |
| SPI | Supplementary Premise Information (CDSS Projects only) |  |  |
| SPR TA |  |  | Special Project Report (State funding document) California Technology Agency |
| TAP |  |  | Task Accomplishment Plan |
| WBS |  |  | Work Breakdown Structure |

## Document Maintenance

This document will be reviewed annually and updated as needed, as the project proceeds through each phase of the system development life cycle. If the document is written in an older format, the document should be revised into the latest OSI template format at the next annual review.   This document contains a revision history log. When changes occur, the document’s revision history log will reflect an updated version number as well as the date, the owner making the change, and change description will be recorded in the revision history log of the document.

# Participant Roles and Responsibilities

This section describes the roles and responsibilities of the <Project Name> staff with regard to cost management. The following are the primary participants in the budget, accounting, and cost management processes from the project’s perspective. In some cases, one individual may perform multiple roles in the process.

## Office of Systems Integration (OSI)

The Office of Systems Integration (OSI) is responsible for coordinating the state budget and accounting processes with the projects in OSI and the appropriate control agencies.

### OSI Director

The OSI Director is responsible for approval of funding documents and representing <Project Name> at the budget hearings.

### OSI Chief Deputy Director

The OSI Chief Deputy Director is responsible for review of project funding documents, and for representing the projects at budget hearings, as necessary.

### OSI Budget Office

The OSI Budget Office is responsible for coordinating the review and submission of approval documents (e.g., Feasibility Study Reports (FSRs) and Advance Planning Document (APDs), Budget Change Concepts (BCCs), and Budget Change Proposals (BCPs)) to the appropriate state control agencies for all OSI projects. The Budget Office coordinates responses to questions from the control agencies and, creates and distributes the Governor’s Budget. They are the single point of contact for state communications (Control Agencies, Project Sponsors, and other State Agencies). The OSI Budget Office also coordinates the development of the department’s travel budget which includes estimates for project travel.

### OSI Accounting Office

The Accounting Office is responsible for coordinating the accounting, customer billing, invoice approval processes, travel advances, and travel claims for all projects in OSI. The Accounting Office works with the OSI Budget Office to reconcile the budget to the expenditures.

### OSI Acquisition Center

The OSI Acquisition Center is responsible for coordinating the acquisition of IT and Non-IT goods and services on behalf of the project.

### <Project Name> Project Director

The Project Director is responsible for approval of the Project Cost Management Plan and is ultimately responsible for the allocation and expenditure of the project budget.

### <Project Name> Project Manager

The Project Manager is responsible for managing and reviewing project costs from a project management perspective to ensure appropriate progress is being made for the funds being expended. The Project Manager works with the financial staff to reconcile the cost management data to the current accounting data.

### <Project Name> Project Financial Manager

The Financial Manager is responsible for leading the cost management effort, sponsoring cost budgeting and tracking activities, facilitating communication on fiscal status, and ensuring the project cost tool is maintained and supporting documentation is maintained. The Financial Manager is responsible for providing the Project Manager with recommendations and status on the project budget and expenditures. This role must be performed by a state employee. If the Project Manager is a state employee they may assume this role.

### <Project Name> Project Financial Analyst(s)

The Financial Analyst(s) are responsible for coordinating and developing project funding and approval documents and expenditure tracking and reconciliation in accordance with state processes. The analysts also work with the Financial Manager to reconcile the cost management and accounting data.

### <Project Name> Project Functional Manager(s)

The Functional Manager(s) are responsible for identifying funding needs and for assisting with the tracking of expenditures, including tracking of staff effort and costs.

## Project Sponsor: < Organization Name >

Section 2.2 should be updated to reflect the name of the sponsor organization. IV&V/IPOC may be removed if the project is not required to have this function.

### Sponsor Financial Staff

The sponsor’s financial staff works with the project financial staff to develop the sponsor’s budget in coordination with the project’s budget. The sponsor financial staff is also responsible for authorizing payment for project services.

### Independent Verification and Validation (IV&V)

Independent Verification and Validation (IV&V) provides an independent determination of whether development products satisfy the intended use and the user needs when operated in the environment for which they are intended (verification), and whether the products satisfy the specified requirements of the project (validation).

### Independent Project Oversight Consultant (IPOC)

Independent Project Oversight Consultant (IPOC) provide an independent review of the project management of a project to ensure approved project plans and sound management practices are used to minimize risk. The IPOC submits a status report to the California Technology Agency (TA)  monthly, or as required that includes a summary of the project’s current budget status based on information from the project financial staff.

## Federal Partner: < Name >

Section 2.3 should be updated to reflect the name of the federal partner, if applicable. Add any additional information regarding federal participation, reporting or required approvals, as appropriate.

The project’s federal partner is responsible for review and approval of project funding documents.

## Contractors

If the project has a prime contractor, indicate how the prime participates in the project’s budgeting, including coordination of planned costs for the next fiscal year (particularly during M&O) and reporting of cost data for inclusion in project cost management processes.

The Contractor is responsible for reporting appropriate costs to the project and to their efforts as described in their contract. The contractor is responsible for managing costs internal to their activities. The contractor should report their costs in their monthly status reports and raise potential or actual cost variances or problems to the project team at appropriate status meetings.

## Counties/Local Offices

If the project is reimbursing counties/local offices for implementation or other development costs, this section describes the primary responsibilities and which areas/groups within the counties/local offices participate in the funding requests and tracking.

The counties/local offices submit requests for reimbursement of implementation costs and assist with expenditure tracking and reconciliation.

# State Budget and Accounting Approach

The following sections summarize the project’s involvement in the state budget and accounting processes.

- Step 1 - Budget Planning

- Step 2 - Acquisitions Tracking

- Step 3 - Acquisitions Reports and Metrics

- Step 4 - Changes to the Budget

- Step 5 - Budget Reconciliation

- The section introduction should remain untouched.

The following sections should describe the high-level processes and interaction of participants. Refer to separate more detailed processes/procedures, as necessary.

## Budget Planning

This section is intended to be written generically enough to describe both the Fall and Spring Budget Processes.

The state budget is established on a yearly basis, the funding for the project is only secured for one year at a time (although requests for future year funding may be reviewed, but not guaranteed).

### Project Concept Approval

Describe how the initial project approval and approximate budget was established/received and what might cause a new concept (e.g., welfare reform, new M&O initiatives, etc.). Discuss where the funding is coming from: grants, general fund, bonds, federal funding, etc. and any restrictions on the money that was/may be received.

Describe who is responsible for the development of any new BCCs. If appropriate, discuss the annual Interagency Agreement updates and how that affects the budget and new concepts. Describe the organizational coordination required to establish the BCC and, if companion BCCs must be used (e.g., one BCC for OSI and one BCC for the Sponsor which are dependent on each other), who is responsible for what types of activities, etc.

When appropriate, new project concepts or staffing requests are proposed through the development of a Budget Change Concept (BCC) and high-level cost estimates (refer to Section 4.1 for more on developing cost estimates). The project financial staff prepares the BCCs in accordance with instructions provided by the OSI Budget Office. The OSI Budget Office coordinates the review of BCCs with the OSI Director and Agency.

### Project Document (< FSR/SPR or APD>) Development

Based on the specific project, describe the project document development process.

Federal Funded Projects: utilize the APD documentation process. Indicate if a separate FSR and APD are submitted or if the APD is used in lieu of the FSR/SPR. Indicate how the APD format was customized to meet state needs. Annual updates to the APD are called APDU.

If the BCC is approved, the project financial staff create a project document (FSR/SPR) which requests approval for the project from the state control agencies <and, if appropriate, the federal partner>. In addition, the project financial staff reviews the project’s current expenditures and identifies any adjustments which may need to be made as a result of changes to the Interagency Agreement or Memoranda of Understanding, or as a result of project progress.

The project financial staff coordinates approvals from OSI, <and, if appropriate, the federal partner>. The OSI Budget Office coordinates approvals from the state control agencies.

### Project Estimation Techniques

Describe how the budget was derived and what historical data or industry materials were used as the basis of estimates. Describe the process used to validate estimates and the supporting materials that were used. Indicate if any independent review of the estimates was/is performed.

TA requires supporting data for estimates to be retained by cost category. Indicate where this information is stored.

The original project budget estimates were developed using < xxxxx >, and validated using < xxxxx >. Estimates for new concepts use the same techniques.

### Budget Change Proposal (BCP) / Supplementary Premise Information (SPI) Development

CDSS Projects Only:  utilize the SPI (in lieu of BCP) document.

The <Project Name> financial staff develops a Budget Change Proposal (BCP) which requests funding for the concept or initiative described in the approval document. The OSI Budget Office coordinates the review of the BCP with the project sponsors, and submits the BCP to the Control Agencies.

### Budget Hearings and Questions

Discuss who will attend the budget hearings and prepare supporting materials for the hearing.

Discuss how questions or comments from the feds are addressed, if appropriate.

Discuss how the project manages the encumbrances at the project, what tool is used (or spreadsheet name/location), and how the projects encumbrances initially are coordinated with OSI Accounting.

The Budget Office coordinates any questions regarding the budget proposals, and assists with the budget hearings. Once the Budget Act is signed, the project financial staff reviews the final Budget Act for any change to the requested amounts.

The Project Manager and Project Financial staff reviews the budget against the cost estimates, and adjust the cost baseline, if necessary.

### Responding to Budget Drills and Analyses

If the project responds to budget drills, it may be useful to include this section.

Discuss the approach to budget drills: who coordinates the response, who reviews the information, who must approve the response, and how responses are coordinated with the sponsor (and when coordination is appropriate). Also discuss other budget analyses and reviews that may be required to support budget reductions, changes in project approach or scope, changes in rates, analysis of proposed contractor work orders or amendments, etc. This section should discuss only the analysis of proposed changes. Refer to the Changing the Project Budget section (below) to describe the specific processes to enact a change.

## Acquisitions Tracking

Discuss other types of expenditures, as appropriate, including sponsor bills and county/local office claims and approvals.

After the Budget Act is signed, the project may begin expending the funds for the fiscal year. Typically the expenditures include acquisitions for products and services, personnel costs, and operations costs. The project works with OSI’s Acquisitions Center and OSI’s Accounting Office, respectively, to procure and pay for the necessary items.

### Acquisitions for IT and Non-IT Goods

Discuss how any equipment purchases are handled, focusing on responsibilities of the different organizations involved. Focus on project specific items, not things described in other plans/state manuals or items provided by the prime contractor. Usually the Administrative and IT staff coordinate these types of acquisitions.

Discuss:

- Who does the product research (e.g., IT, functional manager, requestor, etc.)

- Who has approval authority for the equipment purchase

- Who works with OSI Acquisition Center to conduct the purchase

- Who tests/verifies the equipment

- Who approves the invoice

- Who tracks licenses/on-going subscriptions/warranties and their costs and expirations

- Who pays for the equipment (sponsor, project, OSI)

- If appropriate, describe specific coding or cost allocations

- How are the equipment costs tracked/depreciated and who is responsible for tracking depreciation (project vs. OSI)

The project Administrative and IT staff work with the OSI Acquisition Center to identify and document specific requirements for equipment. The OSI Acquisition Center solicits vendors to obtain the desired equipment at the best price from the various DGS supplier lists. The project notifies OSI Acquisition Center and the Accounting Office when the equipment is received and if it meets the stated requirements. Upon approval by the project office, the Accounting Office coordinates payment to the vendor.

### Acquisitions for Services

Discuss briefly how project contracts are procured and how contract expenditures are handled. If contract withholds, liquidated damages, etc. are used, describe the processes to track and invoke these – refer to the appropriate contract management processes for additional information. Discuss any coordination performed with the Acquisitions and Contract Manager for tracking deliverables, services, invoices, withholds, and liquidated damages.

The project Procurement and Contract Management staff work with the OSI Acquisition Center to identify and document specific requirements for the desired services. The OSI Acquisition Center solicits offers/proposals from qualified bidders, coordinates questions/answers to the requirements and oversees with the review and evaluation of offers/proposals. The project works with OSI Acquisition Center to conduct interviews, if appropriate, and selects the winning bidder. The OSI Acquisition Center creates and issues the contract documents.

Depending on the contract amount, either the OSI Director or Agency Secretary is the final approver of consultant contracts.  The Project Manager is the approver of the Task Accomplishment Plans (TAPs), and consultant invoices. The Project Functional Manager tracks the contractor day-to-day tasking, performs review of consultant work products, and assists with invoice review and approvals.

The project has three to five working days to respond to contractor invoices, in accordance with Government Code Section 927 (California Prompt Payment Act). The contractor submits official invoices to OSI Accounting. OSI Accounting Office sends the Project a copy of the invoice for review and approval. The project financial staff reviews the invoice against the deliverable tracking log and the attached timesheets to validate the information. The Project Manager reviews the invoice and Project Financial Analyst’s comments and recommendations, and makes the final decision to approve or reject an invoice. The approval or rejection notice is faxed to the OSI Accounting Office who coordinates payment with the State Controllers Office.  Refer also to the Contract Management Plan for more on invoice processing and review.

### Personnel and Operations Expenditures

Discuss how staff costs are tracked including the accounting of salary and benefits. Also discuss tracking of operations costs and overhead.

- What tool is used for tracking expenditures

- Where does the expenditure data come from

- How often is the tool updated

- What expenditure reports are generated or received by the project

- Who submits these, to where, and when

- What happens if there is a discrepancy between received reports and project info? How is the problem researched and resolved?

Discuss where actual expenditure data comes from, how the expenditures are validated for accuracy, and how they are coded and posted to the project expenditure tracking tools.

Discuss if there is any coordination with the sponsor regarding monthly or quarterly expenditures. Discuss any coordination with county/local offices for their expenditures.

The project tracks all contract, personnel and operations expenditures in <Insert Expenditure Tool>. At the close of each month, the project receives expenditure reports from the Accounting Office showing the funds that were expended according to California State Accounting and Reporting System (CALSTARS). The project reviews and validates the expenditures match with their records of expenditure approvals and works with the Accounting Office to resolve any discrepancies.

## Expenditure Reports and Metrics

Discuss any accounting/expenditure reports, contractual financial summaries, or staff salary/benefits reports generated by the project that are used to track and monitor costs. Discuss how the reports and metrics are used and how often they are analyzed/reviewed for correctness.

If the project is participating in county/local office costs, add a section to address the specific reports that are generated for and received from the counties/local offices.

Discuss how the project provides data to the IPOC in support of the TA Independent Project Oversight Report (IPOR).  If the project does not have an IPOC, indicate who submits this report.

Expenditure reports are generated for project use in validation and tracking of expenditures against the budget. The OSI Accounting Office is responsible for sending appropriate reports to the sponsor, as requested.

## Changes to the Budget

Describe the process used to review and approve a project budget change. This section should discuss the typical reasons and types of changes such as moving dollars between fiscal years, addressing changes in project approach (usually requiring an SPR), addressing minor changes such as coding/category changes, etc. Describe the approvals required for each type of change and the archiving of the prior cost baseline/budget and establishment of the new cost baseline/budget. Discuss supporting materials that must be kept and/or generated to support the approval process.

Discuss required approvals include a reference to the Budget Development section of the plan for the procedures to enact a change, as appropriate. Include a reference to the contract management processes for changing a contract dollar amount.

If the project budget needs to be adjusted, the Project Manager determines if an approval document (e.g., APD or FSR) and/or BCP/SPI needs to be written to address the change. If a change is deemed necessary, the financial staff develops the approval document and/or BCP/SPI. The OSI Budget Office coordinates the submission and approvals of the document(s) in accordance with the state budget cycle.

Once the change is approved and included in the appropriate fiscal year budget, the Project Manager works with the financial analyst to re-baseline the cost data and estimates.

## Budget Reconciliation

Describe any specific procedures or actions taken to reconcile, such as hiring an independent auditor or coordinating with other projects to reconcile each other’s books independently.  Describe any reconciliation of county/local office expenditures and any coordination with the sponsor. Streamlined projects may combine these sections.

### Yearly Reconciliation of the Project’s Financial Books

Discuss how end-of-fiscal-year reconciliations are performed and what reports are generated. Indicate how discrepancies are addressed and where the fiscal year information is stored. Indicate if any outside auditors are used to validate the information.

The Project Financial Manager is responsible for coordinating and performing the reconciliation of the actual expenditures to the approved budget, and working with the OSI Accounting Office to address any issues. Project Financial staff performs an internal reconciliation annually in preparation for the official reconciliation with the OSI Accounting Office (typically in July-August). Reconciliation includes a comparison of actual to planned expenditures as well as actual expenditures against the approved budget.

### Final Reconciliation the Project’s Financial Books

This section may be left as TBD for the first iteration of the plan, but should be completed, at the latest, by the time the solicitation for a prime contractor is initiated, in case the procurement and project are cancelled.

Discuss if there is a final audit of the project’s books (internally, by OSI, by the sponsor, or by an independent contractor), how the project performs disencumbrances, and any final accounting reports that may be generated for OSI, the sponsor, the control agencies or the feds.

Discuss the financial reports that are included in the Post Implementation Evaluation Report (PIER).

Discuss the final archiving of the project’s budget and accounting papers and any financial tools.

# Cost Management Approach

This section describes cost management from the PMBOK perspective. Projects have some leeway in the amount of rigor applied to this area, but must establish a cost baseline and perform some comparison of actual costs to the cost baseline. Changes to the cost baseline must be documented.

The following section summarizes the project management processes for managing costs on the project as tailored from the PMBOK.

- Step 1 - Cost Planning

- Step 2 - Cost Tracking

- Step 3 - Cost Reporting and Metrics

- Step 4 - Cost Control and Changes

- Step 5 - Cost Closeout

Communication is a key part of the cost management process and occurs at every step of the process among the project team, project stakeholders and consultant team.

## Cost Planning

### Resource Planning

- Discuss the inputs used to establish the resource estimates. Indicate where the resources estimates and supporting information is located/stored.

Cost estimation begins upon completion of the project WBS. Resource skills are determined based on the needs of the project and the products being produced. The project uses and tailors the personnel resource information from the <Project Name> Staff Management Plan and <Project Name> Responsibility Assignment Matrix for determining needed resource skills.

### Cost Estimating

Describe any specific cost methods used to validate or confirm the costs estimates for the various tasks. Refer to PMBOK, regarding Cost Estimating for more info. Discuss correlation of cost allocations to the project budget (chart of accounts) or put this information in Section 5 on ‘Reconciling the Accounting/PM Perspectives’.

Hour estimates are created for each WBS item. The necessary skill sets and staff labor categories are identified for each WBS element. Approximate costs are estimated based on the anticipated classification of staff assigned to the work.

The anticipated costs are allocated to each WBS item and totaled. Resource/labor costs are allocated by resource category and total.

The estimates are then used to request funding or funding adjustments for the project (refer to Section 3.1 on state budget requests). Risks associated with the cost estimates are documented and included in the risk management database.

### Establishing the Cost Baseline

Describe how the cost baseline is set and what approvals are required. Indicate if the baseline is set manually (by saving a “clean” copy to fall back to, or a new version in WorkSite) or what specific tool feature is used to establish the cost baseline.

Once the Budget Act is signed, the Project Manager and Project Financial Analyst review the cost allocation (of funding per WBS item) against the approved budget, and adjust the allocations, if necessary, to reflect the approved funding for the year. Upon approval by the Project Manager, the cost allocations are baselined. For more information on the current cost allocations to WBS items, refer to the project’s Master Project Plan.

## Cost Tracking

Actual hours expended are recorded and validated against attendance records and contractor monthly reports. The hours are converted to costs for tracking the cost of current progress to determine if the project is staying within and expected to complete within budget.

### Project Labor Hour Tracking

Indicate how project (state) staff track their hours against the project’s schedule and assigned work from the WBS. Indicate which WBS level work is tracked against. Indicate how labor hours are translated to costs.

Describe how staff submits timesheets and/or how they use the labor hour tracking worksheet to record hours against the WBS items:

- Where is the data located

- Who is responsible for entering the data (each individual)?

- What type of data is recorded

- Who reviews/validates the data has been entered

- Who ensures the sheets are setup and ready for use

### Consultant Costs and Labor Hours Tracking

Discuss how consultant costs are tracked and how their labor hours are rolled up into the overall tracking of labor hours against the project WBS items.  Indicate which WBS level the consultant items are included in.

- Consultants are required to submit monthly timesheets showing labor hours worked by SOW tasks. Each SOW task is mapped to a specific WBS item by the Project Functional Manager.

### Overall Cost Tracking

Discuss how the overall cost of the project (e.g., overhead, facility, benefits, etc.) is tracked. Indicate if just staff and contract costs are considered project costs.

FYI:  The Technology Agency requires

- Actual costs to be recorded by cost category

- Comparison of actual costs to budgeted costs on a regular basis

- Supporting data for actual costs to be retained

Overall costs are compared to the budgeted project costs on a monthly basis by the Project Financial Manager. The overall costs are comprised of the actual labor hours (state and consultant) and project expenditures for the month (received from the project financial staff). Variances are reviewed and analyzed to determine the cause and possible mitigations or corrections.

## Cost Reporting and Metrics

To assist with tracking actual costs against the baseline, the following charts/reports are used. The charts are available in the <Insert reporting tool such as CalSTARS, Excel, etc>, and are updated as described below.

- Spending Plan (by fiscal year) – a run chart showing the actual costs against the baseline by month for the fiscal year and the cumulative total to date for the fiscal year.

- Cost by WBS Item - a bar chart showing the labor costs by Level 1 WBS items by month for the fiscal year and the cumulative total to date for the fiscal year.

- Cost Variance by WBS Item – a bar chart showing the actual costs against the baseline to date.

- Labor Hours by WBS’ Deliverable Item – a bar chart showing the amount of effort expended towards the Level 1 WBS items by month for the fiscal year and the cumulative total (to date) for the fiscal year.

The Project Manager and Project Financial Manager will compile the reports and submit the reports to the Project Director and if needed, Project Executive Steering committee consistent with the Communication Management Plan reporting requirements.

## Cost Control and Changes

### Cost Variances

For variances against the baseline of more than ten percent at the Level 1 WBS deliverable items, the rational for the variance is documented in the associated report and discussed at the management staff meeting. If the variance does not affect the overall project cost baseline, no other actions are required.

### <Project Name> Executive Steering Committee

If the overall cost baseline is affected, the variance is documented and reported to the Project Director and, subsequently, the <Project Name> Executive Steering Committee. The Project Director and the <Project Name> Executive Steering Committee review the rationale and discuss the options and mitigations for dealing with the variance, and determine if a re-plan, is necessary.  If so, the issue and recommendation is presented to the <Project Name> Executive Committee for review and approval. The <Project Name> Executive Steering Committee makes the policy decision to amend the projects’ cost, scope, schedule, or quality.

### Cost Re-Planning

If a re-plan is deemed necessary by the <Project Name> Executive Steering Committee, the project prepares documents to address the re-plan. The state funding documents are included in the next budget cycle and are subject to the normal review and approval processes.

### Cost Re-Baselining

Once the re-plan is approved, the Project Manager works with the Project Financial Manager to re-baseline the cost data and estimates based on the approved funding. The project works with the OSI Accounting Office to adjust their encumbrances and accounting tools to reflect the re-plan.

## Cost Closeout

At the end of the project, the cost historical information is completed by the Project Financial Manager, reviewed by the Project Manager, submitted to OSI Budget Office for review and then forwarded to TA.

### Annual Cost Summary

At the end of the fiscal year, the Project Manager and Project Financial Manager summarize the actual hours and costs expended against the baseline for the fiscal year. The annual summary is archived for historical purposes.

### Lessons Learned on Cost Management

Lessons learned related to costs and cost estimation are used in the development of the subsequent fiscal year’s cost baseline.

# Reconciling the State Process to the Project Process

As discussed previously, the State budgeting and accounting processes operate separately from the project cost management processes, though they are related. This section discusses the relationships and where these processes must interact and synchronize.

## Budgeting and the Cost Baseline

Once the project management baseline (or revised) budgets have been finalized, the <Project Name> team must determine if future Annual budget demands require adjustments to OSI’s base spending authority. If additional spending authority is required, a BCP must be prepared. If additional spending authority is not required, the project adjusts the cost baseline to reflect the actual approved budget for the fiscal year.

## Attendance Tracking and Time Reporting

- Specifically discuss how the attendance tracking and time reporting processes relate and reconcile to each other as part of the cost tracking process. Who is responsible for the coordination and reconciling? What happens when there is a discrepancy? Do not repeat information that has been discussed in prior sections, but summarize or refer to the appropriate section, as applicable.

State staff submits monthly attendance reports at the end of the month. These reports are used by OSI Accounting to bill the project for state staff salary and benefits.

## Invoice Processing

Invoices must clearly identify the products (deliverables) and service period for which the invoice is requesting payment. The prime contractor and nonprime contractors must adhere to specific invoice requirements set forth in the contract.   All contractor invoices are sent directly to OSI’s Accounting Office. This office logs the invoice, begins the processing cycle and coordinates the actual payment with the SCO once all the appropriate approvals have been received. The Accounting Office retains the original invoice.

The California Prompt Payment Act (Government Code Section 927, et seq.) established a 45-day turnaround time for payment of undisputed invoices. The 45-day period begins when the invoice is received at OSI and ends when the check is sent from the SCO to the contractor. OSI has only 30 days to process the invoice and route it to SCO for payment. Within these 30 days, the <Project Name> project has only five business days to process the invoice and fax the response back to the Accounting Office. (Projects that exceed their allotted five-business day review will incur the late penalty fees should payment not be issued within the 45-day time frame allowed.) The SCO has 15 days to process the check request.

After logging the invoice, the Accounting Office routes a copy of the invoice to the project for review and approval. Upon receipt of the invoice at the project, it is routed to the Project Financial Analyst who verifies that the personnel, classifications, and rates in the invoice correspond to the terms in the contract. The Project Financial Analyst also verifies the PCA codes are correct, if applicable. If travel expenses have been included, the Financial Analyst verifies the contractor is authorized to bill for travel expenses, the necessary receipts are present and under no circumstances will claim exceed the state’s allowable travel rates. The invoice is then routed to the Contract Manager (CM).

If the invoice is from a nonprime contractor, the CM will verify that all deliverables for that billing month have been received and approved.  If the deliverable(s) has not been approved, the invoice will not be approved for payment. If the invoice is from the prime contractor, the CM will verify that all issues relating to withholds and liquidated damages have been reviewed and addressed.

If all the information is acceptable, the invoice is passed to the Project Manager for final review and signature. If the Project Manager approves the invoice, the approved paperwork is sent back to the OSI Accounting Unit, who will then send a payment request to the SCO.

If some or all of the deliverables or services were unacceptable, the CM notifies the Accounting Office that the invoice is unacceptable and indicates why the invoice is being disputed. The OSI Accounting Office sends a notice of invoice dispute (Form 209) to the contractor indicating why the invoice cannot be paid and what must be done or corrected. The 45-day processing clock stops when the Accounting Office sends the notice of invoice dispute to the contractor. After addressing the problems, the contractor re-submits an invoice for payment to OSI’s Accounting Office and the processing clock is reset and restarted.

## Budget Changes and Cost Control

Changes to the annual OSI budget and spending plan may be required by the project to support a re-plan. The Project Manager and Project Financial Manager will partner to ensure that the State budget and the project management baseline estimates match. Corrective actions or change requests will follow the appropriate project change or budget change processes.

## Reconciliation

At the end of the fiscal year and at the end of the project, a reconciliation must be completed using both the project cost management and project accounting processes. The expenditures must reconcile to the approved budget and also to the OSI accounting system.

# County Budget Management

- If the project is reimbursing counties/local offices for costs, this section is mandatory.

- If the project involves payment of county costs or reimbursements to counties or local offices, this section is considered mandatory. For projects not dealing with county/local office funding, this section should be marked as not applicable.

Complete this section by discussing budget planning, cost allocations, spending authorities, expenditure approvals, expenditure tracking and receipts, and reconciliation.

Additional procedures for the county/local office should be developed and referenced in this plan which describes how to request state funding for county activities; how the request is reviewed, approved and included in the project/sponsor budget; and how the actual funding is provided/reimbursed to the county.

# Project Cost Tool

If the project is using a database tool (MS Access) or other software package (other than MS Excel) for tracking costs and budget information, this section should be included.

If the project only uses MS Excel spreadsheets, then indicate this and list the names and WorkSite numbers (or location) of the spreadsheets and their purpose.

## Cost Tool Description

- Identify and discuss the primary features of the tool/database. Indicate the manufacturer/developer and who is responsible for maintenance and upgrades of the tool. Indicate the platform and version of the tool. Indicate why the tool was selected. Indicate any interfaces or dependencies to other tools.

Discuss security and user accounts. Indicate if the data is considered sensitive and if there are any special approvals for data updates or major changes. Indicate if there was any customization done for the project that is different from the “standard” version.

Indicate where the user manual and/or training materials are located or accessed.

## Using the Cost Tool

Discuss the specifics about using a tool including the primary features and reports used by the project. Refer to the specific procedures available and any tips/tricks for using the tool. If appropriate, attach supporting information in an appendix or refer to where it may be found.

APPENDICES

Appendices may be added to provide additional specific information on the projects budget/cost processes. Typical appendices include a listing of the specific pseudo codes and charge codes to be used to report costs to the sponsor; the specific reports (or examples) which are used to communicate to the sponsor and/or department; and specific posting or claiming instructions and cost assumptions for historical reference.

The project has chosen to tailor the PMBOK guidance on Cost as follows:  The planning processes of Cost (Resource Planning, Cost Estimating, and Cost Budgeting) have been consolidated into a section called Cost Planning.  The PMBOK Controlling processes (Cost Control) have been expanded into four sections called Cost Tracking, Cost Reporting and Metrics, Cost Control and Changes, and Cost Closeout.

Refer to the project Master Project Plan to obtain the project’s WBS and refer to the project Schedule Management Plan for a description of how the WBS was established.