## Slide 1
MASTERS IN PROJECT MANAGEMENT
PROJECT RISK
MANAGEMENT
Class: MS(PM)-2(A,B&C)

## Slide 2
PE, PMP, PgMP, PME, MCT, PRINCE2 Practitioner.
PE, PMP, PgMP, PME, MCT, PRINCE2 Practitioner.
Instructor
Suhail Iqbal
Notes: Custom animation effects: horizontal scrolling text
(Basic)
To reproduce the text effects on this slide, do the following:
On the Home tab, in the Slides group, click Layout, and then click Blank.
On the Insert tab, in the Text group, click Text Box, and then on the slide, drag to draw the text box.
Enter text in the text box. (Note: You may want to add a bullet point at the end of your text, as in the example above. On the Insert tab, in the Text group, click Symbol. In the Symbol dialog box, in the Font list, select (normal text). In the Subset list, select General Punctuation. In the Character Code box, enter 2022 to select BULLET, and then click Insert.)
Select the text. On the Home tab, in the Font group, do the following:
  In the Font list, select Gill Sans MT.
  In the Font Size list, select 36.
  Click Bold.
  Click the arrow next to Font Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
On the Home tab, in the Paragraph group, click Align Text Left to align the text left in the text box. (Note: If the text wraps to more than one line, drag the adjustment handles on the text box to widen it until the text fits on one line.)
Drag the text box to the left of the lower left edge of the slide. (Note: To see beyond the edges of the slide, on the View tab, click Zoom, and then in the Zoom dialog box, in the Percent box, enter 40%.)
To reproduce the animation effects on this slide, do the following:
On the Animations tab, in the Animations group, click Custom Animation.
On the slide, select the text box. In the Custom Animation task pane, do the following:
  Click Add Effect, point to Entrance, and then click More Effects. In the Add Entrance Effect dialog box, under Basic, click Fly In.
  Select the animation effect (fly-in effect for the text box). Click the arrow to the right of the select effect, and then click Effect Options. In the Fly In dialog box, do the following:
    On the Effect tab, in the Direction list, select From Right.
    On the Timing tab, do the following:
      In the Start list, select With Previous.
      In the Speed box, enter 16 seconds.
      In the Repeat list, select Until End of Slide.
On the slide, select the text box. On the Home tab, in the Clipboard group, click the arrow under Paste, and then click Duplicate.
In the Custom Animation task pane, select the second animation effect (fly-in effect for the second text box). Click the arrow to the right of the selected effect, and then click Timing. In the Fly In dialog box, on the Timing tab, in the Delay box, enter 8. (Note: You may need to adjust the delay time if the length of your text is different than the example above.)
On the slide, drag the second text box on top of the first text box.
On the Home tab, in the Editing group, click Select, and then click Selection Pane.
In the Selection and Visibility pane, press and hold CTRL, and then select both text boxes. On the Home tab, in the Drawing group, click Arrange, point to Align, and then do the following:
  Click Align Selected Objects.
  Click Align Middle.
  Click Align Center.
To reproduce the background effects on this slide, do the following:
Right-click the slide background area, and then click Format Background. In the Format Background dialog box, click Fill in the left pane, and then select Picture or texture fill in the Fill pane. Under Insert from, click File. In the Insert Picture dialog box, select a picture, and then click Insert.
On the Home tab, in the Drawing group, click Shapes, and then under Rectangles click Rectangle (first option from the left). On the slide, drag to draw a rectangle.
Select the rectangle. Under Drawing Tools, on the Format tab, in the Size group, do the following:
  In the Shape Height box, enter 7.5”.
  In the Shape Width box, enter 1”.
Under Drawing Tools, on the Format tab, in the Shape Styles group, click the arrow next to Shape Outline, and then click No Outline.
On the Home Tab, in the Drawing group, click the arrow next to Shape Fill, point to Gradient, and then click More Gradients. In the Format Shape dialog box, click Fill in the left pane, select Gradient fill in the Fill pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Right (first row, fourth option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click Black, Text 1 (first row, second option from the left).
    In the Transparency box, enter 0%.
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click Black, Text 1, (first row, second option from the left).
    In the Transparency box, enter 100%.
On the slide, select the rectangle. On the Home tab, in the Drawing group, click Arrange, point to Align, and then do the following:
  Click Align to Slide.
  Click Align Left.
  Click Align Middle.
Select the rectangle. On the Home tab, in the Clipboard group, click the arrow under Paste, and then click Duplicate.
Select the duplicate rectangle. On the Home Tab, in the Drawing group, click the arrow next to Shape Fill, point to Gradient, and then click Linear Left (second row, third option from the left).
With the duplicate rectangle still selected, on the Home tab, in the Drawing group, click Arrange, point to Align, and then do the following:
  Click Align to Slide.
  Click Align Right.
  Click Align Middle.

## Slide 3
SYLLABUS
Unit | Content | Learning Objectives
10. Planning Risk Responses | Purpose and Objective of the Plan Risk Responses Process Critical Success Factors for the Plan Risk Responses Process Risk Response Strategies Tools and Techniques Documenting the Results | Understanding the Project Environment and various types of Risk Responses which can be planned for positive as well as negative risks (threats and opportunities)

## Slide 4
UNIT 10
PLAN RISK RESPONSES
PROJECT RISK
MANAGEMENT
Class: MS(PM)-2 (A,B&C)
UNIT 10

## Slide 5
PLAN RISK RESPONSES
LEARNING OBJECTIVE
Understanding the Project Environment and various types of Risk Responses which can be planned for positive as well as negative risks (threats and opportunities).
UNIT 10

## Slide 6
What is the Project Environment?
Response Options
System Standards
Insurance
Response Planning
Purpose and Objective of the Plan Risk Responses Process
Critical Success Factors for the Plan Risk Responses Process
Contingency Reserves
Risk and Safety
Principal Determinants
Managing by Stakeholder Groupings and categories
The Means and Value of Exercising Positive Influence
Risks in Contracts
Tools & Techniques for the Plan Risk Responses Process
Documenting the Results of the Plan Risk Responses Process
UNIT 10
PLAN RISK RESPONSES
CONTENT

## Slide 7
PLAN RISK RESPONSES
Purpose and Objectives
UNIT 8

## Slide 8
The Plan Risk Responses process determines effective response actions that are appropriate to the priority of the individual risks and to the overall project risk.
It takes into account the stakeholders’ risk attitudes and the conventions specified in the Risk Management Plan, in addition to any constraints and assumptions that were determined when the risks were identified and analyzed.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Introduction

## Slide 9
The objective of the Plan Risk Responses process is to determine the set of actions which most enhance the chances of project success while complying with applicable organizational and project constraints.
Once risks have been identified, analyzed and prioritized, plans should be developed for addressing every risk the project team considers to be sufficiently important, either because of the threat it poses to the project objectives or the opportunity it offers.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Purpose and Objectives

## Slide 10
The planning entails agreeing upon the actions to be taken and the potential changes to budget, schedule, resources, and scope which these actions might cause.
Contingent risk response actions need to be executed at the optimum time. For this reason, the response specification for each such risk should include a description of any corresponding trigger conditions.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Contingent Risk Responses

## Slide 11
The responsibility for monitoring the project conditions and implementing the corresponding actions should be clearly assigned.
Every risk should have been allocated to a risk owner as part of the Identify Risks process, and each of the corresponding risk responses should now be assigned to a specific risk action owner.
The risk owner is responsible for ensuring that the risk response is effective and for planning additional risk responses if required, whereas the risk action owner is responsible for ensuring that the agreed-upon risk responses are carried out as planned, in a timely manner.
The role of the risk owner and that of the risk action owner may be assigned to a single person.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Risk Responsibilities

## Slide 12
Responses, when implemented, can have potential effects on/the project objectives and, as such, can generate additional risks.
These are known as secondary risks and have to be analyzed and planned for in the same way as those risks which were initially identified.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Secondary Risks

## Slide 13
It is never feasible or even desirable to eliminate all threats from a project.
Similarly, there is also a limit to the extent to which opportunities can be proactively managed.
There may be residual risks that will remain after the responses have been implemented.
These residual risks should be clearly identified, analyzed, documented, and communicated to all relevant stakeholders.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Residual Risks

## Slide 14
All the approved, unconditional actions arising from risk response planning should be integrated into the project management plan in order to ensure that they are carried out as part of normal project implementation.
The corresponding organizational and project management rules should also be invoked, including the following:-
  Project change management and configuration control
  Project planning, budgeting, and scheduling
  Resource management, and
  Project communication planning
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Project Integration

## Slide 15: PLAN RISK RESPONSES

## Slide 16
11.5
Risk Register
Risk Management Plan
____________
Inputs
1
Tools and Techniques
2
Outputs
3
Process 11.5
Plan Risk Responses
Risk Register Updates
Risk Related Contract Decisions
Project Management Plan Updates
Project Document Updates
____________
Reference: Figure 11.17.
PMBOK® Guide, 4th Ed
8
Risk
2
Planning
Strategies for Negative Risks or Threats
Strategies for Positive Risks or Opportunities
Contingent Response Strategies
Expert Judgment
___________
Process of developing options and actions to enhance opportunities and to reduce threats to project objectives.
Notes: Picture with three text columns
(Intermediate)
To reproduce the picture effects on this slide, do the following:
On the Home tab, in the Slides group, click Layout, and then click Blank.
On the Insert tab, in the Illustrations group, click Picture.
In the Insert Picture dialog box, select a picture and then click Insert.
Select the picture. Under Picture Tools, on the Format tab, in the bottom right corner of the Size group, click the Size and Position dialog box launcher.
In the Size and Position dialog box, on the Size tab, resize or crop the picture as needed so that under Size and rotate, the Height box is set to 1.48” and the Width box is set to 9.17”. Resize the picture under Size and rotate by entering values into the Height and Width boxes. Crop the picture under Crop from by entering values into the Left, Right, Top, and Bottom boxes.
On the Home tab, in the bottom right corner of the Drawing group, click the Format Shape dialog box launcher. In the Format Shape dialog box, click Line Color in the left pane, select Gradient line in the right pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Up (second row, second option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
Also in the Format Shape dialog box, click Line Style in the left pane, and then in the right pane, in the Width box, enter 1 pt.
On the Home tab, in the Drawing group, click Shape Effects, point to Glow, and then do the following:
  Under Glow Variations, select any option in the first row (5 pt glow options).
  Point to More Glow Colors, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
On the Home tab, in the Drawing group, click Arrange, point to Align, and then click Align Center.
To reproduce the first column heading on this slide, do the following:
On the Home tab, in the Drawing group, click Shapes, and then under Rectangles, click Rectangle (first option from the left). On the slide, drag to draw a rectangle.
Under Drawing Tools, on the Format tab, in the Size group, do the following:
  In the Shape Height box, enter 1”.
  In the Shape Width box, enter 2.92”.
On the Home tab, in the bottom right corner of the Drawing group, click the Format Shape dialog box launcher. In the Format Shape dialog box, click Fill in the left pane, select Gradient fill in the right pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Down (first row, second option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 32%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2 (first row, third option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2, Darker 25% (third row, third option from the left).
Also in the Format Shape dialog box, click Line Color in the left pane, select Gradient line in the Line Color pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Up (second row, second option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
Also in the Format Shape dialog box, click Line Style in the left pane. In the right pane, in the Width box, enter 1 pt.
On the Home tab, in the Drawing group, click Shape Effects, point to Glow, and then do the following:
  Under Glow Variations, select any option in the first row (5 pt glow options).
  Point to More Glow Colors, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
On the slide, right-click the rectangle and then click Edit Text.
Enter text in the text box and select the text. On the Home tab, in the Font group, select Gill Sans MT from the Font list and then select 24 from the Font Size list.
On the Home tab, in the Paragraph group, click Align Text Left to align the text left within the text box.
Under Drawing Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click Tan, Background 2, Darker 75% (fifth row, third option from the left).
On the Home tab, in the bottom-right corner of the Drawing group, click the Format Shapes dialog box launcher. In the Format Shapes dialog box, click Text Box in the left pane. In the right pane, under Internal margin, enter 1” in the Left box to increase the left margin in the rectangle to accommodate the embossed number.
On the Home tab, in the Drawing group, click Shapes, and then under Lines, click Line (first option from the left).
Press and hold SHIFT, and then on the slide, drag to draw a straight, vertical line.
Under Drawing Tools, on the Format tab, in the Size group, in the Width box, enter 0.75”.
On the Home tab, in the bottom-right corner of the Drawing group, click the Format Shapes dialog box launcher. In the Format Shapes dialog box, click Line Style in the left pane, and then do the following in the right pane:
  In the Width box, enter 2.25 pt.
  Click the button next to Dash type, and then click Round Dot (second option from the top).
Also in the Format Shapes dialog box, click Line Color in the left pane. In the right pane, click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
On the slide, drag the line onto the rectangle, just left of the text box.
On the Insert tab, in the Text box, click Text Box and then on the slide, drag to draw another text box.
Enter 1 in the text box and select the text. On the Home tab, in the Font group, select Calisto MT from the Font list and then enter 50 in the Font Size box.
On the Home tab, in the Paragraph group, click Center to center the text within the text box.
Under Drawing Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click Tan, Background 2, Darker 25% (third row, third option from the left).
Drag the text box onto the rectangle, left of the dotted vertical line.
On the Home tab, in the Editing group, click Select, and then click Selection Pane.
In the Selection and Visibility pane, press and hold CTRL to select the text box, line, and rectangle.
On the Home tab, in the Drawing group, click Arrange, point to Align, and then click Align Middle.
  To reproduce the other column headings on this slide, do the following:
On the Home tab, in the Editing group, click Select, and then click Selection Pane.
In the Selection and Visibility pane, press and hold CTRL to select the text box, line, and rectangle.
On the Home tab, in the Drawing group, click Arrange, and then under Group Objects click Group.
On the Home tab, in the Clipboard group, click the arrow under Paste, and then click Duplicate. Repeat the process until you have a total of three groups of shapes.
Select each group in the Selection and Visibility pane and drag it on the slide to form a row under the picture.
Also in the Selection and Visibility pane, press and hold CTRL and select all three groups. On the Home tab, in the Drawing group, click Arrange, point to Align, and then do the following:
  Click Align Middle.
  Click Distribute Horizontally.
  To change the numbers in the duplicate text boxes (second and third from the left), click in each text box and edit the text.
To reproduce the first column (the “subtext” portion) on this slide, do the following:
On the Home tab, in the Drawing group, click Shapes, and then under Rectangles click Rectangle (first option from the left).
On the slide, drag to draw the rectangle so that the top edge is just below the first column heading and the bottom edge is at the bottom of the slide.
Under Drawing Tools, on the Format tab, in the Size group, in the Shape Width box, enter 2.92” so that the subtext column is the same width as the column heading above it.
On the Home tab, in the Drawing group, click the arrow next to Shape Outline, and then click No Outline.
On the Home tab, in the bottom right corner of the Drawing group, click the Format Shape dialog box launcher. In the Format Shape dialog box, click Fill in the left pane, select Gradient fill in the right pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Down (first row, second option from the left).
  Under Gradient stops, click Add or Remove until three stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
    In the Transparency box, enter 100%.
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 50%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2, Darker 25% (third row, third option from the left).
    In the Transparency box, enter 25%.
  Select Stop 3 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
    In the Transparency box, enter 100%.
On the slide, right-click the column and then click Edit Text.
Enter text in the text box and select the text. On the Home tab, in the Font group, select Gill Sans MT from the Font list and then enter 22 in the Font Size box.
On the Home tab, in the Paragraph group, click Center to center the text within the rectangle.
Under Drawing Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click White, Background 1, Darker 50% (sixth row, first option from the left).
On the Home tab, in the bottom-right corner of the Drawing group, click the Format Shapes dialog box launcher. In the Format Shapes dialog box, click Text Box in the left pane. In the right pane, under Text layout, in the Vertical Alignment list, select Top.
To reproduce the other columns (the “subtext” portion) on this slide, do the following:
Select the first “subtext” rectangle. On the Home tab, in the Clipboard group, click the arrow under Paste, and then click Duplicate. Repeat the process until you have a total of three “subtext” rectangles.
Drag each duplicate on the slide to form a row under the “text heading” rectangles.
Press and hold SHIFT and select all three “subtext” rectangles. On the Home tab, in the Drawing group, click Arrange, point to Align, and then click Distribute Horizontally.
To reproduce the background on this slide, do the following:
Right-click the slide background area, and then click Format Background. In the Format Background dialog box, click Fill in the left pane, select Gradient fill in the right pane, and then do the following:
  In the Type list, select Radial.
  Click the button next to Direction, and then click From Center (third option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2 (first row, third option from the left).

## Slide 17
PLAN RISK RESPONSES
Reference: Figure 11.19.
PMBOK® Guide, 5th Ed

## Slide 18
PLAN RISK RESPONSES
Reference: Figure 11.18.
PMBOK® Guide, 4th Ed

## Slide 19: Reducing the Risk
Hazard Prevention
Risk Avoidance
Risk Transfer
Likelihood Reduction
Contingency Planning

## Slide 20: Risk Analysis - Factors
Risk Exposure
Confidence of the risk assessment
Compound Risks
The number of Risks
Cost of Action
  Risk Reduction Leverage – Cost Benefit

## Slide 21: Risk Response Strategies (-ive)
Mitigation
(Corrective action)
Avoidance
(Prevention)
Acceptance
(Accept consequences)
Transference
(Shift Responsibility)
Notes: Avoidance - eliminating a specific threat, usually by eliminating the cause.
Mitigation - reducing the expected monetary value of a risk event by reducing the probability of occurrence, reducing the risk event value, or both.
Acceptance - accepting the consequences.
  Active - developing a contingency plan
  Passive - accepting a lower profit if some activities overrun

## Slide 22: RISK RESPONSE STRATEGIES
NEGATIVE STRATEGIES
AVOID
TRANSFER
MITIGATE
ACCEPT
POSITIVE STRATEGIES
ENHANCE
SHARE
EXPLOIT
ACCEPT

## Slide 23
Results from a Monte Carlo Simulation of a Project Schedule
Days After Project Start
0
10
20
30
40
50
60
70
80
90
100
110
120
130
140
150
160
170
180
190
200
Cumulative Probability
This S-curve shows the cumulative probability of project completion by a particular date. For example, the intersection of the dashed ones shows that there is a 50 percent probability that the project will be finished within 145 days of its start. Project completion dates toward the left have higher risk while those toward the right have lower risk.

## Slide 24: Classes of Contractual Documents
Spectrum of risk
CPPC
CPFF
CPIF
FPI
FFP
Cost Plus Fixed
Fee (CPFF)
Cost Plus Incentive Fee (CPIF)
Variable Sharing Ratio
Firm Fixed Price
0 100
Cost Plus Percentage of Costs (CPPC)
100 0
Fixed Price Incentive (FPI)
Seller Risk
LOW
HIGH
Buyer Risk
HIGH
LOW
Notes: Click to add text

## Slide 25: Insurable Risk
Direct property damage – Insurance of principal assets, e.g., equipment, materials, property, auto
Indirect consequential loss – Indirect loss suffered by third party, resulting from actions by the contractor
Legal liability – Design errors, public bodily injury, project-performance failure
Personnel – Bodily injury
Wrap-up insurance – All the above integrated into one agreement – usually provided by the owner

## Slide 26
PLAN RISK RESPONSES
Critical Success Factors
UNIT 10

## Slide 27
PLAN RISK RESPONSES
Critical Success Factors
8.2.1 Communicate
8.2.2 Define Roles and Responsibilities
8.2.3 Specify Timing of Responses
8.2.4 Provide resources, budget and schedule
8.2.5 Address interactions of risks and responses
8.2.6 Ensure appropriate, timely, effective, and agreed-upon responses
8.2.7 Address threats and opportunities
8.2.8 Develop strategies
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 28
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
PLAN RISK RESPONSES
Critical Success Factors

## Slide 29
PLAN RISK RESPONSES
Critical Success Factors
8.2.1 Communicate
Communication with the various stakeholders should be maintained in an open and appropriate manner.
The resulting plans are disseminated and approval obtained in order to ensure full acceptance by all stakeholders.
Organizational causes of risk should be addressed openly
  Culture
  Attitudes
  Disagreements concerning objectives
This may require involving high levels of the organization’s management and other stakeholders.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 30
PLAN RISK RESPONSES
Critical Success Factors
8.2.2 Define Roles and Responsibilities
The risk response success will be dependent upon the full support and involvement of the project team and other stakeholders.
The key roles for Project Risk Management are those of risk owner and risk action owner.
A single risk owner should be assigned to every identified risk, and each agreed-upon risk response should have a single risk action owner.
The people with the corresponding responsibilities should be aware of what is expected of them, and the other project stakeholders should understand and accept the needs and authority of these roles.
Management may take ownership of risks with political, organizational causes.
In addition, senior management should approve and track associated risk-related contingency reserves.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 31
PLAN RISK RESPONSES
Critical Success Factors
8.2.3 Specify Timing of Responses
Agreed-upon responses should be integrated into the project management plan and will therefore be scheduled and assigned for execution.
The responses that depend on uncertain conditions should be monitored so as to be performed if the conditions warrant them.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 32
PLAN RISK RESPONSES
Critical Success Factors
8.2.4 Provide Resources, Budget, and Schedule for Responses
Each response should be planned in detail in accordance with the methodology of the project and integrated into the project management plan. It entails,
  Estimating the resources, costs, and duration
  Updating the budget and schedule
  Obtaining approval from management
  Obtaining commitment from the risk owners and risk action owners.
Management’s role at this stage is vital for
  Supporting the project manager in developing risk responses and
  Authorizing the corresponding resources.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 33
PLAN RISK RESPONSES
Critical Success Factors
8.2.5 Address interactions of risks and responses
Responses may be developed to address risks related by:-
  Cause and effect, or
  Common root cause
Categorization of risks may help identify and address responses, by using tools such as
  Risk Breakdown structure
  Affinity Diagram
  Other categorization tools
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 34
PLAN RISK RESPONSES
Critical Success Factors
8.2.5 Address interactions of risks and responses
There is also a need during the Plan Risk Responses process to consider the risks aggregated during the Perform Quantitative Risk Analysis process and then develop generic responses where possible.
Another interaction effect that may occur is when one risk, if it occurs, may affect the probability or impact of other risks.
Deciding on the response strategy may require a compromise, since some proposed responses may be mutually exclusive or counterproductive.
Mitigating a threat to time could cost money, thereby increasing pressure on the budget.
Risk response planning also needs to take a holistic view of all proposed responses and make sure they are coherent.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 35
PLAN RISK RESPONSES
Critical Success Factors
8.2.5 Address interactions of risks and responses
The challenge therefore in planning responses to risks is the need to control the potential effects of the strategy developed for treating the original risk.
If this is overlooked, the total level of threat in a project can actually increase, or the potential for opportunities can be compromised.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 36
PLAN RISK RESPONSES
Critical Success Factors
8.2.6 Ensure appropriate, timely, effective, and agreed-upon responses
In general, responses should be appropriate, timely, cost-effective, feasible, achievable, agreed-upon, assigned and accepted.
Any proposed risk response plan needs to be assessed against the following criteria:-
  Consistency with organizational values, project objectives, and stakeholder expectations.
  Technical feasibility
  Ability of the project team or risk action owners outside the project to carry out the corresponding actions
  Balance between overall impact of the response on the project objectives and the improvement in the risk profile of the project.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 37
PLAN RISK RESPONSES
Critical Success Factors
8.2.7 Address threats and opportunities
Risk response planning should combine responses that address the threats as well as those that provide for opportunities into a single, integrated plan.
If either threats or opportunities are not fully addressed, the combined set of response strategies will be incomplete and may even be invalid.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 38
PLAN RISK RESPONSES
Critical Success Factors
8.2.8 Develop strategies before tactical responses
Risk response planning should be carried out in an open-minded manner rather than adopting the first response that seems to be feasible.
The responses should be planned at a general, strategic level and the strategy validated and agreed upon, prior to detailed tactical approach.
Once the responses have been planned at a strategic level, they should be expanded into actions at the tactical level and integrated into the project management plan.
This activity may generate additional secondary risks, which will need to be addressed at this time.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 39
PLAN RISK RESPONSES
Risk Response Strategies
UNIT 10

## Slide 40
PLAN RISK RESPONSES
Risk Response Strategies
8.3.1
8.3.2
8.3.3
8.3.4
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Avoid a Threat
Transfer
Mitigate
Accept
Exploit an Opportunity
Share
Enhance
Accept
Threats /
Negative Risks
Opportunities /
Positive Risks
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 41
PLAN RISK RESPONSES
Risk Response Strategies
8.3.1 Avoid a Threat / Exploit an Opportunity
8.3.2 Transfer a Threat / Share an Opportunity
This strategy involves taking the actions required to address a threat or an opportunity in order to ensure either that the threat cannot occur or can have no effect on the project, or that the opportunity will occur and the project will be able to take advantage of it.
This strategy entails transference to a third party that is better positioned to address a particular threat or opportunity.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 42
PLAN RISK RESPONSES
Risk Response Strategies
8.3.3 Mitigate a Threat / Enhance an Opportunity
8.3.4 Accept a Threat / Accept an Opportunity
Mitigation and enhancement are the most widely applicable response strategies.
Here, the approach is to identify actions that will decrease the probability and/or the impact of a threat, and increase the probability and/or impact of an opportunity.
This strategy applies when the other strategies are not considered applicable or feasible.
Acceptance entails taking no action unless the risk actually occurs, in which case contingency or fallback plans may be developed ahead of time, to be implemented if the risk presents itself.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 43
PLAN RISK RESPONSES
Risk Response Strategies
8.3.5 Applying Risk Response Strategies to
Overall Project Risk
In addition to responding to individual risks, the four risk response strategies can be applied to address overall project risk as follows:-
  Cancel the project, as a last resort, if the overall level of risk remains unacceptable.
  Set up a business structure in which the customer and the supplier share the risk.
  Re-plan the project or change the scope and boundaries of the project, e.g., by modifying the project priority, resource allocations, delivery calendar, etc.
  Pursue the project despite a risk exposure that exceeds the desired level.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 44
PLAN RISK RESPONSES
Tools and Techniques
UNIT 10

## Slide 45
PLAN RISK RESPONSES
Tools and Techniques
There are four categories of tools and techniques, as follows:-
8.4.1 Creativity tools to identify potential responses
8.4.2 Decision-support tools for determining the optimal potential response.
8.4.3 Strategy implementation techniques designed to turn a strategy into action
8.4.4 Tools to transfer control to the Monitor and Control Risks process
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 46
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 47
PLAN RISK RESPONSES
Tools and Techniques
8.4.1 Response Identification
Risk Response Planning builds on the available information about the potential risks and aims to determine the optimal set of responses.
For this reason, it should involve subject matter experts and employ creativity techniques in order to explore all of the options.
Project planning and execution techniques are then required to evaluate the potential effects of the various options of the various options on the project’s objectives.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 48
PLAN RISK RESPONSES
Tools and Techniques
8.4.2 Response Selection
Once the set of potential responses for the risks being addressed is established, decision-support techniques may need to be applied to select the best possible subset from these responses.
The selection process should take into account the cost of the responses, the impact on the project objectives, uncertainty of outcomes and the possible secondary and residual risks.
The Identify Risks, Perform Quantitative Risk Analysis, and Plan Risk Responses processes may then need to be applied to the resultant project management plan and the residual and secondary risks that it would entail.
This iterative approach continues until all of the individual risks are deemed acceptable and the overall risk is within a predefined threshold.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 49
PLAN RISK RESPONSES
Tools and Techniques
8.4.3 Action Planning
Project planning tools are used to turn the chosen strategies into concrete actions and to integrate these into existing plans.
The corresponding actions may be unconditional (i.e., integrated into the project management plan) or contingent on a trigger condition and predefined as a contingency response strategy.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 50
PLAN RISK RESPONSES
Tools and Techniques
8.4.4 Ownership and Responsibility Assignment
The project manager needs to use resource assignment processes to ensure the availability of an owner for each risk and for each response action, so that each associated risk is managed and each corresponding risk response is carried out in a timely and effective manner.
To enable risk monitoring to identify the imminence or actual occurrence of the corresponding event, every contingency response strategy should include a set of trigger conditions.
The responsibility for monitoring these conditions should be clearly assigned in the Plan Risk Responses process and managed in the Monitor and Control Risks process.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 51
PLAN RISK RESPONSES
Tools and Techniques
8.4.4 Ownership and Responsibility Assignment
The strategic definition of risk responses should include measurable criteria for success of the response.
Risk action owners should monitor their assigned risks, take agreed-upon actions as required, and provide the risk owners with relevant information on status or changes to the risk characteristics.
Risk owners should assess the effectiveness of any actions, decide whether additional actions are required, and keep the project manager informed of the situation.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 52
PLAN RISK RESPONSES
Documenting the Results
UNIT 10

## Slide 53
PLAN RISK RESPONSES
Documenting the Results
Risk response planning is based on the information placed in the risk register during execution of the Identify Risks and Perform Analysis processes.
The corresponding risk response information is often referred to as the risk response plan, although it may in fact be integral part of the risk register.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 54
PLAN RISK RESPONSES
Documenting the Results
8.5.1 Add Risk Responses to the Risk Register
The response-related information for each risk is recorded in the risk register and updated regularly.
Any interested stakeholder should be able to rapidly access all the information required to verify their responsibilities and manage the risks in accordance with the risk response plan.
The set of residual risks and their priorities are clearly identified and recorded.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 55
PLAN RISK RESPONSES
Documenting the Results
8.5.2 Add Corresponding Risk Responses to the Project Management Plan
While developing the detailed set of risk responses, the project-related implications are evaluated for inclusion in a modified project management plan.
These include costs, resource assignments, scheduling details. And changes to project documentation.
Until these changes are formally approved along with the additional risks that they may carry, risk response planning cannot be considered complete.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 56
PLAN RISK RESPONSES
Documenting the Results
8.5.3 Review and Document Predicted Exposure
Once the risk responses have been defined and integrated into the project management plan, the individual and overall residual risks related to this plan are evaluated in order to determine whether additional response planning is required.
This evaluation should provide an estimate of both the expected post-response situation and the potential improvement of the risk exposure assuming that the proposed responses are effective.
The evaluation should be documented.
UNIT 10
From Practice Standard for Project Risk Management, 1st Ed, PMI
Notes: ROLE OF PROJECT RISK MGMT
In Corporate Business Management
Two Basic Types in Corporate Business Management:-
Business Risk
  Inherent chances of both profit and loss associated with the particular business endeavor.
  Business entities employ skilled staff to increase the chances of profit and reduce the chances of loss.
  The essential purpose is to maximize profits.
Pure or Insurable Risk
  Involves only a chance for loss and no chance for profit.
  Insurable risks can be further sub-divided into four categories:-
    Direct property loss
    Indirect property loss
    Liability loss
    Personal loss

## Slide 57
Review Questions
UNIT 9

## Slide 58
THE END
THANK YOU
The End